## README
Workbook guide
How to use
• Start on the Dashboard tab for high-level KPIs and charts.
• Use the navigation links on the Dashboard (and the 'Home' link on each sheet) to jump around.
• The Detail tab contains all 867 line items from Project_Detail.csv (filterable).
• Summary tabs (Packages/CBS/Methods) roll up Detail using Excel formulas (SUMIFS/COUNTIFS).
• Assumptions and Risks tabs contain the consolidated registers from the markdown files.
• Inputs tab contains mappings (Package → Category) and contingency rates by CBS bucket.
Notes
Contingency in BOE has minor internal inconsistencies (Executive Summary vs bucket table). This workbook uses the BOE §7.2 bucket rates for calculations and shows the delta vs the BOE stated total.
Data sources (local files)
• Project_Detail.csv
• Project_BOE.md
• Consolidated_Assumptions.md
• Consolidated_Risks.md
Go to Dashboard

## Dashboard
Canola Oil Transload Facility — Estimate Dashboard
Data snapshot: 2026-01-29 (from source files)
Navigate: |  | Base estimate (calc.) | Contingency (calc.) | Total estimate (calc.)
Package roll-up
CBS roll-up
Pricing methods
All line items (867)
Assumptions (groups) |  | BOE stated total | BOE stated contingency | Delta (calc - BOE)
Assumptions (items) |  | 117100000 | 24700000
Risks (groups)
Risks (items)
BOE reference
Inputs / lookups |  | # Packages | # Deliverables | # Line items
Read me |  | 36 | 202 | 867
|  | Assumptions (groups) | Assumptions (raw) | Risks (groups)
|  | 311 | 588 | 120
|  | Risks (raw) | Pricing date | Estimate class
|  | 297 | January 2026 | Class 5 (Order of Magnitude)
Charts
Package | Total | Category
PKG-13
PKG-08
PKG-14
PKG-30
PKG-04
PKG-10
PKG-17
PKG-02
PKG-16
PKG-26
Category | Base
Site & Civil
Structural
Mechanical
Electrical & I&C
Buildings & Protection
Project Execution
Risk category | Groups
UNCATEGORIZED | 46
RSK-SCOPE | 27
RSK-INTF | 15
RSK-TECH | 8
RSK-PRICE | 7
RSK-QUAL | 4
RSK-SCHED | 4
RSK-QTY | 3
RSK-ENV | 2
RSK-PROD | 2
RSK-ESC | 1
Assumption category | Groups
ASM-PRICE | 123
UNCATEGORIZED | 96
ASM-LABOR | 28
ASM-QTY | 17
ASM-INTF | 13
ASM-ENG | 12
ASM-TECH | 12
ASM-SCOPE | 10

## Summary_Packages
Package summary (computed from Detail) | [7 empty] | Home
Package | Description | PackageCategory | Confidence | Base | Contingency | Total | LineItems
PKG-00 | Site Establishment | Site & Civil | LOW
PKG-01 | Demolition & Removals | Site & Civil | LOW
PKG-02 | Earthworks & Ground Improvement | Site & Civil | LOW
PKG-03 | Underground Utilities & Drainage | Site & Civil | LOW
PKG-04 | Pavement & Surfacing | Site & Civil | LOW
PKG-05 | Concrete Structures | Structural | LOW
PKG-06 | Structural Steelwork | Structural | LOW
PKG-07 | Rail Works | Structural | LOW
PKG-08 | Marine Structures | Structural | LOW
PKG-09 | Marine Outfitting | Structural | LOW
PKG-10 | Railcar Unloading System | Mechanical | LOW
PKG-11 | Marine Loading System | Mechanical | LOW
PKG-12 | Product Transfer & Metering | Mechanical | LOW
PKG-13 | Storage Tanks | Mechanical | LOW
PKG-14 | Process Piping | Mechanical | LOW
PKG-15 | Pumps & Rotating Equipment | Mechanical | LOW-MED
PKG-16 | Valves & Specialty Equipment | Mechanical | LOW
PKG-17 | Electrical Power Distribution | Electrical & I&C | LOW
PKG-18 | Lighting | Electrical & I&C | LOW
PKG-19 | Control Systems | Electrical & I&C | LOW
PKG-20 | Field Instrumentation | Electrical & I&C | LOW
PKG-21 | Buildings (MCC/Shelters) | Buildings & Protection | LOW
PKG-22 | Building Interior & MEP | Buildings & Protection | LOW
PKG-23 | Fire Protection | Buildings & Protection | LOW
PKG-24 | Security Systems | Buildings & Protection | LOW
PKG-25 | Communications & IT | Buildings & Protection | LOW
PKG-26 | Protective Coatings & Painting | Buildings & Protection | LOW-MED
PKG-27 | Insulation | Project Execution | LOW
PKG-28 | Design Verification | Project Execution | LOW
PKG-29 | Testing | Project Execution | LOW
PKG-30 | Commissioning | Project Execution | LOW-MED
PKG-31 | Documentation | Project Execution | LOW
PKG-32 | Regulatory & Permits | Project Execution | LOW
PKG-33 | HSE Management | Project Execution | LOW
PKG-34 | Coordination & Interfaces | Project Execution | LOW
PKG-35 | Training & Handover | Project Execution | LOW

## Summary_CBS
CBS summary (computed from Detail) | [5 empty] | Home
CBS | Base | Rate | Contingency | Total | Share_of_Total
MAT
CD
E
PM
CI
COM
P
FRT
TOTAL |  |  |  |  | 100%

## Summary_Methods
Pricing method summary (computed from Detail) |  |  |  | Home
Method | LineItems | Base | Share_of_Base
ALLOWANCE
CAD
PARAMETRIC
RATE_TABLE

## Assumptions_Groups
Assumptions — consolidated groups | [7 empty] | Home
CategoryCode | Category | GroupID | GroupTitle | Theme | PackagesCount | Packages | ItemsCount
ASM-ENG | Engineering Effort | ASM-ENG-001 | Design Calculations Effort | Design Calculations Effort | 8 | PKG-05, PKG-06, PKG-08, PKG-10, PKG-11, PKG-17, PKG-20, PKG-21 | 8
ASM-ENG | Engineering Effort | ASM-ENG-002 | Calculations |  | 1 | PKG-13 | 1
ASM-ENG | Engineering Effort | ASM-ENG-003 | Design Codes and Standards |  | 1 | PKG-23 | 1
ASM-ENG | Engineering Effort | ASM-ENG-004 | Drawings |  | 1 | PKG-13 | 1
ASM-ENG | Engineering Effort | ASM-ENG-005 | Engineering Design Effort (6 Deliverables) |  | 1 | PKG-22 | 1
ASM-ENG | Engineering Effort | ASM-ENG-006 | Engineering Drawing Effort |  | 1 | PKG-20 | 1
ASM-ENG | Engineering Effort | ASM-ENG-007 | Engineering design at approximately 11% of construction value |  | 1 | PKG-21 | 1
ASM-ENG | Engineering Effort | ASM-ENG-008 | Engineering effort estimated at **3,400 hours** across 5 deliverables |  | 1 | PKG-16 | 1
ASM-ENG | Engineering Effort | ASM-ENG-009 | Lighting poles designed for NBCC 2020 seismic and wind loads for Surrey, BC loca... |  | 1 | PKG-18 | 1
ASM-ENG | Engineering Effort | ASM-ENG-010 | Shop Drawings and Submittals |  | 1 | PKG-22 | 1
ASM-ENG | Engineering Effort | ASM-ENG-011 | Specifications |  | 1 | PKG-13 | 1
ASM-ENG | Engineering Effort | ASM-ENG-012 | Three HMI workstations: 2 operator stations + 1 engineering station |  | 1 | PKG-19 | 1
ASM-INTF | Interface & Coordination | ASM-INTF-013 | Interface Dependencies | Interface Dependencies | 1 | PKG-22 | 4
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 |  | 4 | PKG-27, PKG-28, PKG-29, PKG-30 | 73
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source |  | 2 | PKG-24, PKG-25 | 41
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 |  | 1 | PKG-26 | 25
ASM-INTF | Interface & Coordination | ASM-INTF-017 | 40-60 HMI graphics screens for operator interface |  | 1 | PKG-19 | 1
ASM-INTF | Interface & Coordination | ASM-INTF-018 | Control system equipment installed in MCC building per PKG-21/22 |  | 1 | PKG-19 | 1
ASM-INTF | Interface & Coordination | ASM-INTF-019 | Coordination Meeting Records — DEL-34.01 |  | 1 | PKG-34 | 1
ASM-INTF | Interface & Coordination | ASM-INTF-020 | Interface Agreements — DEL-34.02 |  | 1 | PKG-34 | 1
ASM-INTF | Interface & Coordination | ASM-INTF-021 | Marine Coordination Records — DEL-34.03 |  | 1 | PKG-34 | 1
ASM-INTF | Interface & Coordination | ASM-INTF-022 | Marine loading system (PKG-11) requires **~25 valves** (loading arm isolation, f... |  | 1 | PKG-16 | 1
ASM-INTF | Interface & Coordination | ASM-INTF-023 | Product transfer and metering (PKG-12) requires **~30 valves** |  | 1 | PKG-16 | 1
ASM-INTF | Interface & Coordination | ASM-INTF-024 | Site Access and Temporary Works (PKG-06 Allocation) |  | 1 | PKG-06 | 1
ASM-INTF | Interface & Coordination | ASM-INTF-025 | Terminal Operations Coordination |  | 1 | PKG-23 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-026 | Installation Labor Rates | Installation Labor Rates | 5 | PKG-11, PKG-14, PKG-15, PKG-16, PKG-21 | 11
ASM-LABOR | Labor & Installation | ASM-LABOR-027 | Actuator hookup (pneumatic/electrical) adds **2-4 hours per actuated valve** |  | 1 | PKG-16 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-028 | Cable Tray and Conduit Installation Scope |  | 1 | PKG-17 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-029 | Construction Labor Productivity |  | 1 | PKG-23 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-030 | Construction Labor Rates (BC Lower Mainland) |  | 1 | PKG-22 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-031 | Control valve calibration and loop check (30 valves) estimated at **4 hours per ... |  | 1 | PKG-16 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-032 | Crane and Equipment for Steel Erection |  | 1 | PKG-06 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-033 | Distribution Panel Installation Scope |  | 1 | PKG-17 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-034 | Engineering Labor Hours |  | 1 | PKG-23 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-035 | Fire Water Loop Installation Productivity |  | 1 | PKG-23 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-036 | Grating Supply and Installation |  | 1 | PKG-06 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-037 | Grounding System Installation Scope |  | 1 | PKG-17 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-038 | Handrail Supply and Installation |  | 1 | PKG-06 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-039 | Instrument Installation Rate |  | 1 | PKG-20 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-040 | LV Switchgear Installation Scope |  | 1 | PKG-17 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-041 | MCC Installation Scope |  | 1 | PKG-17 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-042 | MEP Installation Productivity |  | 1 | PKG-22 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-043 | MV Switchgear Installation Scope |  | 1 | PKG-17 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-044 | Marine loading transient study requires ~180 hours specialist work |  | 1 | PKG-14 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-045 | Normal industrial site access; no special access constraints for control system ... |  | 1 | PKG-19 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-046 | Railcar unloading transient study requires ~200+ hours specialist work |  | 1 | PKG-14 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-047 | Relief valve field verification (20 valves) estimated at **2 hours per valve** |  | 1 | PKG-16 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-048 | Structural Steel Erection Labor |  | 1 | PKG-06 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-049 | Transformer Installation Scope |  | 1 | PKG-17 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-050 | UPS Installation Scope |  | 1 | PKG-17 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-051 | Valve installation assumes **standard site access** (no major rigging constraint... |  | 1 | PKG-16 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-052 | Valve installation duration estimated at **8-12 weeks** (field installation phas... |  | 1 | PKG-16 | 1
ASM-LABOR | Labor & Installation | ASM-LABOR-053 | Valve installation includes rigging, bolting, gasket installation, alignment, hy... |  | 1 | PKG-16 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | Material Quantities | 8 | PKG-05, PKG-10, PKG-11, PKG-14, PKG-15, PKG-16, PKG-18, PKG-21 | 40
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | Equipment Unit Pricing | 5 | PKG-10, PKG-11, PKG-14, PKG-16, PKG-18 | 36
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | Technical Specification Writing | 14 | PKG-00, PKG-01, PKG-05, PKG-06, PKG-08, PKG-10, PKG-11, PKG-14, PKG-16, PKG-17, PKG-19, PKG-20, PKG-21, PKG-32 | 16
ASM-PRICE | Pricing Allowances | ASM-PRICE-057 | Engineering Drawing Production | Engineering Drawing Production | 11 | PKG-00, PKG-01, PKG-05, PKG-06, PKG-08, PKG-10, PKG-11, PKG-14, PKG-17, PKG-19, PKG-21 | 12
ASM-PRICE | Pricing Allowances | ASM-PRICE-058 | Installation & Test Records | Installation & Test Records | 9 | PKG-05, PKG-06, PKG-08, PKG-10, PKG-11, PKG-13, PKG-14, PKG-17, PKG-20 | 9
ASM-PRICE | Pricing Allowances | ASM-PRICE-059 | Data Sheet Package | Data Sheet Package | 6 | PKG-06, PKG-10, PKG-11, PKG-17, PKG-19, PKG-21 | 6
ASM-PRICE | Pricing Allowances | ASM-PRICE-060 | 32 individual spill containment pans (one per unloading station) at $8,000/unit. |  | 1 | PKG-10 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-061 | 7 doors (6 personnel + 1 overhead) at $4,500 average |  | 1 | PKG-21 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-062 | API 610 process pump costs estimated as follows: |  | 1 | PKG-15 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-063 | Abutment Materials Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-064 | Actuator costs: Pneumatic $3k-$15k (size-dependent), Electric $8k-$40k (size-dep... |  | 1 | PKG-16 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-065 | Building Size for MEP Allowance Scaling |  | 1 | PKG-22 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-066 | Building commissioning coordination at $15,000 |  | 1 | PKG-21 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-067 | CEMP Compliance Monitoring Allowance |  | 1 | PKG-33 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-068 | Catwalk Structural Steel Supply Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-069 | Catwalk and Abutment Installation Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-070 | Commissioning Parametric Allowance |  | 1 | PKG-32 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-071 | Concrete testing and quality control services estimated at $65,000 CAD allowance... |  | 1 | PKG-05 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-072 | Containment sump construction at $45,000 |  | 1 | PKG-11 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-073 | Control system software licenses: $100,000 (DCS/PLC + HMI + historian) |  | 1 | PKG-19 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-074 | Correspondence Filing and Archiving Allowance |  | 1 | PKG-32 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-075 | Correspondence Register Setup and Maintenance Allowance |  | 1 | PKG-32 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-076 | Corrosion protection allowance of $35,000 for marine environment |  | 1 | PKG-21 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-077 | DEL-08.04 Marine Geotechnical Report Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-078 | DEL-08.06 Berthing Energy Report Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-079 | DEL-08.07 Fender Data Package Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-080 | DEL-08.08 Fender Supplier Verification Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-081 | DEL-08.09 Mooring Analysis Report Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-082 | DEL-08.10 Current Assessment Report Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-083 | DEL-08.11 Debris Loading Basis Note Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-084 | DFO Compliance Monitoring Allowance |  | 1 | PKG-32 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-085 | Defects Liability Support Allowance ($165,000) |  | 1 | PKG-35 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-086 | Demolition Materials and Temporary Works Allowance |  | 1 | PKG-01 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-087 | Demolition Procedures Allowance |  | 1 | PKG-01 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-088 | Demolition Records QA/QC Allowance |  | 1 | PKG-01 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-089 | Dolphin 2 Marine Demolition Allowance |  | 1 | PKG-01 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-090 | Door and window installation at $18,000 allowance |  | 1 | PKG-21 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-091 | E&I materials at $65,000 + installation at $100,000 |  | 1 | PKG-11 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-092 | EPCM/Project Management estimated at 6% of (CD + CI + MAT) = 6% × ($53,200 + $9,... |  | 1 | PKG-15 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-093 | Electrical Installation Materials Allowance |  | 1 | PKG-17 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-094 | Emergency Response Plan Allowance |  | 1 | PKG-33 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-095 | Equipment schedule documents (2 documents) estimated at $5,000 CAD allowance. |  | 1 | PKG-00 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-096 | Expansion joints/loops allowance $65,000 |  | 1 | PKG-14 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-097 | FAT $25,000 + SAT $20,000 + commissioning support $10,000 |  | 1 | PKG-19 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-098 | Fencing Removal Allowance |  | 1 | PKG-01 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-099 | Finishing and punch list allowance of $25,000 |  | 1 | PKG-21 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-100 | Fire Alarm System Installation Cost |  | 1 | PKG-23 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-101 | Fire Hydrant Installation Cost |  | 1 | PKG-23 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-102 | Fire Water Loop Installation Cost |  | 1 | PKG-23 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-103 | Foam System Installation Cost |  | 1 | PKG-23 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-104 | Foundation materials (concrete, piles, reinforcing) at $85,000 allowance |  | 1 | PKG-21 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-105 | Freight and Logistics Allowance |  | 1 | PKG-17 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-106 | Freight and Marine Logistics Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-107 | Ground liner system interface work (concrete curbs, anchors, terminations) estim... |  | 1 | PKG-05 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-108 | Handover Coordination Allowance ($85,000) |  | 1 | PKG-35 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-109 | Hydrostatic testing at $95,000 for ~10-15 test packages |  | 1 | PKG-14 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-110 | Initial spare parts estimated at 8% of pump equipment cost ($850,000 × 8% = $68,... |  | 1 | PKG-15 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-111 | Installation quality records and documentation: $32,000 |  | 1 | PKG-19 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-112 | Leak detection system at $85,000 supply + $35,000 install for 3-zone coverage |  | 1 | PKG-11 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-113 | Lighting circuit wiring and conduit from panels to fixtures: allowance $40,000-$... |  | 1 | PKG-18 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-114 | Lighting circuit wiring, conduit, and accessories: $40,000-$80,000 CAD allowance... |  | 1 | PKG-18 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-115 | Lighting controls installation and programming: $15,000-$40,000 CAD allowance. |  | 1 | PKG-18 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-116 | Limited industrial glazing allowance of $15,000 |  | 1 | PKG-21 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-117 | Loading Platform Steel Erection Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-118 | Loading Platform Structural Steel Supply Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-119 | Loading arm installation requires crane barge for heavy lift; included in instal... |  | 1 | PKG-11 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-120 | Marine Coatings and Touch-Up Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-121 | Marine Hardware Installation Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-122 | Marine Hardware and Miscellaneous Steel Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-123 | Marine Piling Installation Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-124 | Marine Piling Supply Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-125 | Mechanical seal systems and auxiliary equipment (seal flush systems, cooling wat... |  | 1 | PKG-15 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-126 | Method Statements Allowance |  | 1 | PKG-33 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-127 | Miscellaneous cables and terminations: $60,000 |  | 1 | PKG-19 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-128 | NDE and weld inspection at ~$250/weld for 500+ welds |  | 1 | PKG-14 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-129 | Nitrogen connection at $15,000 supply + $15,000 install |  | 1 | PKG-11 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-130 | Occupational Health & Safety Plan Allowance |  | 1 | PKG-33 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-131 | Permit Application Engineering Allowance |  | 1 | PKG-32 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-132 | Permit Fees Allowance |  | 1 | PKG-32 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-133 | Permit Receipt and Tracking PM Allowance |  | 1 | PKG-32 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-134 | Post-works road survey, deficiency identification, and closeout estimated at $18... |  | 1 | PKG-00 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-135 | Pre-works road survey and photo documentation estimated at $15,000 CAD allowance... |  | 1 | PKG-00 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-136 | Printing & Binding Costs - Drawings |  | 1 | PKG-31 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-137 | Printing & Binding Costs - Manuals |  | 1 | PKG-31 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-138 | Procurement Services Parametric Allowance |  | 1 | PKG-32 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-139 | Procurement services estimated at 2% of equipment cost ($850,000 × 2% = $17,000)... |  | 1 | PKG-15 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-140 | Project Management Parametric Allowance |  | 1 | PKG-32 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-141 | Pump couplings and fabricated baseplates estimated at 12% of pump cost. |  | 1 | PKG-15 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-142 | QA/QC inspection and envelope testing at $18,000 |  | 1 | PKG-21 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-143 | Regulatory/Environmental Consultant Support Allowance |  | 1 | PKG-32 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-144 | Relief valve set pressure testing performed at **vendor FAT** (included in valve... |  | 1 | PKG-16 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-145 | Risk Assessments Allowance |  | 1 | PKG-33 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-146 | Road access and security process documents (3 plans) estimated at $8,000 CAD all... |  | 1 | PKG-00 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-147 | Road deficiency remediation and restoration work estimated at $25,000 CAD allowa... |  | 1 | PKG-00 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-148 | SPPP Compliance Monitoring Allowance |  | 1 | PKG-33 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-149 | Salt Tent Dismantling Allowance |  | 1 | PKG-01 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-150 | Security gate hardware, access control system, and installation estimated at $75... |  | 1 | PKG-00 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-151 | Security gate staffing during construction estimated at $180,000 CAD allowance. |  | 1 | PKG-00 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-152 | Site Clearance QA/QC ($134,000) |  | 1 | PKG-35 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-153 | Site Reinstatement Allowance ($350,000) |  | 1 | PKG-35 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-154 | Site establishment procedures (3 procedures) estimated at $9,000 CAD allowance. |  | 1 | PKG-00 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-155 | Software development effort: $120,000 (PLC logic $80k + HMI $30k + historian $10... |  | 1 | PKG-19 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-156 | Sump pump package at $25,000 supply for 5 HP submersible |  | 1 | PKG-11 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-157 | Temporary facilities, laydown areas, utilities, fencing, and site infrastructure... |  | 1 | PKG-00 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-158 | Temporary water supply pipe, backflow preventer, connections, and installation e... |  | 1 | PKG-00 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-159 | Track 6 Rail Demolition Allowance |  | 1 | PKG-01 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-160 | Training Delivery Allowance ($395,000) |  | 1 | PKG-35 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-161 | Training Materials Development Allowance ($285,000) |  | 1 | PKG-35 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-162 | Training Records Management ($47,000) |  | 1 | PKG-35 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-163 | Transport Canada Compliance Monitoring Allowance |  | 1 | PKG-32 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-164 | Trestle Steel Erection Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-165 | Trestle Structural Steel Supply Allowance |  | 1 | PKG-08 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-166 | VFPA PER Compliance Monitoring Allowance |  | 1 | PKG-32 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-167 | Valve O&M manuals and documentation **included in valve supply cost** (no separa... |  | 1 | PKG-16 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-168 | Valve bolting and gaskets estimated at **5% of valve cost** |  | 1 | PKG-16 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-169 | Valve factory acceptance testing (FAT) **included in valve supply cost**; site a... |  | 1 | PKG-16 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-170 | Valve freight estimated at **8% of valve FOB cost** |  | 1 | PKG-16 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-171 | Valve installation equipment (crane, rigging, lifting gear) included in **CD ins... |  | 1 | PKG-16 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-172 | Valve nameplates and tags **included** in valve supply cost (no separate allowan... |  | 1 | PKG-16 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-173 | Waste Disposal and Hauling Allowance |  | 1 | PKG-01 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-174 | Waste Management Records Allowance |  | 1 | PKG-33 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-175 | Waterstops and joint materials for containment walls estimated at $45,000 CAD al... |  | 1 | PKG-05 | 1
ASM-PRICE | Pricing Allowances | ASM-PRICE-176 | Waterway Pollution Control Method Statement Allowance |  | 1 | PKG-33 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-177 | 2,000 meters of fiber optic cable for control network backbone |  | 1 | PKG-19 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-178 | Actuator distribution: 60% manual, 30% pneumatic, 10% electric (by valve count) |  | 1 | PKG-16 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-179 | Distribution Panels Quantity |  | 1 | PKG-17 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-180 | Estimated I/O count: 600-800 points based on facility scope |  | 1 | PKG-19 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-181 | Fire Hydrant Quantity |  | 1 | PKG-23 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-182 | Instrument Cable Quantity |  | 1 | PKG-20 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-183 | Junction Box Quantity |  | 1 | PKG-20 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-184 | Loading arm is single-arm configuration (not dual counterweighted arms) |  | 1 | PKG-11 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-185 | MV/LV Transformers Quantity and Sizing |  | 1 | PKG-17 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-186 | Major Equipment Count |  | 1 | PKG-31 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-187 | Motor Control Centers Quantity and Distribution |  | 1 | PKG-17 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-188 | Operational Systems Count |  | 1 | PKG-31 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-189 | Plumbing Fixture Count and Equipment |  | 1 | PKG-22 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-190 | Total Drawing Count |  | 1 | PKG-31 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-191 | Total valve count estimated at **220 valves** (30 control, 150 isolation, 20 rel... |  | 1 | PKG-16 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-192 | Trenchless Crossing Count — 2-4 Crossings |  | 1 | PKG-34 | 1
ASM-QTY | Quantity Assumptions | ASM-QTY-193 | Valve count by type: 30 control (13%), 150 isolation (68%), 20 relief (9%), 20 s... |  | 1 | PKG-16 | 1
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-194 | Construction Indirects Factor | Construction Indirects Factor | 3 | PKG-14, PKG-15, PKG-16 | 3
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-195 | Scope Exclusions | Scope Exclusions | 1 | PKG-16 | 2
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-196 | Cable Pulling and Termination Scope |  | 1 | PKG-17 | 1
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-197 | Electrical Testing and Commissioning Support Scope |  | 1 | PKG-17 | 1
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-198 | Fire Water Loop Piping Scope |  | 1 | PKG-23 | 1
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-199 | Grounding System Scope |  | 1 | PKG-17 | 1
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-200 | Lighting controls include occupancy sensing, daylight harvesting, and time sched... |  | 1 | PKG-18 | 1
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-201 | Phase 2 connection provisions included in DEL-14.01 scope |  | 1 | PKG-14 | 1
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-202 | Testing and Commissioning Scope |  | 1 | PKG-22 | 1
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-203 | Valve testing (DEL-16.05) included in **COM factor** (no separate testing line) |  | 1 | PKG-16 | 1
ASM-TECH | Technical Parameters | ASM-TECH-204 | Material Specification | Material Specification | 4 | PKG-11, PKG-14, PKG-16, PKG-18 | 5
ASM-TECH | Technical Parameters | ASM-TECH-205 | Contingency Percentage | Contingency Percentage | 1 | PKG-01 | 1
ASM-TECH | Technical Parameters | ASM-TECH-206 | All valves comply with **API/ASME/CSA standards** (premium quality; not economy-... |  | 1 | PKG-16 | 1
ASM-TECH | Technical Parameters | ASM-TECH-207 | Fire Water and Fire Alarm Material Pricing |  | 1 | PKG-23 | 1
ASM-TECH | Technical Parameters | ASM-TECH-208 | Foam System Material Pricing |  | 1 | PKG-23 | 1
ASM-TECH | Technical Parameters | ASM-TECH-209 | Gaskets, bolting, small fittings at ~5% of pipe material |  | 1 | PKG-14 | 1
ASM-TECH | Technical Parameters | ASM-TECH-210 | HVAC System Capacity and Equipment |  | 1 | PKG-22 | 1
ASM-TECH | Technical Parameters | ASM-TECH-211 | Instrument Environment Rating |  | 1 | PKG-20 | 1
ASM-TECH | Technical Parameters | ASM-TECH-212 | Interior process/warehouse area fixtures require IP54+ rating for dust and moist... |  | 1 | PKG-18 | 1
ASM-TECH | Technical Parameters | ASM-TECH-213 | Plumbing Piping Materials and Routing |  | 1 | PKG-22 | 1
ASM-TECH | Technical Parameters | ASM-TECH-214 | Structural Steel Material Supply (Fabricated Tonnage) |  | 1 | PKG-06 | 1
ASM-TECH | Technical Parameters | ASM-TECH-215 | Valve materials and coatings suitable for **C4/C5-M corrosion category** (coasta... |  | 1 | PKG-16 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-216 | Weather/Season Impact | Weather/Season Impact | 2 | PKG-10, PKG-11 | 2
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-217 | 40-50 I/O modules to support 600-800 I/O points |  | 1 | PKG-19 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-218 | 6-8 control cabinets (main panels + field junction boxes) |  | 1 | PKG-19 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-219 | 8 sump pumps for grouped containment drainage (4 pumps per zone × 2 zones). |  | 1 | PKG-10 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-220 | 8-10 industrial network switches for control network |  | 1 | PKG-19 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-221 | Access equip |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-222 | Actuators and accessories rated for **Class I, Division 2 / Zone 2** (Group D) h... |  | 1 | PKG-16 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-223 | Agitators |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-224 | Basic Process Control System (BPCS) only; no separate SIS |  | 1 | PKG-19 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-225 | Cable Routing Method |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-226 | Cable Tray Length and Type |  | 1 | PKG-17 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-227 | Calibration and Loop Testing |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-228 | Canola oil properties assumed as: |  | 1 | PKG-15 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-229 | Conduit Length and Type |  | 1 | PKG-17 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-230 | Construction Duration Assumption |  | 1 | PKG-33 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-231 | Construction Duration — 24-30 Months |  | 1 | PKG-34 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-232 | Construction Equipment Rental Rates |  | 1 | PKG-22 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-233 | Control Cable Length |  | 1 | PKG-17 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-234 | Control valve complexity: 50% standard globe, 30% ball/butterfly, 20% severe ser... |  | 1 | PKG-16 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-235 | Control valve positioners use **HART protocol** (digital communication with DCS) |  | 1 | PKG-16 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-236 | Crane |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-237 | Data Sheet Preparation |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-238 | Data sheets |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-239 | Defects Liability Period (12 Months) |  | 1 | PKG-35 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-240 | Document Management Software/Database |  | 1 | PKG-31 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-241 | ERC is integral with loading arm supply (not separate procurement) |  | 1 | PKG-11 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-242 | Electric motors and variable frequency drives (VFDs) estimated as: |  | 1 | PKG-15 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-243 | Electrical |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-244 | Emergency lighting covers code-minimum egress paths plus safety-critical operati... |  | 1 | PKG-18 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-245 | Environmental and HSE Compliance |  | 1 | PKG-22 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-246 | Exterior lighting poles: 30-40 ft height, steel or aluminum construction, galvan... |  | 1 | PKG-18 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-247 | Exterior lighting poles: 30-50 poles, steel or aluminum, 30-40 ft height, marine... |  | 1 | PKG-18 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-248 | External coating |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-249 | Fab QA |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-250 | Field Touch-Up Painting and Protective Coatings |  | 1 | PKG-06 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-251 | Fire Alarm Control Panel |  | 1 | PKG-23 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-252 | Fire Alarm Wiring and Conduit |  | 1 | PKG-23 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-253 | Fire Detection and Notification Devices |  | 1 | PKG-23 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-254 | Fire Sprinkler Piping and Fittings |  | 1 | PKG-22 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-255 | Fire Suppression System (Automatic Sprinklers) |  | 1 | PKG-22 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-256 | Fire Water Supply Source |  | 1 | PKG-23 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-257 | Fire Water Valves and Fittings |  | 1 | PKG-23 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-258 | Foam Concentrate Storage and Proportioning |  | 1 | PKG-23 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-259 | HSE Staffing Model Assumption |  | 1 | PKG-33 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-260 | HVAC Ductwork and Distribution |  | 1 | PKG-22 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-261 | Historian configured for 400-600 process and calculated tags |  | 1 | PKG-19 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-262 | Hydro test |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-263 | Instrument Conduit System |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-264 | Instrument Supports and Mounting |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-265 | Instrument Tubing and Fittings |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-266 | Instrumentation |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-267 | Interior Electrical (Building Services) |  | 1 | PKG-22 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-268 | Interior Finishes (Flooring, Walls, Ceilings) |  | 1 | PKG-22 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-269 | Internal coating |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-270 | Isolation valve hydrostatic testing performed as **part of piping hydrostatic te... |  | 1 | PKG-16 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-271 | LV Power Cable Length |  | 1 | PKG-17 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-272 | LV Switchgear Configuration |  | 1 | PKG-17 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-273 | MV Power Cable Length |  | 1 | PKG-17 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-274 | MV Switchgear Configuration |  | 1 | PKG-17 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-275 | Manholes |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-276 | Marine Loading Foam System |  | 1 | PKG-23 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-277 | Marine Loading Instrumentation |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-278 | Miscellaneous Switches |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-279 | NDE |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-280 | Nozzles |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-281 | OEM Training for 8 Major Systems |  | 1 | PKG-35 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-282 | Overflow |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-283 | Phase 2 |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-284 | Pipe Supports and Racks |  | 1 | PKG-06 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-285 | Product Classification |  | 1 | PKG-23 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-286 | Railcar Unloading Instrumentation |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-287 | Railcar unloading stations (32 stations) require **16 control valves** (one per ... |  | 1 | PKG-16 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-288 | Required illuminance levels assumed based on IESNA recommendations pending ER ex... |  | 1 | PKG-18 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-289 | Roof type |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-290 | Security Compliance Records — DEL-34.04 |  | 1 | PKG-34 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-291 | Shell courses |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-292 | Site Conditions |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-293 | Site Conditions and Access |  | 1 | PKG-22 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-294 | Stairs and Gangways (Fabricated Items) |  | 1 | PKG-06 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-295 | Standard industrial control system complexity (typical liquid terminal) |  | 1 | PKG-19 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-296 | Steel weight |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-297 | Storage tanks (3 tanks) require **~36 valves total** (12 per tank) |  | 1 | PKG-16 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-298 | Tank Foam Discharge Systems |  | 1 | PKG-23 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-299 | Tank Instrumentation Density |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-300 | Tank dimensions |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-301 | Tank sizing |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-302 | Three remote HMI panels at: railcar unloading area, tank farm, marine loading pl... |  | 1 | PKG-19 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-303 | Training Population (30-50 Personnel) |  | 1 | PKG-35 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-304 | Transfer Piping Instrumentation |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-305 | Trenchless Crossing Monitoring — DEL-34.05 |  | 1 | PKG-34 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-306 | Two redundant DCS/PLC controllers (primary and standby) |  | 1 | PKG-19 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-307 | UPS System Sizing |  | 1 | PKG-17 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-308 | Valve size distribution: 60% small (DN50-100), 30% medium (DN150-200), 10% large... |  | 1 | PKG-16 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-309 | Warranty and Spare Parts |  | 1 | PKG-22 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-310 | Water draw-off |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-311 | Weld Inspection and NDT |  | 1 | PKG-06 | 1

## Assumptions_Items
Assumptions — source items | [6 empty] | Home
CategoryCode | Category | GroupID | GroupTitle | Package | AssumptionID | Description
ASM-ENG | Engineering Effort | ASM-ENG-001 | Design Calculations Effort | PKG-05 | A-003 | Concrete structures design calculations (foundation calcs,..
ASM-ENG | Engineering Effort | ASM-ENG-001 | Design Calculations Effort | PKG-06 | A-003 | Structural Steel Design Calculations Effort
ASM-ENG | Engineering Effort | ASM-ENG-001 | Design Calculations Effort | PKG-08 | A-803 | DEL-08.03 Design Calculations Allowance
ASM-ENG | Engineering Effort | ASM-ENG-001 | Design Calculations Effort | PKG-10 | A-008 | DEL-10.03 Design Calculations engineering effort priced at..
ASM-ENG | Engineering Effort | ASM-ENG-001 | Design Calculations Effort | PKG-11 | A-009 | Design calculations require ~80 hours at $250/hr (senior p..
ASM-ENG | Engineering Effort | ASM-ENG-001 | Design Calculations Effort | PKG-17 | A-1703 | Electrical Power Design Calculations Allowance
ASM-ENG | Engineering Effort | ASM-ENG-001 | Design Calculations Effort | PKG-20 | A-013 | Design Calculation Effort
ASM-ENG | Engineering Effort | ASM-ENG-001 | Design Calculations Effort | PKG-21 | A-005 | Structural/foundation calculations at $45,000 allowance
ASM-ENG | Engineering Effort | ASM-ENG-002 | Calculations | PKG-13 | A-013 | Calculations
ASM-ENG | Engineering Effort | ASM-ENG-003 | Design Codes and Standards | PKG-23 | A-022 | Design Codes and Standards
ASM-ENG | Engineering Effort | ASM-ENG-004 | Drawings | PKG-13 | A-011 | Drawings
ASM-ENG | Engineering Effort | ASM-ENG-005 | Engineering Design Effort (6 Deliverables) | PKG-22 | A-006 | Engineering Design Effort (6 Deliverables)
ASM-ENG | Engineering Effort | ASM-ENG-006 | Engineering Drawing Effort | PKG-20 | A-011 | Engineering Drawing Effort
ASM-ENG | Engineering Effort | ASM-ENG-007 | Engineering design at approximately 11% of construction value | PKG-21 | A-003 | Engineering design at approximately 11% of construction va..
ASM-ENG | Engineering Effort | ASM-ENG-008 | Engineering effort estimated at **3,400 hours** across 5 deliverables | PKG-16 | A-1613 | Engineering effort estimated at **3,400 hours** across 5 d..
ASM-ENG | Engineering Effort | ASM-ENG-009 | Lighting poles designed for NBCC 2020 seismic and wind loads for Surrey, BC loca... | PKG-18 | A-1830 | Lighting poles designed for NBCC 2020 seismic and wind loa..
ASM-ENG | Engineering Effort | ASM-ENG-010 | Shop Drawings and Submittals | PKG-22 | A-021 | Shop Drawings and Submittals
ASM-ENG | Engineering Effort | ASM-ENG-011 | Specifications | PKG-13 | A-012 | Specifications
ASM-ENG | Engineering Effort | ASM-ENG-012 | Three HMI workstations: 2 operator stations + 1 engineering station | PKG-19 | A-004 | Three HMI workstations: 2 operator stations + 1 engineerin..
ASM-INTF | Interface & Coordination | ASM-INTF-013 | Interface Dependencies | PKG-22 | A-014 | Control System Interfaces (Coordination with PKG-19)
ASM-INTF | Interface & Coordination | ASM-INTF-013 | Interface Dependencies | PKG-22 | A-015 | Electrical Power Coordination (PKG-17 Interface)
ASM-INTF | Interface & Coordination | ASM-INTF-013 | Interface Dependencies | PKG-22 | A-016 | Fire Water Supply (PKG-23 Interface)
ASM-INTF | Interface & Coordination | ASM-INTF-013 | Interface Dependencies | PKG-22 | A-017 | Building Coordination (PKG-21 Interface)
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2701 | PKG-27 A-2701
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2702 | PKG-27 A-2702
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2703 | PKG-27 A-2703
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2704 | PKG-27 A-2704
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2705 | PKG-27 A-2705
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2706 | PKG-27 A-2706
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2707 | PKG-27 A-2707
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2708 | PKG-27 A-2708
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2709 | PKG-27 A-2709
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2710 | PKG-27 A-2710
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2711 | PKG-27 A-2711
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2712 | PKG-27 A-2712
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2713 | PKG-27 A-2713
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2714 | PKG-27 A-2714
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2715 | PKG-27 A-2715
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2716 | PKG-27 A-2716
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2717 | PKG-27 A-2717
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2718 | PKG-27 A-2718
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-27 | A-2719 | PKG-27 A-2719
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2801 | PKG-28 A-2801
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2802 | PKG-28 A-2802
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2803 | PKG-28 A-2803
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2804 | PKG-28 A-2804
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2805 | PKG-28 A-2805
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2806 | PKG-28 A-2806
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2807 | PKG-28 A-2807
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2808 | PKG-28 A-2808
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2809 | PKG-28 A-2809
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2810 | PKG-28 A-2810
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2811 | PKG-28 A-2811
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2812 | PKG-28 A-2812
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2813 | PKG-28 A-2813
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2814 | PKG-28 A-2814
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-28 | A-2815 | PKG-28 A-2815
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2901 | PKG-29 A-2901
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2902 | PKG-29 A-2902
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2903 | PKG-29 A-2903
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2904 | PKG-29 A-2904
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2905 | PKG-29 A-2905
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2906 | PKG-29 A-2906
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2907 | PKG-29 A-2907
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2908 | PKG-29 A-2908
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2909 | PKG-29 A-2909
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2910 | PKG-29 A-2910
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2911 | PKG-29 A-2911
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2912 | PKG-29 A-2912
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2913 | PKG-29 A-2913
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2914 | PKG-29 A-2914
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2915 | PKG-29 A-2915
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2916 | PKG-29 A-2916
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-29 | A-2917 | PKG-29 A-2917
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3001 | PKG-30 A-3001
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3002 | PKG-30 A-3002
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3003 | PKG-30 A-3003
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3004 | PKG-30 A-3004
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3005 | PKG-30 A-3005
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3006 | PKG-30 A-3006
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3007 | PKG-30 A-3007
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3008 | PKG-30 A-3008
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3009 | PKG-30 A-3009
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3010 | PKG-30 A-3010
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3011 | PKG-30 A-3011
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3012 | PKG-30 A-3012
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3013 | PKG-30 A-3013
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3014 | PKG-30 A-3014
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3015 | PKG-30 A-3015
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3016 | PKG-30 A-3016
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3017 | PKG-30 A-3017
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3018 | PKG-30 A-3018
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3019 | PKG-30 A-3019
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3020 | PKG-30 A-3020
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3021 | PKG-30 A-3021
ASM-INTF | Interface & Coordination | ASM-INTF-014 | PKG-27 A-2701 | PKG-30 | A-3022 | PKG-30 A-3022
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-001 | PKG-24 assumption A-001 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-002 | PKG-24 assumption A-002 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-003 | PKG-24 assumption A-003 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-004 | PKG-24 assumption A-004 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-005 | PKG-24 assumption A-005 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-006 | PKG-24 assumption A-006 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-007 | PKG-24 assumption A-007 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-008 | PKG-24 assumption A-008 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-009 | PKG-24 assumption A-009 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-010 | PKG-24 assumption A-010 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-011 | PKG-24 assumption A-011 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-012 | PKG-24 assumption A-012 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-013 | PKG-24 assumption A-013 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-014 | PKG-24 assumption A-014 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-015 | PKG-24 assumption A-015 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-016 | PKG-24 assumption A-016 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-017 | PKG-24 assumption A-017 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-018 | PKG-24 assumption A-018 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-019 | PKG-24 assumption A-019 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-020 | PKG-24 assumption A-020 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-021 | PKG-24 assumption A-021 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-022 | PKG-24 assumption A-022 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-24 | A-023 | PKG-24 assumption A-023 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2501 | PKG-25 assumption A-2501 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2502 | PKG-25 assumption A-2502 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2503 | PKG-25 assumption A-2503 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2504 | PKG-25 assumption A-2504 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2505 | PKG-25 assumption A-2505 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2506 | PKG-25 assumption A-2506 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2507 | PKG-25 assumption A-2507 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2508 | PKG-25 assumption A-2508 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2509 | PKG-25 assumption A-2509 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2510 | PKG-25 assumption A-2510 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2511 | PKG-25 assumption A-2511 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2512 | PKG-25 assumption A-2512 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2513 | PKG-25 assumption A-2513 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2514 | PKG-25 assumption A-2514 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2515 | PKG-25 assumption A-2515 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2516 | PKG-25 assumption A-2516 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2517 | PKG-25 assumption A-2517 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-015 | PKG-24 assumption A-001 - see source | PKG-25 | A-2518 | PKG-25 assumption A-2518 - see source
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2601 | PKG-26 assumption A-2601
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2602 | PKG-26 assumption A-2602
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2603 | PKG-26 assumption A-2603
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2604 | PKG-26 assumption A-2604
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2605 | PKG-26 assumption A-2605
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2606 | PKG-26 assumption A-2606
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2607 | PKG-26 assumption A-2607
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2608 | PKG-26 assumption A-2608
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2609 | PKG-26 assumption A-2609
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2610 | PKG-26 assumption A-2610
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2611 | PKG-26 assumption A-2611
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2612 | PKG-26 assumption A-2612
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2613 | PKG-26 assumption A-2613
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2614 | PKG-26 assumption A-2614
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2615 | PKG-26 assumption A-2615
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2616 | PKG-26 assumption A-2616
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2617 | PKG-26 assumption A-2617
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2618 | PKG-26 assumption A-2618
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2619 | PKG-26 assumption A-2619
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2620 | PKG-26 assumption A-2620
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2621 | PKG-26 assumption A-2621
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2622 | PKG-26 assumption A-2622
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2623 | PKG-26 assumption A-2623
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2624 | PKG-26 assumption A-2624
ASM-INTF | Interface & Coordination | ASM-INTF-016 | PKG-26 assumption A-2601 | PKG-26 | A-2625 | PKG-26 assumption A-2625
ASM-INTF | Interface & Coordination | ASM-INTF-017 | 40-60 HMI graphics screens for operator interface | PKG-19 | A-012 | 40-60 HMI graphics screens for operator interface
ASM-INTF | Interface & Coordination | ASM-INTF-018 | Control system equipment installed in MCC building per PKG-21/22 | PKG-19 | A-001 | Control system equipment installed in MCC building per PKG..
ASM-INTF | Interface & Coordination | ASM-INTF-019 | Coordination Meeting Records — DEL-34.01 | PKG-34 | A-003 | Coordination Meeting Records — DEL-34.01
ASM-INTF | Interface & Coordination | ASM-INTF-020 | Interface Agreements — DEL-34.02 | PKG-34 | A-002 | Interface Agreements — DEL-34.02
ASM-INTF | Interface & Coordination | ASM-INTF-021 | Marine Coordination Records — DEL-34.03 | PKG-34 | A-004 | Marine Coordination Records — DEL-34.03
ASM-INTF | Interface & Coordination | ASM-INTF-022 | Marine loading system (PKG-11) requires **~25 valves** (loading arm isolation, f... | PKG-16 | A-1618 | Marine loading system (PKG-11) requires **~25 valves** (lo..
ASM-INTF | Interface & Coordination | ASM-INTF-023 | Product transfer and metering (PKG-12) requires **~30 valves** | PKG-16 | A-1619 | Product transfer and metering (PKG-12) requires **~30 valv..
ASM-INTF | Interface & Coordination | ASM-INTF-024 | Site Access and Temporary Works (PKG-06 Allocation) | PKG-06 | A-014 | Site Access and Temporary Works (PKG-06 Allocation)
ASM-INTF | Interface & Coordination | ASM-INTF-025 | Terminal Operations Coordination | PKG-23 | A-019 | Terminal Operations Coordination
ASM-LABOR | Labor & Installation | ASM-LABOR-026 | Installation Labor Rates | PKG-11 | A-012 | OEM qualification package requires ~60 hours at $200/hr
ASM-LABOR | Labor & Installation | ASM-LABOR-026 | Installation Labor Rates | PKG-14 | A-011 | Stress analysis requires ~340 hours at $250/hr including C..
ASM-LABOR | Labor & Installation | ASM-LABOR-026 | Installation Labor Rates | PKG-14 | A-012 | Line list requires ~100 hours at $250/hr for 50+ lines
ASM-LABOR | Labor & Installation | ASM-LABOR-026 | Installation Labor Rates | PKG-14 | A-016 | Valve closing time verification requires ~80 hours at $250..
ASM-LABOR | Labor & Installation | ASM-LABOR-026 | Installation Labor Rates | PKG-15 | A-003 | Installation labor assumed as:
ASM-LABOR | Labor & Installation | ASM-LABOR-026 | Installation Labor Rates | PKG-15 | A-009 | Commissioning estimated at 16 manhours per pump unit (14 p..
ASM-LABOR | Labor & Installation | ASM-LABOR-026 | Installation Labor Rates | PKG-15 | A-010 | Engineering effort estimated at 480 total hours ($100,000 ..
ASM-LABOR | Labor & Installation | ASM-LABOR-026 | Installation Labor Rates | PKG-16 | A-1607 | Valve installation labor hours: 4-24 hours per valve (size..
ASM-LABOR | Labor & Installation | ASM-LABOR-026 | Installation Labor Rates | PKG-16 | A-1612 | Installation labor rate **$95/hr all-in** (blended pipefit..
ASM-LABOR | Labor & Installation | ASM-LABOR-026 | Installation Labor Rates | PKG-16 | A-1614 | Mechanical engineering rate **$155/hr blended** (P.Eng., E..
ASM-LABOR | Labor & Installation | ASM-LABOR-026 | Installation Labor Rates | PKG-21 | A-015 | Foundation installation labor/equipment at $65,000
ASM-LABOR | Labor & Installation | ASM-LABOR-027 | Actuator hookup (pneumatic/electrical) adds **2-4 hours per actuated valve** | PKG-16 | A-1621 | Actuator hookup (pneumatic/electrical) adds **2-4 hours pe..
ASM-LABOR | Labor & Installation | ASM-LABOR-028 | Cable Tray and Conduit Installation Scope | PKG-17 | A-1727 | Cable Tray and Conduit Installation Scope
ASM-LABOR | Labor & Installation | ASM-LABOR-029 | Construction Labor Productivity | PKG-23 | A-018 | Construction Labor Productivity
ASM-LABOR | Labor & Installation | ASM-LABOR-030 | Construction Labor Rates (BC Lower Mainland) | PKG-22 | A-010 | Construction Labor Rates (BC Lower Mainland)
ASM-LABOR | Labor & Installation | ASM-LABOR-031 | Control valve calibration and loop check (30 valves) estimated at **4 hours per ... | PKG-16 | A-1629 | Control valve calibration and loop check (30 valves) estim..
ASM-LABOR | Labor & Installation | ASM-LABOR-032 | Crane and Equipment for Steel Erection | PKG-06 | A-008 | Crane and Equipment for Steel Erection
ASM-LABOR | Labor & Installation | ASM-LABOR-033 | Distribution Panel Installation Scope | PKG-17 | A-1724 | Distribution Panel Installation Scope
ASM-LABOR | Labor & Installation | ASM-LABOR-034 | Engineering Labor Hours | PKG-23 | A-012 | Engineering Labor Hours
ASM-LABOR | Labor & Installation | ASM-LABOR-035 | Fire Water Loop Installation Productivity | PKG-23 | A-013 | Fire Water Loop Installation Productivity
ASM-LABOR | Labor & Installation | ASM-LABOR-036 | Grating Supply and Installation | PKG-06 | A-010 | Grating Supply and Installation
ASM-LABOR | Labor & Installation | ASM-LABOR-037 | Grounding System Installation Scope | PKG-17 | A-1726 | Grounding System Installation Scope
ASM-LABOR | Labor & Installation | ASM-LABOR-038 | Handrail Supply and Installation | PKG-06 | A-009 | Handrail Supply and Installation
ASM-LABOR | Labor & Installation | ASM-LABOR-039 | Instrument Installation Rate | PKG-20 | A-019 | Instrument Installation Rate
ASM-LABOR | Labor & Installation | ASM-LABOR-040 | LV Switchgear Installation Scope | PKG-17 | A-1722 | LV Switchgear Installation Scope
ASM-LABOR | Labor & Installation | ASM-LABOR-041 | MCC Installation Scope | PKG-17 | A-1723 | MCC Installation Scope
ASM-LABOR | Labor & Installation | ASM-LABOR-042 | MEP Installation Productivity | PKG-22 | A-012 | MEP Installation Productivity
ASM-LABOR | Labor & Installation | ASM-LABOR-043 | MV Switchgear Installation Scope | PKG-17 | A-1721 | MV Switchgear Installation Scope
ASM-LABOR | Labor & Installation | ASM-LABOR-044 | Marine loading transient study requires ~180 hours specialist work | PKG-14 | A-015 | Marine loading transient study requires ~180 hours special..
ASM-LABOR | Labor & Installation | ASM-LABOR-045 | Normal industrial site access; no special access constraints for control system ... | PKG-19 | A-002 | Normal industrial site access; no special access constrain..
ASM-LABOR | Labor & Installation | ASM-LABOR-046 | Railcar unloading transient study requires ~200+ hours specialist work | PKG-14 | A-014 | Railcar unloading transient study requires ~200+ hours spe..
ASM-LABOR | Labor & Installation | ASM-LABOR-047 | Relief valve field verification (20 valves) estimated at **2 hours per valve** | PKG-16 | A-1630 | Relief valve field verification (20 valves) estimated at *..
ASM-LABOR | Labor & Installation | ASM-LABOR-048 | Structural Steel Erection Labor | PKG-06 | A-007 | Structural Steel Erection Labor
ASM-LABOR | Labor & Installation | ASM-LABOR-049 | Transformer Installation Scope | PKG-17 | A-1720 | Transformer Installation Scope
ASM-LABOR | Labor & Installation | ASM-LABOR-050 | UPS Installation Scope | PKG-17 | A-1725 | UPS Installation Scope
ASM-LABOR | Labor & Installation | ASM-LABOR-051 | Valve installation assumes **standard site access** (no major rigging constraint... | PKG-16 | A-1640 | Valve installation assumes **standard site access** (no ma..
ASM-LABOR | Labor & Installation | ASM-LABOR-052 | Valve installation duration estimated at **8-12 weeks** (field installation phas... | PKG-16 | A-1632 | Valve installation duration estimated at **8-12 weeks** (f..
ASM-LABOR | Labor & Installation | ASM-LABOR-053 | Valve installation includes rigging, bolting, gasket installation, alignment, hy... | PKG-16 | A-1620 | Valve installation includes rigging, bolting, gasket insta..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-05 | A-005 | Ring wall foundations for 3 tanks estimated at 450 m³ conc..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-05 | A-006 | Tank farm containment walls estimated at 600 m³ concrete t..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-05 | A-007 | Equipment pads for pumps, metering, railcar unloading equi..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-05 | A-008 | Thrust blocks for underground piping estimated at 80 m³ co..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-05 | A-009 | Reinforcing steel for all concrete structures estimated at..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-05 | A-010 | Formwork for containment walls estimated at 1,500 m² conta..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-10 | A-003 | Gravity flow header piping length estimated at 400 linear ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-11 | A-002 | Double-walled export pipe at 150 lm, $1,500/lm supply + $1..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-11 | A-005 | Operator shelter at $75,000 supply + $25,000 install for 1..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-11 | A-013 | Pipe supports at $45,000 supply + $35,000 install (~$300/l..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-14 | A-008 | Insulation and heat trace for ~1,200 lm at $200/lm supply ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-14 | A-025 | Pipe racks assumed in PKG-06 Structural Steelwork; support..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-15 | A-001 | Total of 14 pump units for the facility (4 railcar unloadi..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-16 | A-1609 | Relief valve count estimated at **20 units** (3 tank, 8 pu..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-16 | A-1610 | Strainer count estimated at **20 units** (8 pump suction, ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-16 | A-1622 | Control valves (30 units) include **smart positioners** ($..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-16 | A-1635 | External valve coating/painting **excluded** from PKG-16 (..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-16 | A-1644 | Valve winterization (heat trace, insulation) **excluded** ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-16 | A-1646 | Valve warranty (typically 12-24 months) and defects liabil..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-18 | A-1801 | Exterior pole-mounted LED area lights: 30-50 fixtures.
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-18 | A-1802 | Building-mounted exterior LED wall packs: 20-30 fixtures.
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-18 | A-1803 | Interior high-bay or linear LED fixtures for warehouse/pro..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-18 | A-1804 | Interior LED fixtures for offices, control rooms, utility ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-18 | A-1805 | Emergency battery-backed LED fixtures for egress lighting:..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-18 | A-1806 | Lighting control sensors and devices (occupancy, photocell..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-18 | A-1808 | Assume 10-20% of fixtures located in hazardous classified ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-18 | A-1821 | Assume 10-20% of fixtures in hazardous classified areas (C..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-18 | A-1822 | LED fixtures: 100-120 lm/W efficacy, 50,000+ hours L70 lum..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-18 | A-1827 | Civil discipline (PKG-01, PKG-02, PKG-03) provides pole fo..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-18 | A-1829 | Lighting supplied from 120/208V or 347/600V 3-phase electr..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-18 | A-1831 | LED fixtures: minimum 5-year manufacturer warranty on fixt..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-21 | A-001 | Pre-engineered metal building supply at $650/m² for 600 m²..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-21 | A-002 | Prefabricated operator shelter at $45,000 each (4 units)
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-21 | A-008 | Insulated metal panel cladding at $120/m² for wall R-20 up..
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-21 | A-009 | Standing seam roof with R-30 insulation at $85/m²
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-21 | A-013 | Shelter foundation materials at $8,000 each (4 units)
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-21 | A-016 | PEMB erection at $180/m² for 600 m² building
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-21 | A-017 | Cladding and roofing installation at $95/m²
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-21 | A-019 | Shelter installation at $12,000 each (4 units)
ASM-PRICE | Pricing Allowances | ASM-PRICE-054 | Material Quantities | PKG-21 | A-020 | Shelter foundation installation at $6,000 each (4 units)
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-001 | Railcar unloading arms priced at $50,000 CAD per unit (32 ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-002 | Quick-connect couplers priced at $3,000 CAD per unit (32 u..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-011 | Flow indicators priced at $2,500 CAD per unit (32 units).
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-012 | Atmospheric venting system (32 connections + routing + fla..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-013 | Header isolation valves and fittings priced at $85,000 tot..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-014 | Installation consumables and fasteners priced at $45,000 t..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-015 | Unloading arm installation labor priced at $8,000 per unit..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-016 | Header piping installation labor priced at $450 per linear..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-017 | Containment pan installation labor priced at $4,500 per un..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-018 | Sump pump installation labor priced at $3,000 per unit (8 ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-019 | Flow indicator installation labor priced at $1,000 per uni..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-020 | Venting system installation labor priced at $28,000 total ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-021 | Setting out and survey labor priced at $18,000 total for 3..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-022 | Hydrostatic testing and flushing labor priced at $22,000 t..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-023 | Coating touch-up and protection labor priced at $13,000 to..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-024 | Unloading arm factory acceptance testing and commissioning..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-025 | System integration testing priced at $28,000 total.
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-026 | Performance testing and verification priced at $22,000 tot..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-10 | A-027 | Final inspection and commissioning documentation priced at..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-11 | A-001 | Marine loading arm priced at $950,000 including ERC, hydra..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-14 | A-001 | Rail unloading header system priced at 250 lm × $1,500/lm ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-14 | A-002 | Tank farm piping priced at 150 lm inlet + 100 lm outlet ma..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-14 | A-003 | Export piping priced at 350 lm × $1,200/lm supply + $1,000..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-14 | A-004 | Recycle/return piping priced at 150 lm × $800/lm supply + ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-14 | A-005 | Nitrogen distribution priced at 400 lm × $300/lm supply + ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-14 | A-006 | Small bore utility piping priced at 200 lm × $300/lm suppl..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-14 | A-007 | Pipe supports priced at 300 units × $600/unit supply + $60..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-16 | A-1606 | Valve unit costs based on typical BC/Canada market pricing..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-18 | A-1809 | Exterior pole-mounted LED area lights priced at $1,500-$3,..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-18 | A-1810 | Interior high-bay LED fixtures priced at $800-$1,500 CAD p..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-18 | A-1811 | Interior office/control room LED fixtures priced at $300-$..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-18 | A-1812 | Emergency battery-backed LED fixtures priced at $500-$1,00..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-18 | A-1813 | Lighting control sensors and devices priced at $500-$1,500..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-18 | A-1814 | Exterior lighting poles (30-40 ft, steel or aluminum, mari..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-18 | A-1815 | Exterior lighting installation (pole-mounted fixtures) pri..
ASM-PRICE | Pricing Allowances | ASM-PRICE-055 | Equipment Unit Pricing | PKG-18 | A-1816 | Interior lighting installation (ceiling/wall-mounted fixtu..
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-00 | A-002 | Site establishment specifications (2 specs) estimated at $..
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-01 | A-102 | Demolition Technical Specification Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-05 | A-002 | Concrete technical specifications (3 specs: concrete, rein..
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-06 | A-002 | Structural Steel Technical Specification Writing Effort
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-08 | A-802 | DEL-08.02 Specification Writing Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-08 | A-825 | NDT and Inspection Services Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-10 | A-007 | DEL-10.02 Technical Specification engineering effort price..
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-11 | A-008 | Technical specification requires ~100-120 hours at $200/hr
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-14 | A-010 | Technical specification requires ~200 hours at $225/hr
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-14 | A-021 | Specialty piping work (tie-ins, hot taps) at $45,000 allow..
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-16 | A-1633 | Special tools (torque wrenches, hydrostatic test pump, val..
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-17 | A-1702 | Electrical Power Technical Specification Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-19 | A-016 | Technical specification effort: $40,000 (DCS/PLC + HMI + h..
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-20 | A-012 | Technical Specification Effort
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-21 | A-004 | Building specifications development at $25,000 allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-056 | Technical Specification Writing | PKG-32 | A-3206 | Code Compliance Inspection Coordination Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-057 | Engineering Drawing Production | PKG-00 | A-001 | Site establishment drawing set (4 drawings) estimated at $..
ASM-PRICE | Pricing Allowances | ASM-PRICE-057 | Engineering Drawing Production | PKG-00 | A-009 | Temporary water supply design drawings (3 drawings) estima..
ASM-PRICE | Pricing Allowances | ASM-PRICE-057 | Engineering Drawing Production | PKG-01 | A-101 | Demolition Design Drawing Set Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-057 | Engineering Drawing Production | PKG-05 | A-001 | Concrete structures drawing set estimated at $85,000 CAD a..
ASM-PRICE | Pricing Allowances | ASM-PRICE-057 | Engineering Drawing Production | PKG-06 | A-001 | Structural Steel Design Drawing Set Engineering Effort
ASM-PRICE | Pricing Allowances | ASM-PRICE-057 | Engineering Drawing Production | PKG-08 | A-801 | DEL-08.01 Drawing Production Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-057 | Engineering Drawing Production | PKG-10 | A-006 | DEL-10.01 Design Drawing Set engineering effort priced at ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-057 | Engineering Drawing Production | PKG-11 | A-007 | Drawing set requires ~12-15 sheets at $3,000/sheet average
ASM-PRICE | Pricing Allowances | ASM-PRICE-057 | Engineering Drawing Production | PKG-14 | A-009 | Drawing set requires ~50-60 sheets at $3,000/sheet average
ASM-PRICE | Pricing Allowances | ASM-PRICE-057 | Engineering Drawing Production | PKG-17 | A-1701 | Electrical Power Design Drawing Set Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-057 | Engineering Drawing Production | PKG-19 | A-015 | Control system design drawings effort: $60,000 (architectu..
ASM-PRICE | Pricing Allowances | ASM-PRICE-057 | Engineering Drawing Production | PKG-21 | A-007 | Shop drawing coordination and review at $15,000 allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-058 | Installation & Test Records | PKG-05 | A-004 | Concrete installation and test records documentation estim..
ASM-PRICE | Pricing Allowances | ASM-PRICE-058 | Installation & Test Records | PKG-06 | A-005 | Structural Steel QA/QC Records Compilation Effort
ASM-PRICE | Pricing Allowances | ASM-PRICE-058 | Installation & Test Records | PKG-08 | A-805 | DEL-08.05 Installation & Test Records Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-058 | Installation & Test Records | PKG-10 | A-010 | DEL-10.05 Installation & Test Records engineering/QA effor..
ASM-PRICE | Pricing Allowances | ASM-PRICE-058 | Installation & Test Records | PKG-11 | A-011 | Installation & test records require ~60 hours at $250/hr
ASM-PRICE | Pricing Allowances | ASM-PRICE-058 | Installation & Test Records | PKG-13 | A-015 | Test records
ASM-PRICE | Pricing Allowances | ASM-PRICE-058 | Installation & Test Records | PKG-14 | A-013 | Test record compilation requires ~140 hours at $250/hr
ASM-PRICE | Pricing Allowances | ASM-PRICE-058 | Installation & Test Records | PKG-17 | A-1705 | Electrical Power Installation & Test Records Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-058 | Installation & Test Records | PKG-20 | A-015 | Test Record Documentation
ASM-PRICE | Pricing Allowances | ASM-PRICE-059 | Data Sheet Package | PKG-06 | A-004 | Structural Steel Data Sheet Package Compilation Effort
ASM-PRICE | Pricing Allowances | ASM-PRICE-059 | Data Sheet Package | PKG-10 | A-009 | DEL-10.04 Data Sheet Package engineering effort priced at ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-059 | Data Sheet Package | PKG-11 | A-010 | Data sheet package requires ~40 hours at $200/hr
ASM-PRICE | Pricing Allowances | ASM-PRICE-059 | Data Sheet Package | PKG-17 | A-1704 | Electrical Power Data Sheet Package Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-059 | Data Sheet Package | PKG-19 | A-017 | Data sheet package review effort: $20,000
ASM-PRICE | Pricing Allowances | ASM-PRICE-059 | Data Sheet Package | PKG-21 | A-006 | Building data sheets and schedules at $8,000 allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-060 | 32 individual spill containment pans (one per unloading station) at $8,000/unit. | PKG-10 | A-004 | 32 individual spill containment pans (one per unloading st..
ASM-PRICE | Pricing Allowances | ASM-PRICE-061 | 7 doors (6 personnel + 1 overhead) at $4,500 average | PKG-21 | A-010 | 7 doors (6 personnel + 1 overhead) at $4,500 average
ASM-PRICE | Pricing Allowances | ASM-PRICE-062 | API 610 process pump costs estimated as follows: | PKG-15 | A-002 | API 610 process pump costs estimated as follows:
ASM-PRICE | Pricing Allowances | ASM-PRICE-063 | Abutment Materials Allowance | PKG-08 | A-816 | Abutment Materials Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-064 | Actuator costs: Pneumatic $3k-$15k (size-dependent), Electric $8k-$40k (size-dep... | PKG-16 | A-1626 | Actuator costs: Pneumatic $3k-$15k (size-dependent), Elect..
ASM-PRICE | Pricing Allowances | ASM-PRICE-065 | Building Size for MEP Allowance Scaling | PKG-22 | A-022 | Building Size for MEP Allowance Scaling
ASM-PRICE | Pricing Allowances | ASM-PRICE-066 | Building commissioning coordination at $15,000 | PKG-21 | A-023 | Building commissioning coordination at $15,000
ASM-PRICE | Pricing Allowances | ASM-PRICE-067 | CEMP Compliance Monitoring Allowance | PKG-33 | A-004 | CEMP Compliance Monitoring Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-068 | Catwalk Structural Steel Supply Allowance | PKG-08 | A-815 | Catwalk Structural Steel Supply Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-069 | Catwalk and Abutment Installation Allowance | PKG-08 | A-822 | Catwalk and Abutment Installation Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-070 | Commissioning Parametric Allowance | PKG-32 | A-3213 | Commissioning Parametric Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-071 | Concrete testing and quality control services estimated at $65,000 CAD allowance... | PKG-05 | A-013 | Concrete testing and quality control services estimated at..
ASM-PRICE | Pricing Allowances | ASM-PRICE-072 | Containment sump construction at $45,000 | PKG-11 | A-015 | Containment sump construction at $45,000
ASM-PRICE | Pricing Allowances | ASM-PRICE-073 | Control system software licenses: $100,000 (DCS/PLC + HMI + historian) | PKG-19 | A-019 | Control system software licenses: $100,000 (DCS/PLC + HMI ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-074 | Correspondence Filing and Archiving Allowance | PKG-32 | A-3210 | Correspondence Filing and Archiving Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-075 | Correspondence Register Setup and Maintenance Allowance | PKG-32 | A-3209 | Correspondence Register Setup and Maintenance Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-076 | Corrosion protection allowance of $35,000 for marine environment | PKG-21 | A-014 | Corrosion protection allowance of $35,000 for marine envir..
ASM-PRICE | Pricing Allowances | ASM-PRICE-077 | DEL-08.04 Marine Geotechnical Report Allowance | PKG-08 | A-804 | DEL-08.04 Marine Geotechnical Report Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-078 | DEL-08.06 Berthing Energy Report Allowance | PKG-08 | A-806 | DEL-08.06 Berthing Energy Report Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-079 | DEL-08.07 Fender Data Package Allowance | PKG-08 | A-807 | DEL-08.07 Fender Data Package Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-080 | DEL-08.08 Fender Supplier Verification Allowance | PKG-08 | A-808 | DEL-08.08 Fender Supplier Verification Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-081 | DEL-08.09 Mooring Analysis Report Allowance | PKG-08 | A-809 | DEL-08.09 Mooring Analysis Report Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-082 | DEL-08.10 Current Assessment Report Allowance | PKG-08 | A-810 | DEL-08.10 Current Assessment Report Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-083 | DEL-08.11 Debris Loading Basis Note Allowance | PKG-08 | A-811 | DEL-08.11 Debris Loading Basis Note Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-084 | DFO Compliance Monitoring Allowance | PKG-32 | A-3204 | DFO Compliance Monitoring Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-085 | Defects Liability Support Allowance ($165,000) | PKG-35 | A-005 | Defects Liability Support Allowance ($165,000)
ASM-PRICE | Pricing Allowances | ASM-PRICE-086 | Demolition Materials and Temporary Works Allowance | PKG-01 | A-109 | Demolition Materials and Temporary Works Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-087 | Demolition Procedures Allowance | PKG-01 | A-103 | Demolition Procedures Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-088 | Demolition Records QA/QC Allowance | PKG-01 | A-104 | Demolition Records QA/QC Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-089 | Dolphin 2 Marine Demolition Allowance | PKG-01 | A-106 | Dolphin 2 Marine Demolition Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-090 | Door and window installation at $18,000 allowance | PKG-21 | A-018 | Door and window installation at $18,000 allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-091 | E&I materials at $65,000 + installation at $100,000 | PKG-11 | A-014 | E&I materials at $65,000 + installation at $100,000
ASM-PRICE | Pricing Allowances | ASM-PRICE-092 | EPCM/Project Management estimated at 6% of (CD + CI + MAT) = 6% × ($53,200 + $9,... | PKG-15 | A-008 | EPCM/Project Management estimated at 6% of (CD + CI + MAT)..
ASM-PRICE | Pricing Allowances | ASM-PRICE-093 | Electrical Installation Materials Allowance | PKG-17 | A-1718 | Electrical Installation Materials Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-094 | Emergency Response Plan Allowance | PKG-33 | A-007 | Emergency Response Plan Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-095 | Equipment schedule documents (2 documents) estimated at $5,000 CAD allowance. | PKG-00 | A-004 | Equipment schedule documents (2 documents) estimated at $5..
ASM-PRICE | Pricing Allowances | ASM-PRICE-096 | Expansion joints/loops allowance $65,000 | PKG-14 | A-018 | Expansion joints/loops allowance $65,000
ASM-PRICE | Pricing Allowances | ASM-PRICE-097 | FAT $25,000 + SAT $20,000 + commissioning support $10,000 | PKG-19 | A-022 | FAT $25,000 + SAT $20,000 + commissioning support $10,000
ASM-PRICE | Pricing Allowances | ASM-PRICE-098 | Fencing Removal Allowance | PKG-01 | A-107 | Fencing Removal Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-099 | Finishing and punch list allowance of $25,000 | PKG-21 | A-021 | Finishing and punch list allowance of $25,000
ASM-PRICE | Pricing Allowances | ASM-PRICE-100 | Fire Alarm System Installation Cost | PKG-23 | A-016 | Fire Alarm System Installation Cost
ASM-PRICE | Pricing Allowances | ASM-PRICE-101 | Fire Hydrant Installation Cost | PKG-23 | A-015 | Fire Hydrant Installation Cost
ASM-PRICE | Pricing Allowances | ASM-PRICE-102 | Fire Water Loop Installation Cost | PKG-23 | A-014 | Fire Water Loop Installation Cost
ASM-PRICE | Pricing Allowances | ASM-PRICE-103 | Foam System Installation Cost | PKG-23 | A-017 | Foam System Installation Cost
ASM-PRICE | Pricing Allowances | ASM-PRICE-104 | Foundation materials (concrete, piles, reinforcing) at $85,000 allowance | PKG-21 | A-012 | Foundation materials (concrete, piles, reinforcing) at $85..
ASM-PRICE | Pricing Allowances | ASM-PRICE-105 | Freight and Logistics Allowance | PKG-17 | A-1719 | Freight and Logistics Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-106 | Freight and Marine Logistics Allowance | PKG-08 | A-818 | Freight and Marine Logistics Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-107 | Ground liner system interface work (concrete curbs, anchors, terminations) estim... | PKG-05 | A-012 | Ground liner system interface work (concrete curbs, anchor..
ASM-PRICE | Pricing Allowances | ASM-PRICE-108 | Handover Coordination Allowance ($85,000) | PKG-35 | A-004 | Handover Coordination Allowance ($85,000)
ASM-PRICE | Pricing Allowances | ASM-PRICE-109 | Hydrostatic testing at $95,000 for ~10-15 test packages | PKG-14 | A-019 | Hydrostatic testing at $95,000 for ~10-15 test packages
ASM-PRICE | Pricing Allowances | ASM-PRICE-110 | Initial spare parts estimated at 8% of pump equipment cost ($850,000 × 8% = $68,... | PKG-15 | A-013 | Initial spare parts estimated at 8% of pump equipment cost..
ASM-PRICE | Pricing Allowances | ASM-PRICE-111 | Installation quality records and documentation: $32,000 | PKG-19 | A-021 | Installation quality records and documentation: $32,000
ASM-PRICE | Pricing Allowances | ASM-PRICE-112 | Leak detection system at $85,000 supply + $35,000 install for 3-zone coverage | PKG-11 | A-003 | Leak detection system at $85,000 supply + $35,000 install ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-113 | Lighting circuit wiring and conduit from panels to fixtures: allowance $40,000-$... | PKG-18 | A-1828 | Lighting circuit wiring and conduit from panels to fixture..
ASM-PRICE | Pricing Allowances | ASM-PRICE-114 | Lighting circuit wiring, conduit, and accessories: $40,000-$80,000 CAD allowance... | PKG-18 | A-1818 | Lighting circuit wiring, conduit, and accessories: $40,000..
ASM-PRICE | Pricing Allowances | ASM-PRICE-115 | Lighting controls installation and programming: $15,000-$40,000 CAD allowance. | PKG-18 | A-1817 | Lighting controls installation and programming: $15,000-$4..
ASM-PRICE | Pricing Allowances | ASM-PRICE-116 | Limited industrial glazing allowance of $15,000 | PKG-21 | A-011 | Limited industrial glazing allowance of $15,000
ASM-PRICE | Pricing Allowances | ASM-PRICE-117 | Loading Platform Steel Erection Allowance | PKG-08 | A-821 | Loading Platform Steel Erection Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-118 | Loading Platform Structural Steel Supply Allowance | PKG-08 | A-814 | Loading Platform Structural Steel Supply Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-119 | Loading arm installation requires crane barge for heavy lift; included in instal... | PKG-11 | A-017 | Loading arm installation requires crane barge for heavy li..
ASM-PRICE | Pricing Allowances | ASM-PRICE-120 | Marine Coatings and Touch-Up Allowance | PKG-08 | A-824 | Marine Coatings and Touch-Up Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-121 | Marine Hardware Installation Allowance | PKG-08 | A-823 | Marine Hardware Installation Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-122 | Marine Hardware and Miscellaneous Steel Allowance | PKG-08 | A-817 | Marine Hardware and Miscellaneous Steel Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-123 | Marine Piling Installation Allowance | PKG-08 | A-819 | Marine Piling Installation Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-124 | Marine Piling Supply Allowance | PKG-08 | A-812 | Marine Piling Supply Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-125 | Mechanical seal systems and auxiliary equipment (seal flush systems, cooling wat... | PKG-15 | A-011 | Mechanical seal systems and auxiliary equipment (seal flus..
ASM-PRICE | Pricing Allowances | ASM-PRICE-126 | Method Statements Allowance | PKG-33 | A-003 | Method Statements Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-127 | Miscellaneous cables and terminations: $60,000 | PKG-19 | A-020 | Miscellaneous cables and terminations: $60,000
ASM-PRICE | Pricing Allowances | ASM-PRICE-128 | NDE and weld inspection at ~$250/weld for 500+ welds | PKG-14 | A-020 | NDE and weld inspection at ~$250/weld for 500+ welds
ASM-PRICE | Pricing Allowances | ASM-PRICE-129 | Nitrogen connection at $15,000 supply + $15,000 install | PKG-11 | A-006 | Nitrogen connection at $15,000 supply + $15,000 install
ASM-PRICE | Pricing Allowances | ASM-PRICE-130 | Occupational Health & Safety Plan Allowance | PKG-33 | A-001 | Occupational Health & Safety Plan Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-131 | Permit Application Engineering Allowance | PKG-32 | A-3201 | Permit Application Engineering Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-132 | Permit Fees Allowance | PKG-32 | A-3208 | Permit Fees Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-133 | Permit Receipt and Tracking PM Allowance | PKG-32 | A-3202 | Permit Receipt and Tracking PM Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-134 | Post-works road survey, deficiency identification, and closeout estimated at $18... | PKG-00 | A-007 | Post-works road survey, deficiency identification, and clo..
ASM-PRICE | Pricing Allowances | ASM-PRICE-135 | Pre-works road survey and photo documentation estimated at $15,000 CAD allowance... | PKG-00 | A-006 | Pre-works road survey and photo documentation estimated at..
ASM-PRICE | Pricing Allowances | ASM-PRICE-136 | Printing & Binding Costs - Drawings | PKG-31 | A-004 | Printing & Binding Costs - Drawings
ASM-PRICE | Pricing Allowances | ASM-PRICE-137 | Printing & Binding Costs - Manuals | PKG-31 | A-005 | Printing & Binding Costs - Manuals
ASM-PRICE | Pricing Allowances | ASM-PRICE-138 | Procurement Services Parametric Allowance | PKG-32 | A-3211 | Procurement Services Parametric Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-139 | Procurement services estimated at 2% of equipment cost ($850,000 × 2% = $17,000)... | PKG-15 | A-006 | Procurement services estimated at 2% of equipment cost ($8..
ASM-PRICE | Pricing Allowances | ASM-PRICE-140 | Project Management Parametric Allowance | PKG-32 | A-3212 | Project Management Parametric Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-141 | Pump couplings and fabricated baseplates estimated at 12% of pump cost. | PKG-15 | A-012 | Pump couplings and fabricated baseplates estimated at 12% ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-142 | QA/QC inspection and envelope testing at $18,000 | PKG-21 | A-022 | QA/QC inspection and envelope testing at $18,000
ASM-PRICE | Pricing Allowances | ASM-PRICE-143 | Regulatory/Environmental Consultant Support Allowance | PKG-32 | A-3207 | Regulatory/Environmental Consultant Support Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-144 | Relief valve set pressure testing performed at **vendor FAT** (included in valve... | PKG-16 | A-1624 | Relief valve set pressure testing performed at **vendor FA..
ASM-PRICE | Pricing Allowances | ASM-PRICE-145 | Risk Assessments Allowance | PKG-33 | A-002 | Risk Assessments Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-146 | Road access and security process documents (3 plans) estimated at $8,000 CAD all... | PKG-00 | A-005 | Road access and security process documents (3 plans) estim..
ASM-PRICE | Pricing Allowances | ASM-PRICE-147 | Road deficiency remediation and restoration work estimated at $25,000 CAD allowa... | PKG-00 | A-008 | Road deficiency remediation and restoration work estimated..
ASM-PRICE | Pricing Allowances | ASM-PRICE-148 | SPPP Compliance Monitoring Allowance | PKG-33 | A-005 | SPPP Compliance Monitoring Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-149 | Salt Tent Dismantling Allowance | PKG-01 | A-108 | Salt Tent Dismantling Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-150 | Security gate hardware, access control system, and installation estimated at $75... | PKG-00 | A-011 | Security gate hardware, access control system, and install..
ASM-PRICE | Pricing Allowances | ASM-PRICE-151 | Security gate staffing during construction estimated at $180,000 CAD allowance. | PKG-00 | A-013 | Security gate staffing during construction estimated at $1..
ASM-PRICE | Pricing Allowances | ASM-PRICE-152 | Site Clearance QA/QC ($134,000) | PKG-35 | A-010 | Site Clearance QA/QC ($134,000)
ASM-PRICE | Pricing Allowances | ASM-PRICE-153 | Site Reinstatement Allowance ($350,000) | PKG-35 | A-002 | Site Reinstatement Allowance ($350,000)
ASM-PRICE | Pricing Allowances | ASM-PRICE-154 | Site establishment procedures (3 procedures) estimated at $9,000 CAD allowance. | PKG-00 | A-003 | Site establishment procedures (3 procedures) estimated at ..
ASM-PRICE | Pricing Allowances | ASM-PRICE-155 | Software development effort: $120,000 (PLC logic $80k + HMI $30k + historian $10... | PKG-19 | A-018 | Software development effort: $120,000 (PLC logic $80k + HM..
ASM-PRICE | Pricing Allowances | ASM-PRICE-156 | Sump pump package at $25,000 supply for 5 HP submersible | PKG-11 | A-004 | Sump pump package at $25,000 supply for 5 HP submersible
ASM-PRICE | Pricing Allowances | ASM-PRICE-157 | Temporary facilities, laydown areas, utilities, fencing, and site infrastructure... | PKG-00 | A-012 | Temporary facilities, laydown areas, utilities, fencing, a..
ASM-PRICE | Pricing Allowances | ASM-PRICE-158 | Temporary water supply pipe, backflow preventer, connections, and installation e... | PKG-00 | A-010 | Temporary water supply pipe, backflow preventer, connectio..
ASM-PRICE | Pricing Allowances | ASM-PRICE-159 | Track 6 Rail Demolition Allowance | PKG-01 | A-105 | Track 6 Rail Demolition Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-160 | Training Delivery Allowance ($395,000) | PKG-35 | A-001 | Training Delivery Allowance ($395,000)
ASM-PRICE | Pricing Allowances | ASM-PRICE-161 | Training Materials Development Allowance ($285,000) | PKG-35 | A-003 | Training Materials Development Allowance ($285,000)
ASM-PRICE | Pricing Allowances | ASM-PRICE-162 | Training Records Management ($47,000) | PKG-35 | A-009 | Training Records Management ($47,000)
ASM-PRICE | Pricing Allowances | ASM-PRICE-163 | Transport Canada Compliance Monitoring Allowance | PKG-32 | A-3205 | Transport Canada Compliance Monitoring Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-164 | Trestle Steel Erection Allowance | PKG-08 | A-820 | Trestle Steel Erection Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-165 | Trestle Structural Steel Supply Allowance | PKG-08 | A-813 | Trestle Structural Steel Supply Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-166 | VFPA PER Compliance Monitoring Allowance | PKG-32 | A-3203 | VFPA PER Compliance Monitoring Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-167 | Valve O&M manuals and documentation **included in valve supply cost** (no separa... | PKG-16 | A-1643 | Valve O&M manuals and documentation **included in valve su..
ASM-PRICE | Pricing Allowances | ASM-PRICE-168 | Valve bolting and gaskets estimated at **5% of valve cost** | PKG-16 | A-1627 | Valve bolting and gaskets estimated at **5% of valve cost*..
ASM-PRICE | Pricing Allowances | ASM-PRICE-169 | Valve factory acceptance testing (FAT) **included in valve supply cost**; site a... | PKG-16 | A-1645 | Valve factory acceptance testing (FAT) **included in valve..
ASM-PRICE | Pricing Allowances | ASM-PRICE-170 | Valve freight estimated at **8% of valve FOB cost** | PKG-16 | A-1623 | Valve freight estimated at **8% of valve FOB cost**
ASM-PRICE | Pricing Allowances | ASM-PRICE-171 | Valve installation equipment (crane, rigging, lifting gear) included in **CD ins... | PKG-16 | A-1628 | Valve installation equipment (crane, rigging, lifting gear..
ASM-PRICE | Pricing Allowances | ASM-PRICE-172 | Valve nameplates and tags **included** in valve supply cost (no separate allowan... | PKG-16 | A-1636 | Valve nameplates and tags **included** in valve supply cos..
ASM-PRICE | Pricing Allowances | ASM-PRICE-173 | Waste Disposal and Hauling Allowance | PKG-01 | A-111 | Waste Disposal and Hauling Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-174 | Waste Management Records Allowance | PKG-33 | A-006 | Waste Management Records Allowance
ASM-PRICE | Pricing Allowances | ASM-PRICE-175 | Waterstops and joint materials for containment walls estimated at $45,000 CAD al... | PKG-05 | A-011 | Waterstops and joint materials for containment walls estim..
ASM-PRICE | Pricing Allowances | ASM-PRICE-176 | Waterway Pollution Control Method Statement Allowance | PKG-33 | A-008 | Waterway Pollution Control Method Statement Allowance
ASM-QTY | Quantity Assumptions | ASM-QTY-177 | 2,000 meters of fiber optic cable for control network backbone | PKG-19 | A-010 | 2,000 meters of fiber optic cable for control network back..
ASM-QTY | Quantity Assumptions | ASM-QTY-178 | Actuator distribution: 60% manual, 30% pneumatic, 10% electric (by valve count) | PKG-16 | A-1604 | Actuator distribution: 60% manual, 30% pneumatic, 10% elec..
ASM-QTY | Quantity Assumptions | ASM-QTY-179 | Distribution Panels Quantity | PKG-17 | A-1710 | Distribution Panels Quantity
ASM-QTY | Quantity Assumptions | ASM-QTY-180 | Estimated I/O count: 600-800 points based on facility scope | PKG-19 | A-006 | Estimated I/O count: 600-800 points based on facility scop..
ASM-QTY | Quantity Assumptions | ASM-QTY-181 | Fire Hydrant Quantity | PKG-23 | A-002 | Fire Hydrant Quantity
ASM-QTY | Quantity Assumptions | ASM-QTY-182 | Instrument Cable Quantity | PKG-20 | A-008 | Instrument Cable Quantity
ASM-QTY | Quantity Assumptions | ASM-QTY-183 | Junction Box Quantity | PKG-20 | A-009 | Junction Box Quantity
ASM-QTY | Quantity Assumptions | ASM-QTY-184 | Loading arm is single-arm configuration (not dual counterweighted arms) | PKG-11 | A-018 | Loading arm is single-arm configuration (not dual counterw..
ASM-QTY | Quantity Assumptions | ASM-QTY-185 | MV/LV Transformers Quantity and Sizing | PKG-17 | A-1706 | MV/LV Transformers Quantity and Sizing
ASM-QTY | Quantity Assumptions | ASM-QTY-186 | Major Equipment Count | PKG-31 | A-003 | Major Equipment Count
ASM-QTY | Quantity Assumptions | ASM-QTY-187 | Motor Control Centers Quantity and Distribution | PKG-17 | A-1709 | Motor Control Centers Quantity and Distribution
ASM-QTY | Quantity Assumptions | ASM-QTY-188 | Operational Systems Count | PKG-31 | A-002 | Operational Systems Count
ASM-QTY | Quantity Assumptions | ASM-QTY-189 | Plumbing Fixture Count and Equipment | PKG-22 | A-002 | Plumbing Fixture Count and Equipment
ASM-QTY | Quantity Assumptions | ASM-QTY-190 | Total Drawing Count | PKG-31 | A-001 | Total Drawing Count
ASM-QTY | Quantity Assumptions | ASM-QTY-191 | Total valve count estimated at **220 valves** (30 control, 150 isolation, 20 rel... | PKG-16 | A-1601 | Total valve count estimated at **220 valves** (30 control,..
ASM-QTY | Quantity Assumptions | ASM-QTY-192 | Trenchless Crossing Count — 2-4 Crossings | PKG-34 | A-007 | Trenchless Crossing Count — 2-4 Crossings
ASM-QTY | Quantity Assumptions | ASM-QTY-193 | Valve count by type: 30 control (13%), 150 isolation (68%), 20 relief (9%), 20 s... | PKG-16 | A-1608 | Valve count by type: 30 control (13%), 150 isolation (68%)..
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-194 | Construction Indirects Factor | PKG-14 | A-022 | Weather impacts included in CI factor; no explicit weather..
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-194 | Construction Indirects Factor | PKG-15 | A-007 | Construction indirects estimated at 18% of Construction Di..
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-194 | Construction Indirects Factor | PKG-16 | A-1637 | Valve storage and preservation **included in CI (Construct..
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-195 | Scope Exclusions | PKG-16 | A-1611 | Specialty equipment includes **20 check valves**; other sp..
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-195 | Scope Exclusions | PKG-16 | A-1634 | Valve spare parts **excluded** from PKG-16 estimate (likel..
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-196 | Cable Pulling and Termination Scope | PKG-17 | A-1728 | Cable Pulling and Termination Scope
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-197 | Electrical Testing and Commissioning Support Scope | PKG-17 | A-1729 | Electrical Testing and Commissioning Support Scope
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-198 | Fire Water Loop Piping Scope | PKG-23 | A-001 | Fire Water Loop Piping Scope
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-199 | Grounding System Scope | PKG-17 | A-1712 | Grounding System Scope
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-200 | Lighting controls include occupancy sensing, daylight harvesting, and time sched... | PKG-18 | A-1824 | Lighting controls include occupancy sensing, daylight harv..
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-201 | Phase 2 connection provisions included in DEL-14.01 scope | PKG-14 | A-024 | Phase 2 connection provisions included in DEL-14.01 scope
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-202 | Testing and Commissioning Scope | PKG-22 | A-013 | Testing and Commissioning Scope
ASM-SCOPE | Scope Boundaries | ASM-SCOPE-203 | Valve testing (DEL-16.05) included in **COM factor** (no separate testing line) | PKG-16 | A-1615 | Valve testing (DEL-16.05) included in **COM factor** (no s..
ASM-TECH | Technical Parameters | ASM-TECH-204 | Material Specification | PKG-11 | A-019 | Canola oil service does not require exotic materials (stai..
ASM-TECH | Technical Parameters | ASM-TECH-204 | Material Specification | PKG-14 | A-023 | Carbon steel construction throughout with no exotic alloys
ASM-TECH | Technical Parameters | ASM-TECH-204 | Material Specification | PKG-16 | A-1603 | Product-contact valves specified as **316SS** (stainless s..
ASM-TECH | Technical Parameters | ASM-TECH-204 | Material Specification | PKG-16 | A-1625 | Stainless steel valve cost premium: **~2.5× carbon steel b..
ASM-TECH | Technical Parameters | ASM-TECH-204 | Material Specification | PKG-18 | A-1819 | Exterior fixtures require IP65+ rating and marine-grade co..
ASM-TECH | Technical Parameters | ASM-TECH-205 | Contingency Percentage | PKG-01 | A-110 | Hazardous Materials Contingency Placeholder
ASM-TECH | Technical Parameters | ASM-TECH-206 | All valves comply with **API/ASME/CSA standards** (premium quality; not economy-... | PKG-16 | A-1641 | All valves comply with **API/ASME/CSA standards** (premium..
ASM-TECH | Technical Parameters | ASM-TECH-207 | Fire Water and Fire Alarm Material Pricing | PKG-23 | A-009 | Fire Water and Fire Alarm Material Pricing
ASM-TECH | Technical Parameters | ASM-TECH-208 | Foam System Material Pricing | PKG-23 | A-011 | Foam System Material Pricing
ASM-TECH | Technical Parameters | ASM-TECH-209 | Gaskets, bolting, small fittings at ~5% of pipe material | PKG-14 | A-017 | Gaskets, bolting, small fittings at ~5% of pipe material
ASM-TECH | Technical Parameters | ASM-TECH-210 | HVAC System Capacity and Equipment | PKG-22 | A-001 | HVAC System Capacity and Equipment
ASM-TECH | Technical Parameters | ASM-TECH-211 | Instrument Environment Rating | PKG-20 | A-003 | Instrument Environment Rating
ASM-TECH | Technical Parameters | ASM-TECH-212 | Interior process/warehouse area fixtures require IP54+ rating for dust and moist... | PKG-18 | A-1820 | Interior process/warehouse area fixtures require IP54+ rat..
ASM-TECH | Technical Parameters | ASM-TECH-213 | Plumbing Piping Materials and Routing | PKG-22 | A-008 | Plumbing Piping Materials and Routing
ASM-TECH | Technical Parameters | ASM-TECH-214 | Structural Steel Material Supply (Fabricated Tonnage) | PKG-06 | A-006 | Structural Steel Material Supply (Fabricated Tonnage)
ASM-TECH | Technical Parameters | ASM-TECH-215 | Valve materials and coatings suitable for **C4/C5-M corrosion category** (coasta... | PKG-16 | A-1638 | Valve materials and coatings suitable for **C4/C5-M corros..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-216 | Weather/Season Impact | PKG-10 | A-028 | Year-round construction feasible; winterization may affect..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-216 | Weather/Season Impact | PKG-11 | A-016 | Marine work subject to weather windows; no explicit weathe..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-217 | 40-50 I/O modules to support 600-800 I/O points | PKG-19 | A-007 | 40-50 I/O modules to support 600-800 I/O points
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-218 | 6-8 control cabinets (main panels + field junction boxes) | PKG-19 | A-011 | 6-8 control cabinets (main panels + field junction boxes)
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-219 | 8 sump pumps for grouped containment drainage (4 pumps per zone × 2 zones). | PKG-10 | A-005 | 8 sump pumps for grouped containment drainage (4 pumps per..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-220 | 8-10 industrial network switches for control network | PKG-19 | A-009 | 8-10 industrial network switches for control network
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-221 | Access equip | PKG-13 | A-019 | Access equip
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-222 | Actuators and accessories rated for **Class I, Division 2 / Zone 2** (Group D) h... | PKG-16 | A-1639 | Actuators and accessories rated for **Class I, Division 2 ..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-223 | Agitators | PKG-13 | A-006 | Agitators
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-224 | Basic Process Control System (BPCS) only; no separate SIS | PKG-19 | A-014 | Basic Process Control System (BPCS) only; no separate SIS
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-225 | Cable Routing Method | PKG-20 | A-002 | Cable Routing Method
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-226 | Cable Tray Length and Type | PKG-17 | A-1716 | Cable Tray Length and Type
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-227 | Calibration and Loop Testing | PKG-20 | A-020 | Calibration and Loop Testing
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-228 | Canola oil properties assumed as: | PKG-15 | A-005 | Canola oil properties assumed as:
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-229 | Conduit Length and Type | PKG-17 | A-1717 | Conduit Length and Type
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-230 | Construction Duration Assumption | PKG-33 | A-009 | Construction Duration Assumption
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-231 | Construction Duration — 24-30 Months | PKG-34 | A-006 | Construction Duration — 24-30 Months
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-232 | Construction Equipment Rental Rates | PKG-22 | A-011 | Construction Equipment Rental Rates
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-233 | Control Cable Length | PKG-17 | A-1715 | Control Cable Length
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-234 | Control valve complexity: 50% standard globe, 30% ball/butterfly, 20% severe ser... | PKG-16 | A-1605 | Control valve complexity: 50% standard globe, 30% ball/but..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-235 | Control valve positioners use **HART protocol** (digital communication with DCS) | PKG-16 | A-1642 | Control valve positioners use **HART protocol** (digital c..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-236 | Crane | PKG-13 | A-025 | Crane
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-237 | Data Sheet Preparation | PKG-20 | A-014 | Data Sheet Preparation
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-238 | Data sheets | PKG-13 | A-014 | Data sheets
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-239 | Defects Liability Period (12 Months) | PKG-35 | A-008 | Defects Liability Period (12 Months)
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-240 | Document Management Software/Database | PKG-31 | A-006 | Document Management Software/Database
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-241 | ERC is integral with loading arm supply (not separate procurement) | PKG-11 | A-020 | ERC is integral with loading arm supply (not separate proc..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-242 | Electric motors and variable frequency drives (VFDs) estimated as: | PKG-15 | A-004 | Electric motors and variable frequency drives (VFDs) estim..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-243 | Electrical | PKG-13 | A-023 | Electrical
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-244 | Emergency lighting covers code-minimum egress paths plus safety-critical operati... | PKG-18 | A-1825 | Emergency lighting covers code-minimum egress paths plus s..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-245 | Environmental and HSE Compliance | PKG-22 | A-019 | Environmental and HSE Compliance
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-246 | Exterior lighting poles: 30-40 ft height, steel or aluminum construction, galvan... | PKG-18 | A-1826 | Exterior lighting poles: 30-40 ft height, steel or aluminu..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-247 | Exterior lighting poles: 30-50 poles, steel or aluminum, 30-40 ft height, marine... | PKG-18 | A-1807 | Exterior lighting poles: 30-50 poles, steel or aluminum, 3..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-248 | External coating | PKG-13 | A-010 | External coating
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-249 | Fab QA | PKG-13 | A-016 | Fab QA
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-250 | Field Touch-Up Painting and Protective Coatings | PKG-06 | A-013 | Field Touch-Up Painting and Protective Coatings
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-251 | Fire Alarm Control Panel | PKG-23 | A-004 | Fire Alarm Control Panel
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-252 | Fire Alarm Wiring and Conduit | PKG-23 | A-010 | Fire Alarm Wiring and Conduit
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-253 | Fire Detection and Notification Devices | PKG-23 | A-005 | Fire Detection and Notification Devices
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-254 | Fire Sprinkler Piping and Fittings | PKG-22 | A-009 | Fire Sprinkler Piping and Fittings
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-255 | Fire Suppression System (Automatic Sprinklers) | PKG-22 | A-003 | Fire Suppression System (Automatic Sprinklers)
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-256 | Fire Water Supply Source | PKG-23 | A-020 | Fire Water Supply Source
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-257 | Fire Water Valves and Fittings | PKG-23 | A-003 | Fire Water Valves and Fittings
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-258 | Foam Concentrate Storage and Proportioning | PKG-23 | A-006 | Foam Concentrate Storage and Proportioning
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-259 | HSE Staffing Model Assumption | PKG-33 | A-010 | HSE Staffing Model Assumption
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-260 | HVAC Ductwork and Distribution | PKG-22 | A-007 | HVAC Ductwork and Distribution
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-261 | Historian configured for 400-600 process and calculated tags | PKG-19 | A-008 | Historian configured for 400-600 process and calculated ta..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-262 | Hydro test | PKG-13 | A-021 | Hydro test
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-263 | Instrument Conduit System | PKG-20 | A-018 | Instrument Conduit System
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-264 | Instrument Supports and Mounting | PKG-20 | A-017 | Instrument Supports and Mounting
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-265 | Instrument Tubing and Fittings | PKG-20 | A-010 | Instrument Tubing and Fittings
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-266 | Instrumentation | PKG-13 | A-024 | Instrumentation
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-267 | Interior Electrical (Building Services) | PKG-22 | A-004 | Interior Electrical (Building Services)
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-268 | Interior Finishes (Flooring, Walls, Ceilings) | PKG-22 | A-005 | Interior Finishes (Flooring, Walls, Ceilings)
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-269 | Internal coating | PKG-13 | A-009 | Internal coating
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-270 | Isolation valve hydrostatic testing performed as **part of piping hydrostatic te... | PKG-16 | A-1631 | Isolation valve hydrostatic testing performed as **part of..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-271 | LV Power Cable Length | PKG-17 | A-1714 | LV Power Cable Length
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-272 | LV Switchgear Configuration | PKG-17 | A-1708 | LV Switchgear Configuration
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-273 | MV Power Cable Length | PKG-17 | A-1713 | MV Power Cable Length
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-274 | MV Switchgear Configuration | PKG-17 | A-1707 | MV Switchgear Configuration
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-275 | Manholes | PKG-13 | A-008 | Manholes
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-276 | Marine Loading Foam System | PKG-23 | A-008 | Marine Loading Foam System
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-277 | Marine Loading Instrumentation | PKG-20 | A-006 | Marine Loading Instrumentation
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-278 | Miscellaneous Switches | PKG-20 | A-016 | Miscellaneous Switches
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-279 | NDE | PKG-13 | A-022 | NDE
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-280 | Nozzles | PKG-13 | A-007 | Nozzles
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-281 | OEM Training for 8 Major Systems | PKG-35 | A-007 | OEM Training for 8 Major Systems
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-282 | Overflow | PKG-13 | A-017 | Overflow
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-283 | Phase 2 | PKG-13 | A-020 | Phase 2
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-284 | Pipe Supports and Racks | PKG-06 | A-012 | Pipe Supports and Racks
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-285 | Product Classification | PKG-23 | A-021 | Product Classification
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-286 | Railcar Unloading Instrumentation | PKG-20 | A-005 | Railcar Unloading Instrumentation
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-287 | Railcar unloading stations (32 stations) require **16 control valves** (one per ... | PKG-16 | A-1616 | Railcar unloading stations (32 stations) require **16 cont..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-288 | Required illuminance levels assumed based on IESNA recommendations pending ER ex... | PKG-18 | A-1823 | Required illuminance levels assumed based on IESNA recomme..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-289 | Roof type | PKG-13 | A-004 | Roof type
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-290 | Security Compliance Records — DEL-34.04 | PKG-34 | A-005 | Security Compliance Records — DEL-34.04
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-291 | Shell courses | PKG-13 | A-003 | Shell courses
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-292 | Site Conditions | PKG-20 | A-001 | Site Conditions
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-293 | Site Conditions and Access | PKG-22 | A-018 | Site Conditions and Access
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-294 | Stairs and Gangways (Fabricated Items) | PKG-06 | A-011 | Stairs and Gangways (Fabricated Items)
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-295 | Standard industrial control system complexity (typical liquid terminal) | PKG-19 | A-013 | Standard industrial control system complexity (typical liq..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-296 | Steel weight | PKG-13 | A-005 | Steel weight
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-297 | Storage tanks (3 tanks) require **~36 valves total** (12 per tank) | PKG-16 | A-1617 | Storage tanks (3 tanks) require **~36 valves total** (12 p..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-298 | Tank Foam Discharge Systems | PKG-23 | A-007 | Tank Foam Discharge Systems
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-299 | Tank Instrumentation Density | PKG-20 | A-004 | Tank Instrumentation Density
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-300 | Tank dimensions | PKG-13 | A-002 | Tank dimensions
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-301 | Tank sizing | PKG-13 | A-001 | Tank sizing
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-302 | Three remote HMI panels at: railcar unloading area, tank farm, marine loading pl... | PKG-19 | A-005 | Three remote HMI panels at: railcar unloading area, tank f..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-303 | Training Population (30-50 Personnel) | PKG-35 | A-006 | Training Population (30-50 Personnel)
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-304 | Transfer Piping Instrumentation | PKG-20 | A-007 | Transfer Piping Instrumentation
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-305 | Trenchless Crossing Monitoring — DEL-34.05 | PKG-34 | A-001 | Trenchless Crossing Monitoring — DEL-34.05
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-306 | Two redundant DCS/PLC controllers (primary and standby) | PKG-19 | A-003 | Two redundant DCS/PLC controllers (primary and standby)
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-307 | UPS System Sizing | PKG-17 | A-1711 | UPS System Sizing
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-308 | Valve size distribution: 60% small (DN50-100), 30% medium (DN150-200), 10% large... | PKG-16 | A-1602 | Valve size distribution: 60% small (DN50-100), 30% medium ..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-309 | Warranty and Spare Parts | PKG-22 | A-020 | Warranty and Spare Parts
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-310 | Water draw-off | PKG-13 | A-018 | Water draw-off
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-311 | Weld Inspection and NDT | PKG-06 | A-015 | Weld Inspection and NDT

## Risks_Groups
Risks — consolidated groups | [7 empty] | Home
CategoryCode | Category | GroupID | GroupTitle | Theme | PackagesCount | Packages | ItemsCount
RSK-ENV | Environmental Risk | RSK-ENV-001 | Weather/Environmental Risk | Weather/Environmental Risk | 9 | PKG-01, PKG-08, PKG-11, PKG-13, PKG-14, PKG-16, PKG-20, PKG-21, PKG-23 | 10
RSK-ENV | Environmental Risk | RSK-ENV-002 | Marine Logistics Constraints |  | 1 | PKG-08 | 1
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | Cost Escalation Exposure | 11 | PKG-00, PKG-05, PKG-15, PKG-16, PKG-22, PKG-23, PKG-31, PKG-32, PKG-33, PKG-34, PKG-35 | 14
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | Interface & Coordination Risk | 9 | PKG-00, PKG-05, PKG-10, PKG-11, PKG-14, PKG-16, PKG-22, PKG-32, PKG-34 | 16
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 |  | 4 | PKG-27, PKG-28, PKG-29, PKG-30 | 38
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source |  | 2 | PKG-24, PKG-25 | 18
RSK-INTF | Interface Risk | RSK-INTF-007 | PKG-26 risk R-2601 |  | 1 | PKG-26 | 8
RSK-INTF | Interface Risk | RSK-INTF-008 | Control Room Integration |  | 1 | PKG-19 | 1
RSK-INTF | Interface Risk | RSK-INTF-009 | Coordination and Interface Delays |  | 1 | PKG-15 | 1
RSK-INTF | Interface Risk | RSK-INTF-010 | Emergency Response Plan Integration Complexity |  | 1 | PKG-33 | 1
RSK-INTF | Interface Risk | RSK-INTF-011 | Integration with Control System |  | 1 | PKG-15 | 1
RSK-INTF | Interface Risk | RSK-INTF-012 | Integration with Existing Terminal Systems |  | 1 | PKG-19 | 1
RSK-INTF | Interface Risk | RSK-INTF-013 | Interface - Marine Access |  | 1 | PKG-11 | 1
RSK-INTF | Interface Risk | RSK-INTF-014 | Interface with Other Packages (HSE Dependencies) |  | 1 | PKG-33 | 1
RSK-INTF | Interface Risk | RSK-INTF-015 | Loop Testing Coordination |  | 1 | PKG-20 | 1
RSK-INTF | Interface Risk | RSK-INTF-016 | Marine Coordination Complexity |  | 1 | PKG-34 | 1
RSK-INTF | Interface Risk | RSK-INTF-017 | PKG-21 Building Structure Coordination |  | 1 | PKG-22 | 1
RSK-INTF | Interface Risk | RSK-INTF-018 | Site Access and Operational Interface Risk |  | 1 | PKG-16 | 1
RSK-PRICE | Price Uncertainty | RSK-PRICE-019 | No Vendor Pricing/Quotes Available | No Vendor Pricing/Quotes Available | 9 | PKG-00, PKG-01, PKG-05, PKG-10, PKG-11, PKG-14, PKG-15, PKG-16, PKG-34 | 9
RSK-PRICE | Price Uncertainty | RSK-PRICE-020 | Control System Vendor Selection |  | 1 | PKG-19 | 1
RSK-PRICE | Price Uncertainty | RSK-PRICE-021 | Equipment - Loading Arm Pricing |  | 1 | PKG-11 | 1
RSK-PRICE | Price Uncertainty | RSK-PRICE-022 | Marine Contractor Availability and Pricing Volatility |  | 1 | PKG-08 | 1
RSK-PRICE | Price Uncertainty | RSK-PRICE-023 | Steel price volatility |  | 1 | PKG-13 | 1
RSK-PRICE | Price Uncertainty | RSK-PRICE-024 | Vendor FAT Location |  | 1 | PKG-19 | 1
RSK-PRICE | Price Uncertainty | RSK-PRICE-025 | Vendor Quote Unavailability |  | 1 | PKG-22 | 1
RSK-PROD | Productivity Risk | RSK-PROD-026 | Labor Availability & Productivity | Labor Availability & Productivity | 6 | PKG-05, PKG-10, PKG-15, PKG-16, PKG-21, PKG-22 | 7
RSK-PROD | Productivity Risk | RSK-PROD-027 | Site Access During Operations |  | 1 | PKG-20 | 1
RSK-QTY | Quantity Risk | RSK-QTY-028 | Quantity Uncertainty | Quantity Uncertainty | 5 | PKG-05, PKG-15, PKG-16, PKG-20, PKG-33 | 5
RSK-QTY | Quantity Risk | RSK-QTY-029 | Actuator Sizing and Safety Factor Risk |  | 1 | PKG-16 | 1
RSK-QTY | Quantity Risk | RSK-QTY-030 | Method Statement and Risk Assessment Volume |  | 1 | PKG-33 | 1
RSK-QUAL | Quality Risk | RSK-QUAL-031 | Quality/Rework Risk | Quality/Rework Risk | 6 | PKG-11, PKG-13, PKG-14, PKG-15, PKG-31, PKG-35 | 6
RSK-QUAL | Quality Risk | RSK-QUAL-032 | Engineering Effort Underestimated (LOW) |  | 1 | PKG-01 | 1
RSK-QUAL | Quality Risk | RSK-QUAL-033 | NDE findings |  | 1 | PKG-13 | 1
RSK-QUAL | Quality Risk | RSK-QUAL-034 | Underground Utility Conflicts |  | 1 | PKG-23 | 1
RSK-REG | Regulatory Risk | RSK-REG-035 | Regulatory/Permitting Risk | Regulatory/Permitting Risk | 9 | PKG-00, PKG-08, PKG-10, PKG-11, PKG-15, PKG-21, PKG-23, PKG-32, PKG-33 | 10
RSK-SCHED | Schedule Risk | RSK-SCHED-036 | Schedule/Lead Time Risk | Schedule/Lead Time Risk | 11 | PKG-00, PKG-08, PKG-11, PKG-14, PKG-15, PKG-16, PKG-18, PKG-20, PKG-21, PKG-23, PKG-35 | 11
RSK-SCHED | Schedule Risk | RSK-SCHED-037 | Construction Schedule Duration Variance |  | 1 | PKG-33 | 1
RSK-SCHED | Schedule Risk | RSK-SCHED-038 | Employer Staffing Delays (LOW) |  | 1 | PKG-35 | 1
RSK-SCHED | Schedule Risk | RSK-SCHED-039 | Project Duration Extension |  | 1 | PKG-34 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-040 | Scope Definition/Growth Risk | Scope Definition/Growth Risk | 8 | PKG-00, PKG-01, PKG-13, PKG-15, PKG-16, PKG-22, PKG-32, PKG-33 | 12
RSK-SCOPE | Scope Risk | RSK-SCOPE-041 | Technical Design Complexity | Technical Design Complexity | 6 | PKG-05, PKG-08, PKG-13, PKG-14, PKG-18, PKG-21 | 7
RSK-SCOPE | Scope Risk | RSK-SCOPE-042 | Control System Integration | Control System Integration | 3 | PKG-18, PKG-19, PKG-20 | 6
RSK-SCOPE | Scope Risk | RSK-SCOPE-043 | Commissioning/Testing Complexity | Commissioning/Testing Complexity | 5 | PKG-10, PKG-11, PKG-15, PKG-16, PKG-22 | 5
RSK-SCOPE | Scope Risk | RSK-SCOPE-044 | Equipment Specification Risk | Equipment Specification Risk | 1 | PKG-15 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-045 | API 610 Compliance Requirement Interpretation |  | 1 | PKG-15 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-046 | Actuator and Automation Requirements Risk |  | 1 | PKG-16 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-047 | Asset Hierarchy / CMMS Requirements Complexity |  | 1 | PKG-31 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-048 | Canola Oil Fluid Properties and Heating Requirements |  | 1 | PKG-15 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-049 | Containment Performance Requirements |  | 1 | PKG-05 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-050 | ER Illumination Requirements Exceed Typical Standards |  | 1 | PKG-18 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-051 | Employer's Requirements Interpretation Risk |  | 1 | PKG-32 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-052 | Employer's Requirements Not Extracted |  | 1 | PKG-05 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-053 | Food-Grade Material Requirements |  | 1 | PKG-15 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-054 | Food-Grade Material Requirements Risk |  | 1 | PKG-10 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-055 | Language/Translation Requirements (LOW) |  | 1 | PKG-35 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-056 | Plumbing Fixture Count and Hot Water Requirements |  | 1 | PKG-22 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-057 | Scope - Arm Configuration |  | 1 | PKG-11 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-058 | Scope - Header Sizing |  | 1 | PKG-14 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-059 | Scope - Phase 2 Provisions |  | 1 | PKG-14 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-060 | Scope - Pipe Routing |  | 1 | PKG-11 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-061 | Scope - Piping Quantities |  | 1 | PKG-14 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-062 | Security Compliance Scope |  | 1 | PKG-34 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-063 | Site Reinstatement Scope (HIGH) |  | 1 | PKG-35 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-064 | Technical - Insulation Scope |  | 1 | PKG-14 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-065 | Training Scope Expansion (HIGH) |  | 1 | PKG-35 | 1
RSK-SCOPE | Scope Risk | RSK-SCOPE-066 | Trenchless Crossing Monitoring Scope |  | 1 | PKG-34 | 1
RSK-TECH | Technical Risk | RSK-TECH-067 | Geotechnical/Foundation Risk | Geotechnical/Foundation Risk | 4 | PKG-05, PKG-08, PKG-13, PKG-21 | 6
RSK-TECH | Technical Risk | RSK-TECH-068 | As-Built Markup Complexity |  | 1 | PKG-31 | 1
RSK-TECH | Technical Risk | RSK-TECH-069 | Control Valve Complexity and Trim Selection Risk |  | 1 | PKG-16 | 1
RSK-TECH | Technical Risk | RSK-TECH-070 | Network Infrastructure Complexity |  | 1 | PKG-19 | 1
RSK-TECH | Technical Risk | RSK-TECH-071 | Salt Tent Structure Complexity Unknown (LOW) |  | 1 | PKG-01 | 1
RSK-TECH | Technical Risk | RSK-TECH-072 | Seal System Complexity |  | 1 | PKG-15 | 1
RSK-TECH | Technical Risk | RSK-TECH-073 | Technical - Expansion Provisions |  | 1 | PKG-14 | 1
RSK-TECH | Technical Risk | RSK-TECH-074 | Technical - Vessel Envelope |  | 1 | PKG-11 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-075 | Fire Protection Requirements | Fire Protection Requirements | 1 | PKG-23 | 4
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-076 | Hazardous Area Classification | Hazardous Area Classification | 4 | PKG-16, PKG-18, PKG-20, PKG-21 | 4
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-077 | Installation/Construction Complexity | Installation/Construction Complexity | 1 | PKG-15 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-078 | Agitator selection |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-079 | Building Configuration Changes Affecting Interior Lighting |  | 1 | PKG-18 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-080 | Building Size Uncertainty |  | 1 | PKG-22 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-081 | Cable Routing and Length Uncertainty |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-082 | Calibration Equipment Availability |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-083 | Canola Oil Product Compatibility |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-084 | Commissioning - Flushing |  | 1 | PKG-14 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-085 | Containment Configuration Uncertainty |  | 1 | PKG-10 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-086 | Control Valve Positioner and Communication Protocol Risk |  | 1 | PKG-16 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-087 | Disposal Facility Capacity/Cost Changes (MEDIUM) |  | 1 | PKG-01 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-088 | Documentation Completeness (LOW) |  | 1 | PKG-35 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-089 | Drawing Count Variance |  | 1 | PKG-31 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-090 | Emergency Lighting Extent Beyond Code Minimum |  | 1 | PKG-18 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-091 | Equipment Count Variance |  | 1 | PKG-31 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-092 | Fabrication - Welder Availability |  | 1 | PKG-14 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-093 | Fabricator capacity |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-094 | Freight and Logistics Costs |  | 1 | PKG-15 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-095 | HVAC Load Calculation Uncertainty |  | 1 | PKG-22 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-096 | Hazardous Materials Discovery (HIGH) |  | 1 | PKG-01 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-097 | Header Piping Length Variance |  | 1 | PKG-10 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-098 | Heavy lift availability |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-099 | Historian Platform Selection |  | 1 | PKG-19 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-100 | Hydro test water |  | 1 | PKG-13 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-101 | Instrument Supply Chain Disruption |  | 1 | PKG-20 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-102 | Interfacing Equipment Loads Exceed Structural Capacity |  | 1 | PKG-08 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-103 | MCC Building Size Larger Than Assumed |  | 1 | PKG-21 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-104 | Missing Physical Quantities (Site Facilities & Infrastructure) |  | 1 | PKG-00 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-105 | OEM Training Cost Overrun (MEDIUM) |  | 1 | PKG-35 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-106 | Operator Shelter Count Increase |  | 1 | PKG-21 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-107 | Pump Redundancy and N+1 Configuration |  | 1 | PKG-15 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-108 | Relief Valve Scenario Identification Risk |  | 1 | PKG-16 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-109 | Simultaneous Operations and Throughput Risk |  | 1 | PKG-10 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-110 | Site Layout Changes Affecting Exterior Lighting Design |  | 1 | PKG-18 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-111 | Spare Parts Strategy Unknown |  | 1 | PKG-15 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-112 | Stainless Steel Material Premium Risk |  | 1 | PKG-16 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-113 | System Breakdown Variance |  | 1 | PKG-31 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-114 | Temporary Power and Utilities for Commissioning |  | 1 | PKG-15 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-115 | Terminal Operations Conflicts (MEDIUM) |  | 1 | PKG-35 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-116 | Terminal Operations Interference |  | 1 | PKG-23 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-117 | Terminal Operations Interference (MEDIUM) |  | 1 | PKG-01 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-118 | Track 6 Ballast Contamination (HIGH) |  | 1 | PKG-01 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-119 | VFPA Standards Compliance Effort |  | 1 | PKG-31 | 1
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-120 | Valve Size and Specification Risk |  | 1 | PKG-16 | 1

## Risks_Items
Risks — source items | [7 empty] | Home
CategoryCode | Category | GroupID | GroupTitle | Package | RiskID | RiskTitle | Severity
RSK-ENV | Environmental Risk | RSK-ENV-001 | Weather/Environmental Risk | PKG-01 | R-104 | Marine Weather/Tide Delays (MEDIUM) | MEDIUM
RSK-ENV | Environmental Risk | RSK-ENV-001 | Weather/Environmental Risk | PKG-08 | R-805 | Environmental Design Basis More Severe Than Assumed
RSK-ENV | Environmental Risk | RSK-ENV-001 | Weather/Environmental Risk | PKG-11 | R-011 | Environmental - Weather
RSK-ENV | Environmental Risk | RSK-ENV-001 | Weather/Environmental Risk | PKG-13 | R-008 | Weather impacts
RSK-ENV | Environmental Risk | RSK-ENV-001 | Weather/Environmental Risk | PKG-14 | R-016 | Environmental - Material Storage
RSK-ENV | Environmental Risk | RSK-ENV-001 | Weather/Environmental Risk | PKG-16 | R-1620 | Winter Construction Productivity Impact
RSK-ENV | Environmental Risk | RSK-ENV-001 | Weather/Environmental Risk | PKG-20 | R-006 | Marine Environment Corrosion
RSK-ENV | Environmental Risk | RSK-ENV-001 | Weather/Environmental Risk | PKG-20 | R-012 | Winter Weather Impact
RSK-ENV | Environmental Risk | RSK-ENV-001 | Weather/Environmental Risk | PKG-21 | R-004 | Marine Environment Corrosion Protection
RSK-ENV | Environmental Risk | RSK-ENV-001 | Weather/Environmental Risk | PKG-23 | R-010 | Marine Environment Corrosion
RSK-ENV | Environmental Risk | RSK-ENV-002 | Marine Logistics Constraints | PKG-08 | R-802 | Marine Logistics Constraints
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | PKG-00 | R-008 | Currency and Escalation Exposure
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | PKG-05 | R-008 | Escalation Exposure
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | PKG-15 | R-009 | Labor Rate Escalation
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | PKG-15 | R-010 | Currency Exchange Rate Fluctuation
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | PKG-16 | R-1616 | Material Escalation Risk
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | PKG-16 | R-1619 | Currency Exchange Risk
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | PKG-22 | R-008 | Escalation Risk (2-3 Year Project Duration)
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | PKG-23 | R-008 | Escalation Risk
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | PKG-31 | R-008 | Printing/Binding Cost Escalation
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | PKG-32 | R-3205 | Permit Fee Escalation
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | PKG-32 | R-3206 | Resource Rate Escalation
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | PKG-33 | R-007 | HSE Labor Market Escalation
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | PKG-34 | R-008 | Escalation Exposure — Labor Rate Increases
RSK-ESC | Escalation Risk | RSK-ESC-003 | Cost Escalation Exposure | PKG-35 | R-008 | Escalation Exposure (MEDIUM) | MEDIUM
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-00 | R-004 | Terminal Operational Constraints and Interface Complexity
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-05 | R-006 | Interface Coordination Complexity
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-10 | R-005 | Interface Coordination Risk
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-10 | R-010 | PKG-07 Rail Track Interface Risk
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-11 | R-005 | Interface - PKG-08
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-11 | R-009 | Interface - PKG-19
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-14 | R-006 | Interface - PKG-10
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-14 | R-007 | Interface - PKG-11
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-14 | R-008 | Interface - PKG-13
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-14 | R-009 | Interface - PKG-15
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-16 | R-1608 | Relief Valve Set Pressure and Protected Equipment Coordina..
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-22 | R-007 | PKG-19 Control System Interface Scope Split
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-22 | R-011 | Fire Alarm System Interface (PKG-23 vs PKG-22)
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-32 | R-3207 | Coordination and Interface Complexity
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-34 | R-001 | Interface Agreement Complexity and Count
RSK-INTF | Interface Risk | RSK-INTF-004 | Interface & Coordination Risk | PKG-34 | R-006 | Terminal Operations Interface Complexity
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-27 | R-2701 | PKG-27 R-2701
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-27 | R-2702 | PKG-27 R-2702
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-27 | R-2703 | PKG-27 R-2703
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-27 | R-2704 | PKG-27 R-2704
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-27 | R-2705 | PKG-27 R-2705
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-27 | R-2706 | PKG-27 R-2706
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-27 | R-2707 | PKG-27 R-2707
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-27 | R-2708 | PKG-27 R-2708
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-27 | R-2709 | PKG-27 R-2709
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-27 | R-2710 | PKG-27 R-2710
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-28 | R-2801 | PKG-28 R-2801
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-28 | R-2802 | PKG-28 R-2802
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-28 | R-2803 | PKG-28 R-2803
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-28 | R-2804 | PKG-28 R-2804
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-28 | R-2805 | PKG-28 R-2805
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-28 | R-2806 | PKG-28 R-2806
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-28 | R-2807 | PKG-28 R-2807
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-28 | R-2808 | PKG-28 R-2808
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-29 | R-2901 | PKG-29 R-2901
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-29 | R-2902 | PKG-29 R-2902
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-29 | R-2903 | PKG-29 R-2903
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-29 | R-2904 | PKG-29 R-2904
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-29 | R-2905 | PKG-29 R-2905
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-29 | R-2906 | PKG-29 R-2906
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-29 | R-2907 | PKG-29 R-2907
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-29 | R-2908 | PKG-29 R-2908
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-29 | R-2909 | PKG-29 R-2909
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-30 | R-3001 | PKG-30 R-3001
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-30 | R-3002 | PKG-30 R-3002
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-30 | R-3003 | PKG-30 R-3003
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-30 | R-3004 | PKG-30 R-3004
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-30 | R-3005 | PKG-30 R-3005
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-30 | R-3006 | PKG-30 R-3006
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-30 | R-3007 | PKG-30 R-3007
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-30 | R-3008 | PKG-30 R-3008
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-30 | R-3009 | PKG-30 R-3009
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-30 | R-3010 | PKG-30 R-3010
RSK-INTF | Interface Risk | RSK-INTF-005 | PKG-27 R-2701 | PKG-30 | R-3011 | PKG-30 R-3011
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-24 | R-001 | PKG-24 risk R-001 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-24 | R-002 | PKG-24 risk R-002 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-24 | R-003 | PKG-24 risk R-003 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-24 | R-004 | PKG-24 risk R-004 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-24 | R-005 | PKG-24 risk R-005 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-24 | R-006 | PKG-24 risk R-006 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-24 | R-007 | PKG-24 risk R-007 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-24 | R-008 | PKG-24 risk R-008 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-24 | R-009 | PKG-24 risk R-009 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-24 | R-010 | PKG-24 risk R-010 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-25 | R-2501 | PKG-25 risk R-2501 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-25 | R-2502 | PKG-25 risk R-2502 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-25 | R-2503 | PKG-25 risk R-2503 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-25 | R-2504 | PKG-25 risk R-2504 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-25 | R-2505 | PKG-25 risk R-2505 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-25 | R-2506 | PKG-25 risk R-2506 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-25 | R-2507 | PKG-25 risk R-2507 - see source
RSK-INTF | Interface Risk | RSK-INTF-006 | PKG-24 risk R-001 - see source | PKG-25 | R-2508 | PKG-25 risk R-2508 - see source
RSK-INTF | Interface Risk | RSK-INTF-007 | PKG-26 risk R-2601 | PKG-26 | R-2601 | PKG-26 risk R-2601
RSK-INTF | Interface Risk | RSK-INTF-007 | PKG-26 risk R-2601 | PKG-26 | R-2602 | PKG-26 risk R-2602
RSK-INTF | Interface Risk | RSK-INTF-007 | PKG-26 risk R-2601 | PKG-26 | R-2603 | PKG-26 risk R-2603
RSK-INTF | Interface Risk | RSK-INTF-007 | PKG-26 risk R-2601 | PKG-26 | R-2604 | PKG-26 risk R-2604
RSK-INTF | Interface Risk | RSK-INTF-007 | PKG-26 risk R-2601 | PKG-26 | R-2605 | PKG-26 risk R-2605
RSK-INTF | Interface Risk | RSK-INTF-007 | PKG-26 risk R-2601 | PKG-26 | R-2606 | PKG-26 risk R-2606
RSK-INTF | Interface Risk | RSK-INTF-007 | PKG-26 risk R-2601 | PKG-26 | R-2607 | PKG-26 risk R-2607
RSK-INTF | Interface Risk | RSK-INTF-007 | PKG-26 risk R-2601 | PKG-26 | R-2608 | PKG-26 risk R-2608
RSK-INTF | Interface Risk | RSK-INTF-008 | Control Room Integration | PKG-19 | R-007 | Control Room Integration
RSK-INTF | Interface Risk | RSK-INTF-009 | Coordination and Interface Delays | PKG-15 | R-012 | Coordination and Interface Delays
RSK-INTF | Interface Risk | RSK-INTF-010 | Emergency Response Plan Integration Complexity | PKG-33 | R-005 | Emergency Response Plan Integration Complexity
RSK-INTF | Interface Risk | RSK-INTF-011 | Integration with Control System | PKG-15 | R-022 | Integration with Control System
RSK-INTF | Interface Risk | RSK-INTF-012 | Integration with Existing Terminal Systems | PKG-19 | R-009 | Integration with Existing Terminal Systems
RSK-INTF | Interface Risk | RSK-INTF-013 | Interface - Marine Access | PKG-11 | R-006 | Interface - Marine Access
RSK-INTF | Interface Risk | RSK-INTF-014 | Interface with Other Packages (HSE Dependencies) | PKG-33 | R-008 | Interface with Other Packages (HSE Dependencies)
RSK-INTF | Interface Risk | RSK-INTF-015 | Loop Testing Coordination | PKG-20 | R-010 | Loop Testing Coordination
RSK-INTF | Interface Risk | RSK-INTF-016 | Marine Coordination Complexity | PKG-34 | R-003 | Marine Coordination Complexity
RSK-INTF | Interface Risk | RSK-INTF-017 | PKG-21 Building Structure Coordination | PKG-22 | R-006 | PKG-21 Building Structure Coordination
RSK-INTF | Interface Risk | RSK-INTF-018 | Site Access and Operational Interface Risk | PKG-16 | R-1607 | Site Access and Operational Interface Risk
RSK-PRICE | Price Uncertainty | RSK-PRICE-019 | No Vendor Pricing/Quotes Available | PKG-00 | R-001 | Lack of Project-Specific Pricing Sources
RSK-PRICE | Price Uncertainty | RSK-PRICE-019 | No Vendor Pricing/Quotes Available | PKG-01 | R-106 | No Vendor Quotes — Estimate Accuracy (MEDIUM) | MEDIUM
RSK-PRICE | Price Uncertainty | RSK-PRICE-019 | No Vendor Pricing/Quotes Available | PKG-05 | R-001 | No Vendor Pricing Available
RSK-PRICE | Price Uncertainty | RSK-PRICE-019 | No Vendor Pricing/Quotes Available | PKG-10 | R-001 | Unloading Arm Pricing Uncertainty
RSK-PRICE | Price Uncertainty | RSK-PRICE-019 | No Vendor Pricing/Quotes Available | PKG-11 | R-004 | Price - No Quotes
RSK-PRICE | Price Uncertainty | RSK-PRICE-019 | No Vendor Pricing/Quotes Available | PKG-14 | R-005 | Price - No Quotes
RSK-PRICE | Price Uncertainty | RSK-PRICE-019 | No Vendor Pricing/Quotes Available | PKG-15 | R-002 | Equipment Pricing Uncertainty
RSK-PRICE | Price Uncertainty | RSK-PRICE-019 | No Vendor Pricing/Quotes Available | PKG-16 | R-1606 | Vendor Pricing Variability
RSK-PRICE | Price Uncertainty | RSK-PRICE-019 | No Vendor Pricing/Quotes Available | PKG-34 | R-004 | Lack of Project-Specific Pricing Sources
RSK-PRICE | Price Uncertainty | RSK-PRICE-020 | Control System Vendor Selection | PKG-19 | R-001 | Control System Vendor Selection
RSK-PRICE | Price Uncertainty | RSK-PRICE-021 | Equipment - Loading Arm Pricing | PKG-11 | R-001 | Equipment - Loading Arm Pricing
RSK-PRICE | Price Uncertainty | RSK-PRICE-022 | Marine Contractor Availability and Pricing Volatility | PKG-08 | R-806 | Marine Contractor Availability and Pricing Volatility
RSK-PRICE | Price Uncertainty | RSK-PRICE-023 | Steel price volatility | PKG-13 | R-001 | Steel price volatility
RSK-PRICE | Price Uncertainty | RSK-PRICE-024 | Vendor FAT Location | PKG-19 | R-008 | Vendor FAT Location
RSK-PRICE | Price Uncertainty | RSK-PRICE-025 | Vendor Quote Unavailability | PKG-22 | R-004 | Vendor Quote Unavailability
RSK-PROD | Productivity Risk | RSK-PROD-026 | Labor Availability & Productivity | PKG-05 | R-010 | Labor Availability and Productivity
RSK-PROD | Productivity Risk | RSK-PROD-026 | Labor Availability & Productivity | PKG-10 | R-008 | Installation Productivity Risk
RSK-PROD | Productivity Risk | RSK-PROD-026 | Labor Availability & Productivity | PKG-15 | R-004 | Installation Productivity Variance
RSK-PROD | Productivity Risk | RSK-PROD-026 | Labor Availability & Productivity | PKG-16 | R-1611 | Installation Productivity Risk
RSK-PROD | Productivity Risk | RSK-PROD-026 | Labor Availability & Productivity | PKG-21 | R-005 | Constrained Site Access and Productivity
RSK-PROD | Productivity Risk | RSK-PROD-026 | Labor Availability & Productivity | PKG-21 | R-010 | Union Labor Rates or Availability
RSK-PROD | Productivity Risk | RSK-PROD-026 | Labor Availability & Productivity | PKG-22 | R-005 | Construction Labor Availability and Rates (BC Lower Mainla..
RSK-PROD | Productivity Risk | RSK-PROD-027 | Site Access During Operations | PKG-20 | R-007 | Site Access During Operations
RSK-QTY | Quantity Risk | RSK-QTY-028 | Quantity Uncertainty | PKG-05 | R-002 | Quantity Uncertainty — Concrete and Rebar
RSK-QTY | Quantity Risk | RSK-QTY-028 | Quantity Uncertainty | PKG-15 | R-001 | Pump Quantity Uncertainty
RSK-QTY | Quantity Risk | RSK-QTY-028 | Quantity Uncertainty | PKG-16 | R-1601 | Valve Quantity Uncertainty
RSK-QTY | Quantity Risk | RSK-QTY-028 | Quantity Uncertainty | PKG-20 | R-001 | Instrument Count Uncertainty
RSK-QTY | Quantity Risk | RSK-QTY-028 | Quantity Uncertainty | PKG-33 | R-004 | Waste Management Volume Uncertainty
RSK-QTY | Quantity Risk | RSK-QTY-029 | Actuator Sizing and Safety Factor Risk | PKG-16 | R-1613 | Actuator Sizing and Safety Factor Risk
RSK-QTY | Quantity Risk | RSK-QTY-030 | Method Statement and Risk Assessment Volume | PKG-33 | R-003 | Method Statement and Risk Assessment Volume
RSK-QUAL | Quality Risk | RSK-QUAL-031 | Quality/Rework Risk | PKG-11 | R-012 | Quality - Specialty Work
RSK-QUAL | Quality Risk | RSK-QUAL-031 | Quality/Rework Risk | PKG-13 | R-006 | Coating quality
RSK-QUAL | Quality Risk | RSK-QUAL-031 | Quality/Rework Risk | PKG-14 | R-011 | Quality - NDE Rework
RSK-QUAL | Quality Risk | RSK-QUAL-031 | Quality/Rework Risk | PKG-15 | R-018 | Quality Control and Inspection Effort
RSK-QUAL | Quality Risk | RSK-QUAL-031 | Quality/Rework Risk | PKG-31 | R-006 | Vendor Documentation Quality/Completeness
RSK-QUAL | Quality Risk | RSK-QUAL-031 | Quality/Rework Risk | PKG-35 | R-004 | Defects Liability Workload (MEDIUM) | MEDIUM
RSK-QUAL | Quality Risk | RSK-QUAL-032 | Engineering Effort Underestimated (LOW) | PKG-01 | R-109 | Engineering Effort Underestimated (LOW) | LOW
RSK-QUAL | Quality Risk | RSK-QUAL-033 | NDE findings | PKG-13 | R-010 | NDE findings
RSK-QUAL | Quality Risk | RSK-QUAL-034 | Underground Utility Conflicts | PKG-23 | R-007 | Underground Utility Conflicts
RSK-REG | Regulatory Risk | RSK-REG-035 | Regulatory/Permitting Risk | PKG-00 | R-005 | Authority Approvals and Permitting Delays
RSK-REG | Regulatory Risk | RSK-REG-035 | Regulatory/Permitting Risk | PKG-08 | R-804 | Regulatory Approvals and Permitting Delays
RSK-REG | Regulatory Risk | RSK-REG-035 | Regulatory/Permitting Risk | PKG-10 | R-006 | Regulatory Containment Requirements Risk
RSK-REG | Regulatory Risk | RSK-REG-035 | Regulatory/Permitting Risk | PKG-11 | R-013 | Regulatory - Marine Terminal
RSK-REG | Regulatory Risk | RSK-REG-035 | Regulatory/Permitting Risk | PKG-15 | R-021 | Regulatory and Code Compliance Requirements Beyond API 610
RSK-REG | Regulatory Risk | RSK-REG-035 | Regulatory/Permitting Risk | PKG-21 | R-007 | Building Code or Permit Delays
RSK-REG | Regulatory Risk | RSK-REG-035 | Regulatory/Permitting Risk | PKG-23 | R-009 | Code Compliance Requirements
RSK-REG | Regulatory Risk | RSK-REG-035 | Regulatory/Permitting Risk | PKG-32 | R-3202 | Permit Condition Complexity Unknown
RSK-REG | Regulatory Risk | RSK-REG-035 | Regulatory/Permitting Risk | PKG-32 | R-3203 | Authority Approval Timeline Risk
RSK-REG | Regulatory Risk | RSK-REG-035 | Regulatory/Permitting Risk | PKG-33 | R-001 | HSE Regulatory Requirements Uncertainty
RSK-SCHED | Schedule Risk | RSK-SCHED-036 | Schedule/Lead Time Risk | PKG-00 | R-003 | Construction Duration and Schedule Uncertainty
RSK-SCHED | Schedule Risk | RSK-SCHED-036 | Schedule/Lead Time Risk | PKG-08 | R-808 | Schedule Compression Requiring Premium Rates
RSK-SCHED | Schedule Risk | RSK-SCHED-036 | Schedule/Lead Time Risk | PKG-11 | R-008 | Schedule - Long Lead
RSK-SCHED | Schedule Risk | RSK-SCHED-036 | Schedule/Lead Time Risk | PKG-14 | R-012 | Schedule - Long Lead
RSK-SCHED | Schedule Risk | RSK-SCHED-036 | Schedule/Lead Time Risk | PKG-15 | R-015 | Vendor Lead Times and Schedule Impact
RSK-SCHED | Schedule Risk | RSK-SCHED-036 | Schedule/Lead Time Risk | PKG-16 | R-1612 | Vendor Lead Time and Availability Risk
RSK-SCHED | Schedule Risk | RSK-SCHED-036 | Schedule/Lead Time Risk | PKG-18 | R-1807 | LED Fixture Supply Chain and Lead Times
RSK-SCHED | Schedule Risk | RSK-SCHED-036 | Schedule/Lead Time Risk | PKG-20 | R-004 | Instrument Vendor Lead Times
RSK-SCHED | Schedule Risk | RSK-SCHED-036 | Schedule/Lead Time Risk | PKG-21 | R-008 | PEMB Supplier Lead Time
RSK-SCHED | Schedule Risk | RSK-SCHED-036 | Schedule/Lead Time Risk | PKG-23 | R-005 | Fire Protection Equipment Lead Times
RSK-SCHED | Schedule Risk | RSK-SCHED-036 | Schedule/Lead Time Risk | PKG-35 | R-005 | Training Schedule Compression (MEDIUM) | MEDIUM
RSK-SCHED | Schedule Risk | RSK-SCHED-037 | Construction Schedule Duration Variance | PKG-33 | R-006 | Construction Schedule Duration Variance
RSK-SCHED | Schedule Risk | RSK-SCHED-038 | Employer Staffing Delays (LOW) | PKG-35 | R-006 | Employer Staffing Delays (LOW) | LOW
RSK-SCHED | Schedule Risk | RSK-SCHED-039 | Project Duration Extension | PKG-34 | R-002 | Project Duration Extension
RSK-SCOPE | Scope Risk | RSK-SCOPE-040 | Scope Definition/Growth Risk | PKG-00 | R-006 | Road Damage and Restoration Scope Uncertainty
RSK-SCOPE | Scope Risk | RSK-SCOPE-040 | Scope Definition/Growth Risk | PKG-00 | R-007 | Scope Creep — Site Establishment Requirements Growth
RSK-SCOPE | Scope Risk | RSK-SCOPE-040 | Scope Definition/Growth Risk | PKG-01 | R-102 | Dolphin 2 Marine Demolition Scope Uncertainty (HIGH) | HIGH
RSK-SCOPE | Scope Risk | RSK-SCOPE-040 | Scope Definition/Growth Risk | PKG-13 | R-012 | Phase 2 scope creep
RSK-SCOPE | Scope Risk | RSK-SCOPE-040 | Scope Definition/Growth Risk | PKG-15 | R-007 | Engineering Scope Creep or Coordination Effort
RSK-SCOPE | Scope Risk | RSK-SCOPE-040 | Scope Definition/Growth Risk | PKG-16 | R-1615 | Strainer and Specialty Equipment Scope Ambiguity
RSK-SCOPE | Scope Risk | RSK-SCOPE-040 | Scope Definition/Growth Risk | PKG-16 | R-1617 | Engineering Scope Creep Risk
RSK-SCOPE | Scope Risk | RSK-SCOPE-040 | Scope Definition/Growth Risk | PKG-22 | R-003 | Fire Suppression System Scope Uncertainty
RSK-SCOPE | Scope Risk | RSK-SCOPE-040 | Scope Definition/Growth Risk | PKG-22 | R-009 | Interior Finishes Scope Definition
RSK-SCOPE | Scope Risk | RSK-SCOPE-040 | Scope Definition/Growth Risk | PKG-32 | R-3201 | Permit Count and Scope Uncertainty
RSK-SCOPE | Scope Risk | RSK-SCOPE-040 | Scope Definition/Growth Risk | PKG-32 | R-3204 | Regulatory Consultant Scope Creep
RSK-SCOPE | Scope Risk | RSK-SCOPE-040 | Scope Definition/Growth Risk | PKG-33 | R-002 | Environmental Monitoring Scope Creep
RSK-SCOPE | Scope Risk | RSK-SCOPE-041 | Technical Design Complexity | PKG-05 | R-009 | Seismic Requirements
RSK-SCOPE | Scope Risk | RSK-SCOPE-041 | Technical Design Complexity | PKG-08 | R-807 | Design Changes from ER Requirements Not Yet Extracted
RSK-SCOPE | Scope Risk | RSK-SCOPE-041 | Technical Design Complexity | PKG-13 | R-003 | Seismic complexity
RSK-SCOPE | Scope Risk | RSK-SCOPE-041 | Technical Design Complexity | PKG-14 | R-003 | Technical - Transient Analysis
RSK-SCOPE | Scope Risk | RSK-SCOPE-041 | Technical Design Complexity | PKG-14 | R-004 | Technical - Stress Analysis
RSK-SCOPE | Scope Risk | RSK-SCOPE-041 | Technical Design Complexity | PKG-18 | R-1808 | Design Changes from ER Requirements Not Yet Extracted
RSK-SCOPE | Scope Risk | RSK-SCOPE-041 | Technical Design Complexity | PKG-21 | R-003 | Seismic Design Requirements
RSK-SCOPE | Scope Risk | RSK-SCOPE-042 | Control System Integration | PKG-18 | R-1805 | Control System Integration Complexity Higher Than Assumed
RSK-SCOPE | Scope Risk | RSK-SCOPE-042 | Control System Integration | PKG-19 | R-002 | I/O Count Growth
RSK-SCOPE | Scope Risk | RSK-SCOPE-042 | Control System Integration | PKG-19 | R-003 | Software Development Scope Expansion
RSK-SCOPE | Scope Risk | RSK-SCOPE-042 | Control System Integration | PKG-19 | R-004 | Safety Instrumented System (SIS) Requirement
RSK-SCOPE | Scope Risk | RSK-SCOPE-042 | Control System Integration | PKG-19 | R-005 | Cybersecurity Requirements
RSK-SCOPE | Scope Risk | RSK-SCOPE-042 | Control System Integration | PKG-20 | R-005 | Control System Integration
RSK-SCOPE | Scope Risk | RSK-SCOPE-043 | Commissioning/Testing Complexity | PKG-10 | R-009 | Commissioning Scope Risk
RSK-SCOPE | Scope Risk | RSK-SCOPE-043 | Commissioning/Testing Complexity | PKG-11 | R-010 | Commissioning - Complexity
RSK-SCOPE | Scope Risk | RSK-SCOPE-043 | Commissioning/Testing Complexity | PKG-15 | R-008 | Commissioning Complexity and Schedule
RSK-SCOPE | Scope Risk | RSK-SCOPE-043 | Commissioning/Testing Complexity | PKG-16 | R-1618 | Testing and Commissioning Scope Risk
RSK-SCOPE | Scope Risk | RSK-SCOPE-043 | Commissioning/Testing Complexity | PKG-22 | R-012 | Commissioning and Testing Scope (PKG-30 vs PKG-22)
RSK-SCOPE | Scope Risk | RSK-SCOPE-044 | Equipment Specification Risk | PKG-15 | R-003 | Motor and VFD Requirements Uncertainty
RSK-SCOPE | Scope Risk | RSK-SCOPE-045 | API 610 Compliance Requirement Interpretation | PKG-15 | R-011 | API 610 Compliance Requirement Interpretation
RSK-SCOPE | Scope Risk | RSK-SCOPE-046 | Actuator and Automation Requirements Risk | PKG-16 | R-1605 | Actuator and Automation Requirements Risk
RSK-SCOPE | Scope Risk | RSK-SCOPE-047 | Asset Hierarchy / CMMS Requirements Complexity | PKG-31 | R-007 | Asset Hierarchy / CMMS Requirements Complexity
RSK-SCOPE | Scope Risk | RSK-SCOPE-048 | Canola Oil Fluid Properties and Heating Requirements | PKG-15 | R-006 | Canola Oil Fluid Properties and Heating Requirements
RSK-SCOPE | Scope Risk | RSK-SCOPE-049 | Containment Performance Requirements | PKG-05 | R-005 | Containment Performance Requirements
RSK-SCOPE | Scope Risk | RSK-SCOPE-050 | ER Illumination Requirements Exceed Typical Standards | PKG-18 | R-1802 | ER Illumination Requirements Exceed Typical Standards
RSK-SCOPE | Scope Risk | RSK-SCOPE-051 | Employer's Requirements Interpretation Risk | PKG-32 | R-3208 | Employer's Requirements Interpretation Risk
RSK-SCOPE | Scope Risk | RSK-SCOPE-052 | Employer's Requirements Not Extracted | PKG-05 | R-007 | Employer's Requirements Not Extracted
RSK-SCOPE | Scope Risk | RSK-SCOPE-053 | Food-Grade Material Requirements | PKG-15 | R-013 | Food-Grade Material Requirements
RSK-SCOPE | Scope Risk | RSK-SCOPE-054 | Food-Grade Material Requirements Risk | PKG-10 | R-007 | Food-Grade Material Requirements Risk
RSK-SCOPE | Scope Risk | RSK-SCOPE-055 | Language/Translation Requirements (LOW) | PKG-35 | R-007 | Language/Translation Requirements (LOW) | LOW
RSK-SCOPE | Scope Risk | RSK-SCOPE-056 | Plumbing Fixture Count and Hot Water Requirements | PKG-22 | R-010 | Plumbing Fixture Count and Hot Water Requirements
RSK-SCOPE | Scope Risk | RSK-SCOPE-057 | Scope - Arm Configuration | PKG-11 | R-002 | Scope - Arm Configuration
RSK-SCOPE | Scope Risk | RSK-SCOPE-058 | Scope - Header Sizing | PKG-14 | R-002 | Scope - Header Sizing
RSK-SCOPE | Scope Risk | RSK-SCOPE-059 | Scope - Phase 2 Provisions | PKG-14 | R-014 | Scope - Phase 2 Provisions
RSK-SCOPE | Scope Risk | RSK-SCOPE-060 | Scope - Pipe Routing | PKG-11 | R-003 | Scope - Pipe Routing
RSK-SCOPE | Scope Risk | RSK-SCOPE-061 | Scope - Piping Quantities | PKG-14 | R-001 | Scope - Piping Quantities
RSK-SCOPE | Scope Risk | RSK-SCOPE-062 | Security Compliance Scope | PKG-34 | R-007 | Security Compliance Scope
RSK-SCOPE | Scope Risk | RSK-SCOPE-063 | Site Reinstatement Scope (HIGH) | PKG-35 | R-003 | Site Reinstatement Scope (HIGH) | HIGH
RSK-SCOPE | Scope Risk | RSK-SCOPE-064 | Technical - Insulation Scope | PKG-14 | R-013 | Technical - Insulation Scope
RSK-SCOPE | Scope Risk | RSK-SCOPE-065 | Training Scope Expansion (HIGH) | PKG-35 | R-001 | Training Scope Expansion (HIGH) | HIGH
RSK-SCOPE | Scope Risk | RSK-SCOPE-066 | Trenchless Crossing Monitoring Scope | PKG-34 | R-005 | Trenchless Crossing Monitoring Scope
RSK-TECH | Technical Risk | RSK-TECH-067 | Geotechnical/Foundation Risk | PKG-05 | R-003 | Foundation Type Uncertainty
RSK-TECH | Technical Risk | RSK-TECH-067 | Geotechnical/Foundation Risk | PKG-05 | R-004 | Geotechnical Conditions Unknown
RSK-TECH | Technical Risk | RSK-TECH-067 | Geotechnical/Foundation Risk | PKG-08 | R-801 | Geotechnical Conditions Worse Than Assumed
RSK-TECH | Technical Risk | RSK-TECH-067 | Geotechnical/Foundation Risk | PKG-13 | R-004 | Foundation interface
RSK-TECH | Technical Risk | RSK-TECH-067 | Geotechnical/Foundation Risk | PKG-13 | R-005 | Geotechnical conditions
RSK-TECH | Technical Risk | RSK-TECH-067 | Geotechnical/Foundation Risk | PKG-21 | R-002 | Difficult Ground Conditions Requiring Piles
RSK-TECH | Technical Risk | RSK-TECH-068 | As-Built Markup Complexity | PKG-31 | R-005 | As-Built Markup Complexity
RSK-TECH | Technical Risk | RSK-TECH-069 | Control Valve Complexity and Trim Selection Risk | PKG-16 | R-1604 | Control Valve Complexity and Trim Selection Risk
RSK-TECH | Technical Risk | RSK-TECH-070 | Network Infrastructure Complexity | PKG-19 | R-010 | Network Infrastructure Complexity
RSK-TECH | Technical Risk | RSK-TECH-071 | Salt Tent Structure Complexity Unknown (LOW) | PKG-01 | R-108 | Salt Tent Structure Complexity Unknown (LOW) | LOW
RSK-TECH | Technical Risk | RSK-TECH-072 | Seal System Complexity | PKG-15 | R-005 | Seal System Complexity
RSK-TECH | Technical Risk | RSK-TECH-073 | Technical - Expansion Provisions | PKG-14 | R-017 | Technical - Expansion Provisions
RSK-TECH | Technical Risk | RSK-TECH-074 | Technical - Vessel Envelope | PKG-11 | R-007 | Technical - Vessel Envelope
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-075 | Fire Protection Requirements | PKG-23 | R-001 | Fire Water Demand Uncertainty
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-075 | Fire Protection Requirements | PKG-23 | R-002 | Fire Pump Requirement
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-075 | Fire Protection Requirements | PKG-23 | R-003 | Foam System Complexity
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-075 | Fire Protection Requirements | PKG-23 | R-004 | Fire Alarm Integration Complexity
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-076 | Hazardous Area Classification | PKG-16 | R-1610 | Hazardous Area Classification Impact
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-076 | Hazardous Area Classification | PKG-18 | R-1801 | Hazardous Area Classification Extent Exceeds Assumptions
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-076 | Hazardous Area Classification | PKG-20 | R-003 | Hazardous Area Classification
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-076 | Hazardous Area Classification | PKG-21 | R-009 | Hazardous Area Classification Impact
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-077 | Installation/Construction Complexity | PKG-15 | R-020 | Site-Specific Installation Challenges
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-078 | Agitator selection | PKG-13 | R-007 | Agitator selection
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-079 | Building Configuration Changes Affecting Interior Lighting | PKG-18 | R-1804 | Building Configuration Changes Affecting Interior Lighting
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-080 | Building Size Uncertainty | PKG-22 | R-001 | Building Size Uncertainty
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-081 | Cable Routing and Length Uncertainty | PKG-20 | R-002 | Cable Routing and Length Uncertainty
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-082 | Calibration Equipment Availability | PKG-20 | R-008 | Calibration Equipment Availability
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-083 | Canola Oil Product Compatibility | PKG-20 | R-009 | Canola Oil Product Compatibility
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-084 | Commissioning - Flushing | PKG-14 | R-015 | Commissioning - Flushing
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-085 | Containment Configuration Uncertainty | PKG-10 | R-003 | Containment Configuration Uncertainty
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-086 | Control Valve Positioner and Communication Protocol Risk | PKG-16 | R-1609 | Control Valve Positioner and Communication Protocol Risk
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-087 | Disposal Facility Capacity/Cost Changes (MEDIUM) | PKG-01 | R-107 | Disposal Facility Capacity/Cost Changes (MEDIUM) | MEDIUM
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-088 | Documentation Completeness (LOW) | PKG-35 | R-010 | Documentation Completeness (LOW) | LOW
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-089 | Drawing Count Variance | PKG-31 | R-001 | Drawing Count Variance
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-090 | Emergency Lighting Extent Beyond Code Minimum | PKG-18 | R-1806 | Emergency Lighting Extent Beyond Code Minimum
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-091 | Equipment Count Variance | PKG-31 | R-002 | Equipment Count Variance
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-092 | Fabrication - Welder Availability | PKG-14 | R-010 | Fabrication - Welder Availability
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-093 | Fabricator capacity | PKG-13 | R-002 | Fabricator capacity
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-094 | Freight and Logistics Costs | PKG-15 | R-016 | Freight and Logistics Costs
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-095 | HVAC Load Calculation Uncertainty | PKG-22 | R-002 | HVAC Load Calculation Uncertainty
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-096 | Hazardous Materials Discovery (HIGH) | PKG-01 | R-101 | Hazardous Materials Discovery (HIGH) | HIGH
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-097 | Header Piping Length Variance | PKG-10 | R-002 | Header Piping Length Variance
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-098 | Heavy lift availability | PKG-13 | R-009 | Heavy lift availability
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-099 | Historian Platform Selection | PKG-19 | R-006 | Historian Platform Selection
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-100 | Hydro test water | PKG-13 | R-011 | Hydro test water
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-101 | Instrument Supply Chain Disruption | PKG-20 | R-011 | Instrument Supply Chain Disruption
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-102 | Interfacing Equipment Loads Exceed Structural Capacity | PKG-08 | R-803 | Interfacing Equipment Loads Exceed Structural Capacity
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-103 | MCC Building Size Larger Than Assumed | PKG-21 | R-001 | MCC Building Size Larger Than Assumed
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-104 | Missing Physical Quantities (Site Facilities & Infrastructure) | PKG-00 | R-002 | Missing Physical Quantities (Site Facilities & Infrastruct..
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-105 | OEM Training Cost Overrun (MEDIUM) | PKG-35 | R-002 | OEM Training Cost Overrun (MEDIUM) | MEDIUM
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-106 | Operator Shelter Count Increase | PKG-21 | R-006 | Operator Shelter Count Increase
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-107 | Pump Redundancy and N+1 Configuration | PKG-15 | R-019 | Pump Redundancy and N+1 Configuration
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-108 | Relief Valve Scenario Identification Risk | PKG-16 | R-1614 | Relief Valve Scenario Identification Risk
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-109 | Simultaneous Operations and Throughput Risk | PKG-10 | R-004 | Simultaneous Operations and Throughput Risk
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-110 | Site Layout Changes Affecting Exterior Lighting Design | PKG-18 | R-1803 | Site Layout Changes Affecting Exterior Lighting Design
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-111 | Spare Parts Strategy Unknown | PKG-15 | R-014 | Spare Parts Strategy Unknown
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-112 | Stainless Steel Material Premium Risk | PKG-16 | R-1603 | Stainless Steel Material Premium Risk
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-113 | System Breakdown Variance | PKG-31 | R-003 | System Breakdown Variance
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-114 | Temporary Power and Utilities for Commissioning | PKG-15 | R-017 | Temporary Power and Utilities for Commissioning
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-115 | Terminal Operations Conflicts (MEDIUM) | PKG-35 | R-009 | Terminal Operations Conflicts (MEDIUM) | MEDIUM
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-116 | Terminal Operations Interference | PKG-23 | R-006 | Terminal Operations Interference
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-117 | Terminal Operations Interference (MEDIUM) | PKG-01 | R-105 | Terminal Operations Interference (MEDIUM) | MEDIUM
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-118 | Track 6 Ballast Contamination (HIGH) | PKG-01 | R-103 | Track 6 Ballast Contamination (HIGH) | HIGH
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-119 | VFPA Standards Compliance Effort | PKG-31 | R-004 | VFPA Standards Compliance Effort
UNCATEGORIZED | Uncategorized | UNCATEGORIZED-120 | Valve Size and Specification Risk | PKG-16 | R-1602 | Valve Size and Specification Risk

## Detail
LineUID | FromPackageID | FromDeliverableID | LineID | CBS | WBS_PackageID | WBS_DeliverableID | Description | Qty | Unit | UnitRate | Amount | Currency | Method | SourceRef | Confidence | Notes | Category | ContingencyRate | ContingencyAmount | TotalWithContingency | Home
PKG-00::L001 | PKG-00 | DEL-00.01 | L001 | E | PKG-00 | DEL-00.01 | Site Establishment Design Drawing Set - CAD drafting and production (4 drawings) | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-001 | LOW | Allowance for drawing production without vendor quotes or rate tables
PKG-00::L002 | PKG-00 | DEL-00.02 | L002 | E | PKG-00 | DEL-00.02 | Site Establishment Technical Specification - specification writing (2 specifications) | 1 | LS | 10000 | 10000 | CAD | ALLOWANCE | A-002 | LOW | Allowance for specification writing without rate tables
PKG-00::L003 | PKG-00 | DEL-00.03 | L003 | PM | PKG-00 | DEL-00.03 | Site Establishment Procedures - procedure development (3 procedures) | 1 | LS | 9000 | 9000 | CAD | ALLOWANCE | A-003 | LOW | Allowance for PM procedure development
PKG-00::L004 | PKG-00 | DEL-00.04 | L004 | PM | PKG-00 | DEL-00.04 | Contractor's Equipment Schedule - project controls documentation (2 documents) | 1 | LS | 5000 | 5000 | CAD | ALLOWANCE | A-004 | LOW | Allowance for equipment schedule preparation
PKG-00::L005 | PKG-00 | DEL-00.05 | L005 | PM | PKG-00 | DEL-00.05 | Road Access & Security Planning - access/security process documentation (3 plans) | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-005 | LOW | Allowance for security planning and procedure development
PKG-00::L006 | PKG-00 | DEL-00.06 | L006 | E | PKG-00 | DEL-00.06 | Pre-Works Road Condition Survey - field survey and photo documentation | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-006 | LOW | Allowance for surveyor services without vendor quote
PKG-00::L007 | PKG-00 | DEL-00.07 | L007 | E | PKG-00 | DEL-00.07 | Post-Works Road Condition Survey - survey and deficiency closeout | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-007 | LOW | Allowance for post-construction survey services
PKG-00::L008 | PKG-00 | DEL-00.07 | L008 | CD | PKG-00 | DEL-00.07 | Road Deficiency Remediation - asphalt patching and restoration work | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-008 | LOW | Placeholder for road restoration; highly variable based on actual damage
PKG-00::L009 | PKG-00 | DEL-00.08 | L009 | E | PKG-00 | DEL-00.08 | Temporary Water Supply Design - utility design drawings (3 drawings) | 1 | LS | 10000 | 10000 | CAD | ALLOWANCE | A-009 | LOW | Allowance for water supply design effort
PKG-00::L010 | PKG-00 | DEL-00.08 | L010 | MAT | PKG-00 | DEL-00.08 | Temporary Water Supply Materials - pipe fittings backflow preventer valves | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-010 | LOW | Material allowance without vendor quotes or site layout distances
PKG-00::L011 | PKG-00 | DEL-00.08 | L011 | CD | PKG-00 | DEL-00.08 | Temporary Water Supply Installation - plumbing labor connection testing | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-010 | LOW | Installation labor allowance without rate tables
PKG-00::L012 | PKG-00 | DEL-00.05 | L012 | CD | PKG-00 | DEL-00.05 | Security Gate & Access Control Installation - gate hardware and system install | 1 | LS | 75000 | 75000 | CAD | ALLOWANCE | A-011 | LOW | Allowance for security equipment and installation
PKG-00::L013 | PKG-00 |  | L013 | MAT | PKG-00 |  | Temporary Site Facilities - Materials (office trailers welfare facilities fencing) | 1 | LS | 500000 | 500000 | CAD | ALLOWANCE | A-012 | LOW | Material component of site facilities allowance; breakdown: trailers $300k fencing $150k misc $50k
PKG-00::L014 | PKG-00 |  | L014 | CD | PKG-00 |  | Temporary Site Infrastructure - Construction (laydown electrical utilities signage) | 1 | LS | 350000 | 350000 | CAD | ALLOWANCE | A-012 | LOW | Construction component of site infrastructure allowance; breakdown: laydown $150k electrical $120k welfare $80k
PKG-00::L015 | PKG-00 |  | L015 | CI | PKG-00 |  | Security Gate Staffing - construction phase security operations | 1 | LS | 180000 | 180000 | CAD | ALLOWANCE | A-013 | LOW | 24-month gate staffing allowance (12hr/day 6day/week @ $30/hr); hours TBD from schedule
PKG-00::L016 | PKG-00 |  | L016 | CI | PKG-00 |  | Construction Indirects - field supervision site overhead QA/QC (factor-based) | 1 | LS | 85500 | 85500 | CAD | PARAMETRIC | D-006 | LOW | 18% of CD base ($475k CD × 0.18); factor from fallback model
PKG-00::L017 | PKG-00 |  | L017 | PM | PKG-00 |  | EPCM / Project Management - PKG-00 allocation (factor-based) | 1 | LS | 75630 | 75630 | CAD | PARAMETRIC | D-006 | MED | 6% of (CD+CI+MAT) = 6% × ($475k + $265.5k + $520k) = $75.6k; factor from fallback model
PKG-00::L018 | PKG-00 |  | L018 | P | PKG-00 |  | Procurement Services - vendor coordination expediting (factor-based) | 1 | LS | 10400 | 10400 | CAD | PARAMETRIC | D-006 | MED | 2% of MAT = 2% × $520k; factor from fallback model
PKG-01::L101 | PKG-01 | DEL-01.01 | L101 | E | PKG-01 | DEL-01.01 | Demolition Design Drawing Set - CAD drafting and production (demolition plans removal sequence disposal location plans ~6 drawings) | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-101 | LOW | Allowance for demolition drawing production; more complex than site establishment due to phasing and marine interface
PKG-01::L102 | PKG-01 | DEL-01.02 | L102 | E | PKG-01 | DEL-01.02 | Demolition Technical Specification - specification writing (demolition spec disposal requirements) | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-102 | LOW | Allowance for specification writing; includes performance materials workmanship and disposal requirements sections
PKG-01::L103 | PKG-01 | DEL-01.03 | L103 | PM | PKG-01 | DEL-01.03 | Demolition Procedures - method statement and procedure development (5 procedures: general plus Track 6 Dolphin 2 fencing salt tent) | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-103 | LOW | Allowance for HSE procedure development; Track 6 and Dolphin 2 procedures require specialized content
PKG-01::L104 | PKG-01 | DEL-01.04 | L104 | E | PKG-01 | DEL-01.04 | Demolition Installation & Test Records - QA/QC documentation setup and record preparation | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-104 | LOW | Allowance for QA/QC documentation templates record setup and closeout documentation
PKG-01::L105 | PKG-01 |  | L105 | CD | PKG-01 |  | Track 6 Rail Demolition - rail track removal ballast removal tie disposal (assume ~500 LF rail track) | 1 | LS | 175000 | 175000 | CAD | ALLOWANCE | A-105 | LOW | Placeholder for Track 6 demolition; actual cost depends on track length condition and ballast contamination status
PKG-01::L106 | PKG-01 |  | L106 | CD | PKG-01 |  | Dolphin 2 Marine Demolition - marine structure removal including barge/crane mobilization pile cutting deck removal marine debris control | 1 | LS | 450000 | 450000 | CAD | ALLOWANCE | A-106 | LOW | Marine demolition requires specialized marine equipment and crew; placeholder based on typical marine pile structure removal - highly variable
PKG-01::L107 | PKG-01 |  | L107 | CD | PKG-01 |  | Fencing Removal - perimeter fencing demolition and disposal (assume ~2000 LF chain-link or similar) | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-107 | LOW | Placeholder for fencing removal; relatively simple scope but length unknown
PKG-01::L108 | PKG-01 |  | L108 | CD | PKG-01 |  | Salt Tent Dismantling - building structure demolition foundation removal site restoration | 1 | LS | 125000 | 125000 | CAD | ALLOWANCE | A-108 | LOW | Placeholder for salt tent demolition; cost depends on structure type size and foundation requirements
PKG-01::L109 | PKG-01 |  | L109 | MAT | PKG-01 |  | Demolition Materials and Temporary Works - protection barriers dust control erosion control disposal containers | 1 | LS | 40000 | 40000 | CAD | ALLOWANCE | A-109 | LOW | Materials allowance for temporary works and protection measures during demolition
PKG-01::L110 | PKG-01 |  | L110 | CD | PKG-01 |  | Hazardous Materials Contingency Placeholder - potential asbestos lead or contaminated materials (hazmat survey pending) | 1 | LS | 75000 | 75000 | CAD | ALLOWANCE | A-110 | LOW | Contingency placeholder per D-016; hazmat presence unknown - if survey confirms hazmat actual costs may be significantly higher
PKG-01::L111 | PKG-01 |  | L111 | CD | PKG-01 |  | Waste Disposal and Hauling - demolition waste transport to disposal/recycling facilities (concrete steel wood rail materials) | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-111 | LOW | Placeholder for waste disposal; actual cost depends on material volumes disposal distances and tipping fees
PKG-01::L112 | PKG-01 |  | L112 | CI | PKG-01 |  | Construction Indirects - field supervision safety oversight QA/QC coordination (factor-based) | 1 | LS | 171000 | 171000 | CAD | PARAMETRIC | D-017 | LOW | 18% of CD base ($950k CD x 0.18 = $171k); factor from fallback model per D-017
PKG-01::L113 | PKG-01 |  | L113 | PM | PKG-01 |  | EPCM / Project Management - PKG-01 allocation (factor-based) | 1 | LS | 69660 | 69660 | CAD | PARAMETRIC | D-017 | MED | 6% of (CD+CI+MAT) = 6% x ($950k + $171k + $40k) = $69.7k; factor from fallback model per D-017
PKG-01::L114 | PKG-01 |  | L114 | P | PKG-01 |  | Procurement Services - vendor coordination expediting (factor-based) | 1 | LS | 800 | 800 | CAD | PARAMETRIC | D-017 | MED | 2% of MAT = 2% x $40k = $800; factor from fallback model per D-017
PKG-02::L001 | PKG-02 | DEL-02.01 | L001 | E | PKG-02 | DEL-02.01 | Earthworks Design Drawing Set - CAD drafting (grading plans cut/fill plans ground improvement sections) | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-001 | LOW | ~8-10 sheets at $3k/sheet average
PKG-02::L002 | PKG-02 | DEL-02.02 | L002 | E | PKG-02 | DEL-02.02 | Earthworks Technical Specification - specification writing (earthworks ground improvement geotextile specs) | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-002 | LOW | ~50 hours at $150/hr
PKG-02::L003 | PKG-02 | DEL-02.03 | L003 | E | PKG-02 | DEL-02.03 | Earthworks Design Calculations - cut/fill calculations bearing capacity settlement analysis | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-003 | LOW | ~70 hours at $175/hr
PKG-02::L004 | PKG-02 | DEL-02.04 | L004 | E | PKG-02 | DEL-02.04 | Geotechnical Investigation - field drilling program (15-20 boreholes 15-25m deep) | 1 | LS | 100000 | 100000 | CAD | ALLOWANCE | A-004 | LOW | Drilling mobilization boreholes sampling monitoring wells
PKG-02::L005 | PKG-02 | DEL-02.04 | L005 | E | PKG-02 | DEL-02.04 | Geotechnical Laboratory Testing - soil classification strength compaction tests | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-005 | LOW | Full lab program for design parameters
PKG-02::L006 | PKG-02 | DEL-02.04 | L006 | E | PKG-02 | DEL-02.04 | Geotechnical Reporting - investigation report and ground improvement design | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-006 | LOW | ~100 hours engineering time
PKG-02::L007 | PKG-02 | DEL-02.05 | L007 | E | PKG-02 | DEL-02.05 | Topographic Survey - site survey including utility locates (~7 ha) | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-007 | LOW | Survey and CAD deliverables
PKG-02::L008 | PKG-02 | DEL-02.06 | L008 | E | PKG-02 | DEL-02.06 | Earthworks QA/QC Records Compilation - test records documentation | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-009 | LOW | ~120 hours record compilation
PKG-02::L009 | PKG-02 | DEL-02.07 | L009 | E | PKG-02 | DEL-02.07 | Excavation & Fill Placement Method Statement - procedure development | 1 | LS | 6000 | 6000 | CAD | ALLOWANCE | A-010 | LOW | ~40 hours at $140/hr
PKG-02::L010 | PKG-02 | DEL-02.08 | L010 | E | PKG-02 | DEL-02.08 | Sampling & Testing Program Development | 1 | LS | 4000 | 4000 | CAD | ALLOWANCE | A-011 | LOW | ~30 hours
PKG-02::L011 | PKG-02 | DEL-02.09 | L011 | E | PKG-02 | DEL-02.09 | Compaction Verification Plan Development | 1 | LS | 3500 | 3500 | CAD | ALLOWANCE | A-012 | LOW | ~25 hours
PKG-02::L012 | PKG-02 |  | L012 | CD | PKG-02 |  | Site Stripping & Grubbing - topsoil removal vegetation clearing (~5 ha) | 1 | LS | 75000 | 75000 | CAD | ALLOWANCE | A-013 | LOW | $15k/ha × 5 ha
PKG-02::L013 | PKG-02 |  | L013 | CD | PKG-02 |  | Excavation - cut to design grades (~15000 m³) | 1 | LS | 180000 | 180000 | CAD | ALLOWANCE | A-014 | LOW | $12/m³ × 15000 m³
PKG-02::L014 | PKG-02 |  | L014 | MAT | PKG-02 |  | Imported Structural Fill Material - supply of engineered fill (~25000 m³) | 1 | LS | 375000 | 375000 | CAD | ALLOWANCE | A-015 | LOW | $15/m³ × 25000 m³ material only
PKG-02::L015 | PKG-02 |  | L015 | CD | PKG-02 |  | Fill Placement & Compaction - place and compact in lifts (~25000 m³) | 1 | LS | 250000 | 250000 | CAD | ALLOWANCE | A-015 | LOW | $10/m³ placement and compaction labor
PKG-02::L016 | PKG-02 |  | L016 | MAT | PKG-02 |  | Ground Improvement Materials - stone columns/aggregate (~30000 m²) | 1 | LS | 600000 | 600000 | CAD | ALLOWANCE | A-016 | LOW | $20/m² material component
PKG-02::L017 | PKG-02 |  | L017 | CD | PKG-02 |  | Ground Improvement Installation - vibro-compaction/stone columns (~30000 m²) | 1 | LS | 900000 | 900000 | CAD | ALLOWANCE | A-017 | LOW | $30/m² installation
PKG-02::L018 | PKG-02 |  | L018 | CD | PKG-02 |  | Compaction Testing - nuclear density/sand cone tests (~50 tests) | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-018 | LOW | Testing during fill placement
PKG-02::L019 | PKG-02 |  | L019 | CD | PKG-02 |  | Proof Rolling - verification of structural areas | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-019 | LOW | Proof roll with loaded truck
PKG-02::L020 | PKG-02 |  | L020 | CD | PKG-02 |  | Dewatering - temporary dewatering for excavations | 1 | LS | 50000 | 50000 | CAD | ALLOWANCE | A-021 | LOW | Pumping and disposal allowance
PKG-02::L021 | PKG-02 |  | L021 | MAT | PKG-02 |  | Geotextile Separation Layer - fabric under fill areas (~20000 m²) | 1 | LS | 160000 | 160000 | CAD | ALLOWANCE | A-022 | LOW | $8/m² installed
PKG-02::L022 | PKG-02 |  | L022 | CD | PKG-02 |  | Fine Grading - final grade preparation for pavements/structures | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | D-012 | LOW | ~5 ha at $9k/ha
PKG-02::L023 | PKG-02 |  | L023 | CD | PKG-02 |  | Erosion & Sediment Control - temporary measures during construction | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | D-012 | LOW | Silt fence sediment traps
PKG-02::L024 | PKG-02 |  | L024 | CI | PKG-02 |  | Construction Indirects - field supervision site overhead QA/QC (factor-based) | 1 | LS | 279000 | 279000 | CAD | PARAMETRIC | D-009 | LOW | 18% of CD base ($1.55M × 0.18)
PKG-02::L025 | PKG-02 |  | L025 | PM | PKG-02 |  | EPCM / Project Management - PKG-02 allocation (factor-based) | 1 | LS | 176000 | 176000 | CAD | PARAMETRIC | D-009 | MED | 6% of (CD+CI+MAT) base
PKG-02::L026 | PKG-02 |  | L026 | P | PKG-02 |  | Procurement Services - vendor coordination expediting (factor-based) | 1 | LS | 23000 | 23000 | CAD | PARAMETRIC | D-009 | MED | 2% of MAT ($1.135M × 0.02)
PKG-02::L027 | PKG-02 |  | L027 | COM | PKG-02 |  | Testing & Verification - final verification testing reporting | 1 | LS | 88000 | 88000 | CAD | PARAMETRIC | D-009 | LOW | 3% of (CD+CI+MAT) base
PKG-03::L-001 | PKG-03 | DEL-03.01 | L-001 | E | PKG-03 | DEL-03.01 | Civil engineering design - Underground Utilities Design Drawing Set | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-006 | LOW | Drawing set production including storm drainage plans/profiles; OWS layout; duct banks; trenchless crossings; CAD technician hours included
PKG-03::L-002 | PKG-03 | DEL-03.02 | L-002 | E | PKG-03 | DEL-03.02 | Civil engineering design - Underground Utilities Technical Specification | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-006 | LOW | Specification development for storm drainage; OWS; duct banks; trenchless crossings; materials and workmanship requirements
PKG-03::L-003 | PKG-03 | DEL-03.03 | L-003 | E | PKG-03 | DEL-03.03 | Civil engineering design - Underground Utilities Design Calculations | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-006 | LOW | Hydraulic calculations; OWS sizing; duct bank capacity analysis; trenchless crossing structural calculations
PKG-03::L-004 | PKG-03 | DEL-03.04 | L-004 | E | PKG-03 | DEL-03.04 | Civil engineering design - Underground Utilities Data Sheet Package | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-006 | LOW | Equipment and material data sheets for OWS; pipes; instrumentation; pumps
PKG-03::L-005 | PKG-03 | DEL-03.06 | L-005 | E | PKG-03 | DEL-03.06 | Specialist CCTV survey and reporting | 1 | LS | 32000 | 32000 | CAD | ALLOWANCE | A-013 | LOW | CCTV inspection of storm drainage pipes; defect analysis; remediation recommendations; video file archival; assumes 800-1200 LM survey extent
PKG-03::L-006 | PKG-03 | DEL-03.01 | L-006 | MAT | PKG-03 | DEL-03.01 | Storm drainage pipe and fittings | 1 | LS | 185000 | 185000 | CAD | ALLOWANCE | A-001 + A-009 | LOW | HDPE/concrete/PVC storm pipes DN150-DN600; approximately 800-1200 LM total; includes fittings; bedding materials; pipe material pricing per A-009
PKG-03::L-007 | PKG-03 | DEL-03.01 | L-007 | MAT | PKG-03 | DEL-03.01 | Manholes and catch basins | 1 | LS | 155000 | 155000 | CAD | ALLOWANCE | A-002 + A-009 | LOW | Precast concrete manholes (15-25 units) and catch basins (25-40 units); includes frames/covers/castings; manhole pricing per A-009
PKG-03::L-008 | PKG-03 | DEL-03.04 | L-008 | MAT | PKG-03 | DEL-03.04 | Oil-Water Separator equipment and instrumentation | 1 | LS | 135000 | 135000 | CAD | ALLOWANCE | A-003 + A-009 | LOW | Packaged OWS unit 50-100 L/s capacity; includes internals; instrumentation (level; flow; oil layer monitors; alarms); piping/sumps; OWS pricing per A-009 and A-023 discharge limits
PKG-03::L-009 | PKG-03 | DEL-03.01 | L-009 | MAT | PKG-03 | DEL-03.01 | Duct bank materials | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-004 + A-009 | LOW | PVC/HDPE conduit 400-600 LM total; concrete encasement; pull boxes (10-15 units); conduit pricing per A-009
PKG-03::L-010 | PKG-03 | DEL-03.01 | L-010 | CD | PKG-03 | DEL-03.01 | Storm drainage installation | 1 | LS | 385000 | 385000 | CAD | ALLOWANCE | A-001 + A-010 + A-011 + A-015 | LOW | Excavation (1500-2500 m³); pipe laying (800-1200 LM); manhole/catch basin installation; backfill/compaction; includes dewatering (A-016); shoring (A-017); labor/equipment per A-010/A-011
PKG-03::L-011 | PKG-03 | DEL-03.04 | L-011 | CD | PKG-03 | DEL-03.04 | OWS installation | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-003 + A-010 + A-011 | LOW | OWS equipment installation; piping connections; instrumentation installation; sump construction; electrical tie-ins; testing support; labor/equipment per A-010/A-011
PKG-03::L-012 | PKG-03 | DEL-03.01 | L-012 | CD | PKG-03 | DEL-03.01 | Duct bank installation | 1 | LS | 145000 | 145000 | CAD | ALLOWANCE | A-004 + A-010 + A-011 + A-015 | LOW | Trench excavation; conduit installation; concrete encasement; pull box installation; backfill/compaction; includes shoring/dewatering; labor/equipment per A-010/A-011
PKG-03::L-013 | PKG-03 | DEL-03.01 | L-013 | CD | PKG-03 | DEL-03.01 | Trenchless crossings | 1 | LS | 265000 | 265000 | CAD | ALLOWANCE | A-005 + A-012 | LOW | Auger boring or HDD (4-8 crossings; 15-40m each); casing pipe DN200-DN600; carrier pipe installation; grouting; entry/exit pits; mobilization; boring services per A-012
PKG-03::L-014 | PKG-03 | DEL-03.05 | L-014 | CD | PKG-03 | DEL-03.05 | Installation support and site works | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-018 + A-019 | LOW | Traffic management and access control; environmental protection during construction (erosion/sediment control; SWPPP); site restoration; cleanup; assumptions per A-018 and A-019
PKG-03::L-015 | PKG-03 |  | L-015 | CI | PKG-03 |  | Construction Indirects (factor-based) | 1 | LS | 175500 | 175500 | CAD | PARAMETRIC | D-009 (factor=0.18) | MEDIUM | CI = 0.18 × CD ($975k); includes site supervision; temporary facilities; HSE; QA/QC field inspection; construction management; small tools; per fallback typical model
PKG-03::L-016 | PKG-03 |  | L-016 | P | PKG-03 |  | Procurement Services (factor-based) | 1 | LS | 11400 | 11400 | CAD | PARAMETRIC | D-009 (factor=0.02) | MEDIUM | P = 0.02 × MAT ($570k); includes material sourcing; PO processing; expediting; receiving inspection; material documentation; per fallback typical model
PKG-03::L-017 | PKG-03 |  | L-017 | PM | PKG-03 |  | EPCM/Project Management (factor-based) | 1 | LS | 103000 | 103000 | CAD | PARAMETRIC | D-009 (factor=0.06) | MEDIUM | PM = 0.06 × (CD + CI + MAT) ($1721k); includes project management; engineering management; schedule/cost control; contract administration; stakeholder coordination; per fallback typical model
PKG-03::L-018 | PKG-03 |  | L-018 | COM | PKG-03 |  | Commissioning (factor-based) | 1 | LS | 52000 | 52000 | CAD | PARAMETRIC | D-009 (factor=0.03) | MEDIUM | COM = 0.03 × (CD + CI + MAT) ($1721k); includes pre-commissioning; performance testing per DEL-03.05 (pressure testing; CCTV; OWS performance verification; as-built survey); system acceptance; handover; per fallback typical model
PKG-04::L001 | PKG-04 | DEL-04.01 | L001 | E | PKG-04 | DEL-04.01 | Pavement Design Drawing Set - CAD drafting (paving layout plans sections details line marking plans) | 1 | LS | 32000 | 32000 | CAD | ALLOWANCE | A-007 | LOW | ~10-12 sheets at $3k/sheet average
PKG-04::L002 | PKG-04 | DEL-04.02 | L002 | E | PKG-04 | DEL-04.02 | Pavement Technical Specification - specification writing (asphalt concrete base line marking QC specs) | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-008 | LOW | ~50 hours at $160/hr
PKG-04::L003 | PKG-04 | DEL-04.03 | L003 | E | PKG-04 | DEL-04.03 | Pavement Design Calculations - layer thickness design load analysis structural capacity verification | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-009 | LOW | ~60 hours at $200/hr
PKG-04::L004 | PKG-04 | DEL-04.04 | L004 | E | PKG-04 | DEL-04.04 | Pavement QA/QC Records Compilation - test records documentation acceptance records | 1 | LS | 10000 | 10000 | CAD | ALLOWANCE | A-010 | LOW | ~80 hours at $125/hr
PKG-04::L005 | PKG-04 |  | L005 | MAT | PKG-04 |  | Asphalt Concrete Supply - dense-graded HMA for wearing/binder/base courses (~35000 m² × 150mm avg) | 1 | LS | 700000 | 700000 | CAD | ALLOWANCE | A-001 | LOW | ~8000 tonnes at $85/tonne
PKG-04::L006 | PKG-04 |  | L006 | CD | PKG-04 |  | Asphalt Paving Installation - place and compact wearing/binder/base courses (~35000 m²) | 1 | LS | 525000 | 525000 | CAD | ALLOWANCE | A-001 | LOW | $15/m² placement + compaction labor
PKG-04::L007 | PKG-04 |  | L007 | MAT | PKG-04 |  | Concrete Paving Materials - PCC for heavy load areas (~10000 m² × 200mm) | 1 | LS | 400000 | 400000 | CAD | ALLOWANCE | A-002 | LOW | $40/m² material (concrete reinforcement joints)
PKG-04::L008 | PKG-04 |  | L008 | CD | PKG-04 |  | Concrete Paving Installation - place finish cure joint sawing (~10000 m²) | 1 | LS | 700000 | 700000 | CAD | ALLOWANCE | A-002 | LOW | $70/m² placement finishing curing
PKG-04::L009 | PKG-04 |  | L009 | MAT | PKG-04 |  | Granular Base Course Material - crushed aggregate base (~45000 m² × 200mm) | 1 | LS | 315000 | 315000 | CAD | ALLOWANCE | A-011 | LOW | ~13500 tonnes at $23/tonne delivered
PKG-04::L010 | PKG-04 |  | L010 | CD | PKG-04 |  | Base Course Placement and Compaction (~45000 m²) | 1 | LS | 180000 | 180000 | CAD | ALLOWANCE | A-011 | LOW | $4/m² spread and compact
PKG-04::L011 | PKG-04 |  | L011 | MAT | PKG-04 |  | Curb and Gutter Materials - precast or cast-in-place concrete (~2500 lm) | 1 | LS | 75000 | 75000 | CAD | ALLOWANCE | A-003 | LOW | $30/lm material
PKG-04::L012 | PKG-04 |  | L012 | CD | PKG-04 |  | Curb and Gutter Installation - forming placing finishing (~2500 lm) | 1 | LS | 125000 | 125000 | CAD | ALLOWANCE | A-003 | LOW | $50/lm labor equipment
PKG-04::L013 | PKG-04 |  | L013 | MAT | PKG-04 |  | Sidewalk Materials - concrete (~600 m² × 100mm) | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-004 | LOW | $30/m² material
PKG-04::L014 | PKG-04 |  | L014 | CD | PKG-04 |  | Sidewalk Installation - form place finish cure (~600 m²) | 1 | LS | 30000 | 30000 | CAD | ALLOWANCE | A-004 | LOW | $50/m² labor
PKG-04::L015 | PKG-04 |  | L015 | MAT | PKG-04 |  | Line Marking Materials - thermoplastic and paint (~6000 lm) | 1 | LS | 24000 | 24000 | CAD | ALLOWANCE | A-006 | LOW | $4/lm material
PKG-04::L016 | PKG-04 |  | L016 | CD | PKG-04 |  | Line Marking Application - traffic control safety markings parking stalls (~6000 lm) | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-006 | LOW | $3/lm labor equipment
PKG-04::L017 | PKG-04 |  | L017 | CD | PKG-04 |  | Subgrade Fine Grading - final grade preparation before base course (~45000 m²) | 1 | LS | 90000 | 90000 | CAD | ALLOWANCE | A-012 | LOW | $2/m² fine grading
PKG-04::L018 | PKG-04 |  | L018 | MAT | PKG-04 |  | Tack Coat and Prime Coat Materials (~35000 m²) | 1 | LS | 28000 | 28000 | CAD | ALLOWANCE | A-013 | LOW | $0.80/m² material
PKG-04::L019 | PKG-04 |  | L019 | CD | PKG-04 |  | Tack Coat and Prime Coat Application (~35000 m²) | 1 | LS | 17500 | 17500 | CAD | ALLOWANCE | A-013 | LOW | $0.50/m² application
PKG-04::L020 | PKG-04 |  | L020 | CD | PKG-04 |  | Compaction Testing - nuclear density tests during paving (~90 tests) | 1 | LS | 27000 | 27000 | CAD | ALLOWANCE | A-014 | LOW | $300/test avg
PKG-04::L021 | PKG-04 |  | L021 | CD | PKG-04 |  | Core Sampling and Testing - thickness verification (~25 cores) | 1 | LS | 12500 | 12500 | CAD | ALLOWANCE | A-014 | LOW | $500/core extraction and lab testing
PKG-04::L022 | PKG-04 |  | L022 | CD | PKG-04 |  | Survey and Grade Control - layout staking grade verification | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | D-011 | LOW | Survey crew during construction
PKG-04::L023 | PKG-04 |  | L023 | MAT | PKG-04 |  | Expansion Joints and Sealants - pavement joints at structures and Phase 2 tie-ins | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-016 | LOW | Joint materials and sealant
PKG-04::L024 | PKG-04 |  | L024 | CD | PKG-04 |  | Expansion Joint Installation - sawcutting sealing at structures (~500 lm) | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-016 | LOW | $50/lm
PKG-04::L025 | PKG-04 |  | L025 | CD | PKG-04 |  | OBJ-8 Phase 2 Tie-in Provisions - enhanced documentation and joint protection | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-017 | LOW | Additional work for expansion corridors
PKG-04::L026 | PKG-04 |  | L026 | CI | PKG-04 |  | Construction Indirects - field supervision site overhead QA/QC (factor-based) | 1 | LS | 340000 | 340000 | CAD | PARAMETRIC | D-008 | LOW | 18% of CD base ($1.89M × 0.18)
PKG-04::L027 | PKG-04 |  | L027 | PM | PKG-04 |  | EPCM / Project Management - PKG-04 allocation (factor-based) | 1 | LS | 219000 | 219000 | CAD | PARAMETRIC | D-008 | MED | 6% of (CD+CI+MAT) base
PKG-04::L028 | PKG-04 |  | L028 | P | PKG-04 |  | Procurement Services - vendor coordination expediting (factor-based) | 1 | LS | 32000 | 32000 | CAD | PARAMETRIC | D-008 | MED | 2% of MAT ($1.595M × 0.02)
PKG-04::L029 | PKG-04 |  | L029 | COM | PKG-04 |  | Testing and Verification - final verification testing reporting | 1 | LS | 109000 | 109000 | CAD | PARAMETRIC | D-008 | LOW | 3% of (CD+CI+MAT) base
PKG-05::L001 | PKG-05 | DEL-05.01 | L001 | E | PKG-05 | DEL-05.01 | Concrete Structures Design Drawing Set - structural CAD drafting (22 sheets) | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-001 | LOW | Allowance for drawing production without vendor quotes; includes foundations containment walls equipment pads reinforcement
PKG-05::L002 | PKG-05 | DEL-05.02 | L002 | E | PKG-05 | DEL-05.02 | Concrete Structures Technical Specification - specification writing (3 specifications) | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-002 | LOW | Allowance for concrete reinforcement formwork specifications
PKG-05::L003 | PKG-05 | DEL-05.03 | L003 | E | PKG-05 | DEL-05.03 | Concrete Structures Design Calculations - structural engineering (foundation containment seismic) | 1 | LS | 120000 | 120000 | CAD | ALLOWANCE | A-003 | LOW | Allowance for design calculations including tank foundations containment walls seismic analysis
PKG-05::L004 | PKG-05 | DEL-05.04 | L004 | PM | PKG-05 | DEL-05.04 | Installation & Test Records - QA/QC documentation and coordination | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-004 | LOW | Allowance for concrete pour records cylinder test coordination rebar inspection records
PKG-05::L005 | PKG-05 |  | L005 | MAT | PKG-05 |  | Tank Foundation Concrete - ready-mix supply for 3x15000 MT tank ring walls | 450 | m3 | 220 | 99000 | CAD | ALLOWANCE | A-005 | LOW | 450 m3 derived from 3 tanks x 150 m3 each; ring wall type per D-011
PKG-05::L006 | PKG-05 |  | L006 | CD | PKG-05 |  | Tank Foundation Installation - concrete placement forming curing | 450 | m3 | 180 | 81000 | CAD | ALLOWANCE | A-005 | LOW | Installation rate for slab/foundation work
PKG-05::L007 | PKG-05 |  | L007 | MAT | PKG-05 |  | Containment Wall Concrete - high-quality ready-mix for secondary containment | 600 | m3 | 240 | 144000 | CAD | ALLOWANCE | A-006 | LOW | 600 m3 for perimeter walls supporting OBJ-7 Environmental Protection; premium mix for low permeability
PKG-05::L008 | PKG-05 |  | L008 | CD | PKG-05 |  | Containment Wall Installation - concrete placement with waterstops complex formwork | 600 | m3 | 350 | 210000 | CAD | ALLOWANCE | A-006 | LOW | Higher rate for wall construction with waterstops and containment-grade finishing
PKG-05::L009 | PKG-05 |  | L009 | MAT | PKG-05 |  | Equipment Pad Concrete - ready-mix for pump metering railcar unloading pads | 200 | m3 | 230 | 46000 | CAD | ALLOWANCE | A-007 | LOW | 200 m3 for various equipment pads; includes anchor bolt blockouts
PKG-05::L010 | PKG-05 |  | L010 | CD | PKG-05 |  | Equipment Pad Installation - concrete placement with anchor bolts and grout pockets | 200 | m3 | 250 | 50000 | CAD | ALLOWANCE | A-007 | LOW | Installation includes precision anchor bolt placement
PKG-05::L011 | PKG-05 |  | L011 | MAT | PKG-05 |  | Thrust Block Concrete - ready-mix for underground piping thrust blocks | 80 | m3 | 210 | 16800 | CAD | ALLOWANCE | A-008 | LOW | 80 m3 for approximately 20 thrust block locations
PKG-05::L012 | PKG-05 |  | L012 | CD | PKG-05 |  | Thrust Block Installation - concrete placement in trench locations | 80 | m3 | 200 | 16000 | CAD | ALLOWANCE | A-008 | LOW | Installation in excavated locations
PKG-05::L013 | PKG-05 |  | L013 | MAT | PKG-05 |  | Reinforcing Steel Supply - fabricated rebar delivered (all structures) | 180000 | kg | 2 | 360000 | CAD | ALLOWANCE | A-009 | LOW | 180 tonnes total; 100-150 kg/m3 ratio depending on element type
PKG-05::L014 | PKG-05 |  | L014 | CD | PKG-05 |  | Reinforcing Steel Installation - placement tying inspection | 180000 | kg | 1 | 180000 | CAD | ALLOWANCE | A-009 | LOW | Installation labor for rebar placement
PKG-05::L015 | PKG-05 |  | L015 | MAT | PKG-05 |  | Wall Formwork Materials - rental/purchase for containment walls | 1500 | m2 | 40 | 60000 | CAD | ALLOWANCE | A-010 | LOW | 1500 m2 contact area for containment wall faces
PKG-05::L016 | PKG-05 |  | L016 | CD | PKG-05 |  | Wall Formwork Installation - form erection stripping and cleaning | 1500 | m2 | 50 | 75000 | CAD | ALLOWANCE | A-010 | LOW | Formwork labor for wall construction
PKG-05::L017 | PKG-05 |  | L017 | MAT | PKG-05 |  | Waterstops and Joint Materials - PVC waterstops sealants fillers | 1 | LS | 30000 | 30000 | CAD | ALLOWANCE | A-011 | LOW | 600m of construction joints with waterstops for containment integrity
PKG-05::L018 | PKG-05 |  | L018 | CD | PKG-05 |  | Waterstop Installation - joint preparation waterstop placement sealing | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-011 | LOW | Installation labor for waterstops and joint treatment
PKG-05::L019 | PKG-05 |  | L019 | MAT | PKG-05 |  | Ground Liner Interface Materials - anchor curbs penetration details | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-012 | LOW | Concrete curbs and penetration sealing for liner system interface
PKG-05::L020 | PKG-05 |  | L020 | CD | PKG-05 |  | Ground Liner Interface Installation - curb construction and penetration work | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-012 | LOW | Installation of liner anchor system and penetration details
PKG-05::L021 | PKG-05 |  | L021 | CI | PKG-05 |  | Concrete Testing and Quality Control - cylinder testing field QC third-party inspection | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-013 | MED | Testing program for 1330 m3 concrete; includes lab and field testing
PKG-05::L022 | PKG-05 |  | L022 | CI | PKG-05 |  | Construction Indirects - field supervision site overhead QA/QC (factor-based) | 1 | LS | 144720 | 144720 | CAD | PARAMETRIC | D-006 | LOW | 18% of CD base ($803
PKG-05::L023 | PKG-05 |  | L023 | PM | PKG-05 |  | EPCM / Project Management - PKG-05 allocation (factor-based) | 1 | LS | 111871 | 111871 | CAD | PARAMETRIC | D-006 | MED | 6% of (CD+CI+MAT) = 6% x ($803.8k + $209.7k + $850.8k) = $111.9k
PKG-05::L024 | PKG-05 |  | L024 | P | PKG-05 |  | Procurement Services - vendor coordination expediting (factor-based) | 1 | LS | 17016 | 17016 | CAD | PARAMETRIC | D-006 | MED | 2% of MAT = 2% x $850
PKG-06::L001 | PKG-06 | DEL-06.01 | L001 | E | PKG-06 | DEL-06.01 | Structural Steel Design Drawing Set - CAD drafting (platform GAs stair drawings gangway drawings pipe rack drawings handrail details) | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-001 | LOW | ~12-15 sheets at $3.5k/sheet average
PKG-06::L002 | PKG-06 | DEL-06.02 | L002 | E | PKG-06 | DEL-06.02 | Structural Steel Technical Specification - spec writing (structural steel handrails grating) | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-002 | LOW | ~80 hours at $150/hr for 3 specification sections
PKG-06::L003 | PKG-06 | DEL-06.03 | L003 | E | PKG-06 | DEL-06.03 | Structural Steel Design Calculations - platform pipe rack connection stair gangway analysis | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-003 | LOW | ~100 hours at $175/hr structural engineering
PKG-06::L004 | PKG-06 | DEL-06.04 | L004 | E | PKG-06 | DEL-06.04 | Structural Steel Data Sheet Package - gangway and grating data sheets compilation | 1 | LS | 6000 | 6000 | CAD | ALLOWANCE | A-004 | LOW | ~40 hours at $140/hr
PKG-06::L005 | PKG-06 | DEL-06.05 | L005 | E | PKG-06 | DEL-06.05 | Structural Steel QA/QC Records - mill certs weld inspection records galvanizing certs compilation | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-005 | LOW | ~60 hours at $140/hr documentation
PKG-06::L006 | PKG-06 |  | L006 | MAT | PKG-06 |  | Structural Steel Material Supply - fabricated and galvanized (platforms stairs gangways pipe racks handrails supports) | 150 | tonne | 6000 | 900000 | CAD | ALLOWANCE | A-006 | LOW | 150 tonnes (D-012) at $6k/tonne fabricated/galvanized
PKG-06::L007 | PKG-06 |  | L007 | CD | PKG-06 |  | Structural Steel Erection Labor - field installation welding connections (150 tonnes) | 3750 | hrs | 95 | 356000 | CAD | ALLOWANCE | A-007 | LOW | 25 hrs/tonne × 150 tonnes at $95/hr composite crew rate
PKG-06::L008 | PKG-06 |  | L008 | CD | PKG-06 |  | Crane & Equipment for Steel Erection - mobile crane rigging welding machines access equipment | 1 | LS | 120000 | 120000 | CAD | ALLOWANCE | A-008 | LOW | Crane rental weeks + welding/rigging equipment
PKG-06::L009 | PKG-06 |  | L009 | MAT | PKG-06 |  | Handrail Supply - galvanized steel handrail system (3-rail with posts) material | 400 | m | 150 | 60000 | CAD | ALLOWANCE | A-009 | LOW | 400 m (D-013) at $150/m material
PKG-06::L010 | PKG-06 |  | L010 | CD | PKG-06 |  | Handrail Installation Labor - handrail installation and anchoring | 400 | m | 70 | 28000 | CAD | ALLOWANCE | A-009 | LOW | 400 m at $70/m installation labor
PKG-06::L011 | PKG-06 |  | L011 | MAT | PKG-06 |  | Grating Supply - galvanized steel grating medium-duty industrial material | 800 | m2 | 120 | 96000 | CAD | ALLOWANCE | A-010 | LOW | 800 m² (D-013) at $120/m²
PKG-06::L012 | PKG-06 |  | L012 | CD | PKG-06 |  | Grating Installation Labor - grating cutting fitting and securing | 800 | m2 | 60 | 48000 | CAD | ALLOWANCE | A-010 | LOW | 800 m² at $60/m² installation
PKG-06::L013 | PKG-06 |  | L013 | MAT | PKG-06 |  | Stairs and Gangways - pre-fabricated galvanized stairs and gangways (8 stairs + 4 gangways) | 12 | EA | 15000 | 180000 | CAD | ALLOWANCE | A-011 | LOW | 12 items at $15k/item avg (fabricated galvanized installed)
PKG-06::L014 | PKG-06 |  | L014 | MAT | PKG-06 |  | Pipe Supports and Racks - structural supports along piping runs | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-012 | LOW | Allowance for pipe support steelwork
PKG-06::L015 | PKG-06 |  | L015 | CD | PKG-06 |  | Field Touch-Up Painting - post-erection coating repairs and touch-up | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-013 | LOW | Galvanizing damage repair weld zones
PKG-06::L016 | PKG-06 |  | L016 | CD | PKG-06 |  | Site Access & Temporary Works - laydown material handling offloading (PKG-06 allocation) | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-014 | LOW | Site prep and material handling for steel erection
PKG-06::L017 | PKG-06 |  | L017 | CD | PKG-06 |  | Weld Inspection & NDT - visual UT MT inspection (200 hrs CWB inspector) | 200 | hrs | 110 | 22000 | 22000 | CAD | ALLOWANCE | A-015 | LOW
PKG-06::L018 | PKG-06 |  | L018 | CI | PKG-06 |  | Construction Indirects - field supervision site overhead QA/QC HSE (factor-based) | 1 | LS | 115000 | 115000 | CAD | PARAMETRIC | D-009 | LOW | 18% of CD base ($639k × 0.18)
PKG-06::L019 | PKG-06 |  | L019 | PM | PKG-06 |  | EPCM / Project Management - PKG-06 allocation (factor-based) | 1 | LS | 120000 | 120000 | CAD | PARAMETRIC | D-009 | MED | 6% of (CD+CI+MAT) base
PKG-06::L020 | PKG-06 |  | L020 | P | PKG-06 |  | Procurement Services - vendor coordination expediting inspection (factor-based) | 1 | LS | 27000 | 27000 | CAD | PARAMETRIC | D-009 | MED | 2% of MAT ($1.366M × 0.02)
PKG-06::L021 | PKG-06 |  | L021 | COM | PKG-06 |  | Commissioning & Testing - load testing final inspections punch list verification | 1 | LS | 60000 | 60000 | CAD | PARAMETRIC | D-009 | LOW | 3% of (CD+CI+MAT) base
PKG-07::L001 | PKG-07 | DEL-07.01 | L001 | E | PKG-07 | DEL-07.01 | Rail Works Design Drawing Set - CAD drafting (track layouts rail profiles ballast sections end stop details) | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-001 | LOW | ~6-8 sheets at $3k/sheet average
PKG-07::L002 | PKG-07 | DEL-07.02 | L002 | E | PKG-07 | DEL-07.02 | Rail Works Technical Specification - specification writing (rail ballast track construction specs) | 1 | LS | 7000 | 7000 | CAD | ALLOWANCE | A-002 | LOW | ~45 hours at $150/hr
PKG-07::L003 | PKG-07 | DEL-07.03 | L003 | E | PKG-07 | DEL-07.03 | Rail Works Design Calculations - track geometry and ballast depth calculations | 1 | LS | 10000 | 10000 | CAD | ALLOWANCE | A-003 | LOW | ~55 hours at $175/hr
PKG-07::L004 | PKG-07 | DEL-07.04 | L004 | E | PKG-07 | DEL-07.04 | Rail Works ITR Compilation - installation and test record documentation | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-004 | LOW | ~80 hours at $100/hr
PKG-07::L005 | PKG-07 |  | L005 | MAT | PKG-07 |  | Rail Supply - New Tracks 6 & 7 (1000 linear meters heavy rail 115 RE or equiv) | 1 | LS | 350000 | 350000 | CAD | ALLOWANCE | A-005 | LOW | 1000m at $350/m includes rail delivery
PKG-07::L006 | PKG-07 |  | L006 | MAT | PKG-07 |  | Rail Supply - Track 5 Restoration (300 linear meters) | 1 | LS | 105000 | 105000 | CAD | ALLOWANCE | A-007 | LOW | 300m at $350/m
PKG-07::L007 | PKG-07 |  | L007 | MAT | PKG-07 |  | Track Ties/Sleepers - concrete or timber ties (1300m total track) | 1 | LS | 195000 | 195000 | CAD | ALLOWANCE | A-011 | LOW | 1300m at $150/m avg installed spacing
PKG-07::L008 | PKG-07 |  | L008 | MAT | PKG-07 |  | Track Fasteners & Hardware - clips spikes plates anchors | 1 | LS | 91000 | 91000 | CAD | ALLOWANCE | A-012 | LOW | ~20% of rail cost
PKG-07::L009 | PKG-07 |  | L009 | MAT | PKG-07 |  | Ballast Material Supply - crushed aggregate (1950 m³) | 1 | LS | 117000 | 117000 | CAD | ALLOWANCE | A-009 | LOW | 1950 m³ at $60/m³
PKG-07::L010 | PKG-07 |  | L010 | MAT | PKG-07 |  | End Stops - hydraulic or mechanical car stops (4 units) | 1 | LS | 40000 | 40000 | CAD | ALLOWANCE | A-013 | LOW | 4 units at $10k/unit material
PKG-07::L011 | PKG-07 |  | L011 | CD | PKG-07 |  | Track Installation - New Tracks 6 & 7 (1000m rail placement alignment fastening) | 1 | LS | 200000 | 200000 | CAD | ALLOWANCE | A-006 | LOW | 1000m at $200/m labor
PKG-07::L012 | PKG-07 |  | L012 | CD | PKG-07 |  | Track Restoration - Track 5 (300m remove relay align) | 1 | LS | 75000 | 75000 | CAD | ALLOWANCE | A-008 | LOW | 300m at $250/m (higher complexity)
PKG-07::L013 | PKG-07 |  | L013 | CD | PKG-07 |  | Ballast Placement & Compaction - spread level compact test (1950 m³) | 1 | LS | 78000 | 78000 | CAD | ALLOWANCE | A-010 | LOW | 1950 m³ at $40/m³
PKG-07::L014 | PKG-07 |  | L014 | CD | PKG-07 |  | End Stop Installation - anchor position test (4 units) | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-013 | LOW | 4 units at $5k/unit labor
PKG-07::L015 | PKG-07 |  | L015 | CD | PKG-07 |  | Track Alignment Survey - pre and post installation surveys | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-014 | LOW | Survey and verification
PKG-07::L016 | PKG-07 |  | L016 | CD | PKG-07 |  | Track Geometry Testing - alignment gauge elevation testing | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-016 | LOW | ~65 test locations
PKG-07::L017 | PKG-07 |  | L017 | CD | PKG-07 |  | Ballast Material Testing - gradation and compaction verification | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-017 | LOW | Testing during placement
PKG-07::L018 | PKG-07 |  | L018 | CD | PKG-07 |  | Rail Weld Inspection - visual and UT inspection of rail joints | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-018 | LOW | Inspection per welding plan
PKG-07::L019 | PKG-07 |  | L019 | CD | PKG-07 |  | Track Access Coordination - flagging protection during terminal operations | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-019 | LOW | Safety and coordination allowance
PKG-07::L020 | PKG-07 |  | L020 | CI | PKG-07 |  | Construction Indirects - field supervision site overhead QA/QC (factor-based) | 1 | LS | 84000 | 84000 | CAD | PARAMETRIC | D-009 | LOW | 18% of CD base ($468k × 0.18)
PKG-07::L021 | PKG-07 |  | L021 | PM | PKG-07 |  | EPCM / Project Management - PKG-07 allocation (factor-based) | 1 | LS | 87000 | 87000 | CAD | PARAMETRIC | D-009 | MED | 6% of (CD+CI+MAT) base
PKG-07::L022 | PKG-07 |  | L022 | P | PKG-07 |  | Procurement Services - vendor coordination expediting (factor-based) | 1 | LS | 18000 | 18000 | CAD | PARAMETRIC | D-009 | MED | 2% of MAT ($898k × 0.02)
PKG-07::L023 | PKG-07 |  | L023 | COM | PKG-07 |  | Track Commissioning - load testing final verification acceptance | 1 | LS | 44000 | 44000 | CAD | PARAMETRIC | D-009 | LOW | 3% of (CD+CI+MAT) base
PKG-08::L801 | PKG-08 | DEL-08.01 | L801 | E | PKG-08 | DEL-08.01 | Marine Structures Design Drawing Set - CAD drafting and production (piling layout trestle GA platform GA catwalk abutments ~15 drawings) | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-801 | LOW | Allowance for marine structures drawing production; complex marine design with multiple structures and interfaces to PKG-09 and PKG-11
PKG-08::L802 | PKG-08 | DEL-08.02 | L802 | E | PKG-08 | DEL-08.02 | Marine Structures Technical Specification - specification writing (marine piling spec and structural steel spec for marine environment) | 1 | LS | 28000 | 28000 | CAD | ALLOWANCE | A-802 | LOW | Allowance for marine specification writing; includes corrosion protection cathodic protection welding and marine-specific requirements
PKG-08::L803 | PKG-08 | DEL-08.03 | L803 | E | PKG-08 | DEL-08.03 | Marine Structures Design Calculations - structural engineering (pile capacity trestle design platform design mooring/berthing load analysis) | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-803 | LOW | Allowance for marine structural calculations; includes pile capacity (geotechnical and structural) trestle/platform framing mooring analysis - requires P.Eng. stamp
PKG-08::L804 | PKG-08 | DEL-08.04 | L804 | E | PKG-08 | DEL-08.04 | Marine Geotechnical Report - marine geotechnical investigation bathymetric survey pile capacity recommendations | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-804 | LOW | Allowance for marine geotechnical work; includes bathymetric survey marine soil investigation pile capacity analysis and design recommendations
PKG-08::L805 | PKG-08 | DEL-08.05 | L805 | E | PKG-08 | DEL-08.05 | Marine Structures Installation & Test Records - QA/QC documentation setup and record preparation (pile driving logs weld inspection NDT records) | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-805 | LOW | Allowance for QA/QC documentation templates and record closeout for marine construction
PKG-08::L806 | PKG-08 | DEL-08.06 | L806 | E | PKG-08 | DEL-08.06 | Berthing Energy Calculation Report - vessel berthing energy analysis per PIANC/BS6349 fender demand calculations | 1 | LS | 22000 | 22000 | CAD | ALLOWANCE | A-806 | LOW | Allowance for berthing energy analysis report; requires vessel characteristics environmental data and berthing scenarios
PKG-08::L807 | PKG-08 | DEL-08.07 | L807 | E | PKG-08 | DEL-08.07 | Fender System Deflection Characteristics Data Package - fender selection and data compilation vendor coordination | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-807 | LOW | Allowance for fender data package compilation; includes fender deflection curves manufacturer data and compliance certificates
PKG-08::L808 | PKG-08 | DEL-08.08 | L808 | E | PKG-08 | DEL-08.08 | Fender Supplier Design Verification Letter/Report - vendor coordination and verification documentation | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-808 | LOW | Allowance for fender supplier verification coordination; includes review of supplier calculations and stamped reports
PKG-08::L809 | PKG-08 | DEL-08.09 | L809 | E | PKG-08 | DEL-08.09 | Mooring Analysis Report - moored vessel analysis mooring line loads bollard loads per OCIMF guidelines | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-809 | LOW | Allowance for mooring analysis report; includes environmental loads on moored vessel mooring line tensions and bollard loads
PKG-08::L810 | PKG-08 | DEL-08.10 | L810 | E | PKG-08 | DEL-08.10 | Current Assessment Basis Report - marine current assessment methodology and results for structural loading | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-810 | LOW | Allowance for current assessment report; includes current velocity profiles and loads on structure
PKG-08::L811 | PKG-08 | DEL-08.11 | L811 | E | PKG-08 | DEL-08.11 | Debris Loading Design Basis Note - debris loading assumptions and design basis documentation | 1 | LS | 6000 | 6000 | CAD | ALLOWANCE | A-811 | LOW | Allowance for debris loading basis note; documents assumptions for floating debris and log impact loads
PKG-08::L812 | PKG-08 |  | L812 | MAT | PKG-08 |  | Marine Piling Supply - steel pipe piles or H-piles including corrosion protection coatings (assume 40-60 piles avg 20m length) | 1 | LS | 850000 | 850000 | CAD | ALLOWANCE | A-812 | LOW | Placeholder for marine piling supply; actual cost depends on pile type size quantity and embedment depth - requires geotechnical design
PKG-08::L813 | PKG-08 |  | L813 | MAT | PKG-08 |  | Trestle Structural Steel Supply - fabricated steel framing for access trestle (assume 150m length 3m width 150 tonnes) | 1 | LS | 675000 | 675000 | CAD | ALLOWANCE | A-813 | LOW | Placeholder for trestle structural steel; includes beams columns bracing grating handrails - marine-grade corrosion protection required
PKG-08::L814 | PKG-08 |  | L814 | MAT | PKG-08 |  | Loading Platform Structural Steel Supply - fabricated steel platform structure for marine loading arm and equipment (assume 20m x 15m 80 tonnes) | 1 | LS | 450000 | 450000 | CAD | ALLOWANCE | A-814 | LOW | Placeholder for loading platform steel; includes framing deck equipment supports - marine-grade corrosion protection required
PKG-08::L815 | PKG-08 |  | L815 | MAT | PKG-08 |  | Catwalk Structural Steel Supply - fabricated catwalk structure with handrails and safety features (assume 50m length 25 tonnes) | 1 | LS | 125000 | 125000 | CAD | ALLOWANCE | A-815 | LOW | Placeholder for catwalk steel supply; includes framing grating handrails safety features
PKG-08::L816 | PKG-08 |  | L816 | MAT | PKG-08 |  | Abutment Materials - concrete and reinforcement for landside abutments and trestle tie-in (assume 2 abutments 40m3 each) | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-816 | LOW | Placeholder for abutment construction materials; includes concrete reinforcement formwork tie-in hardware
PKG-08::L817 | PKG-08 |  | L817 | MAT | PKG-08 |  | Marine Hardware and Miscellaneous Steel - ladders platforms accessories sacrificial anodes cathodic protection system | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-817 | LOW | Placeholder for marine accessories; includes access ladders platforms safety equipment corrosion protection anodes
PKG-08::L818 | PKG-08 |  | L818 | FRT | PKG-08 |  | Freight and Marine Logistics - barge/vessel mobilization marine transport crane barge positioning staging | 1 | LS | 175000 | 175000 | CAD | ALLOWANCE | A-818 | LOW | Placeholder for marine logistics; includes barge mobilization marine transport staging areas - required for pile installation and steel erection
PKG-08::L819 | PKG-08 |  | L819 | CD | PKG-08 |  | Marine Piling Installation - pile driving marine crane/barge pile positioning driving records integrity testing (40-60 piles) | 1 | LS | 650000 | 650000 | CAD | ALLOWANCE | A-819 | LOW | Placeholder for pile installation; requires marine crane/barge pile driving equipment pile integrity testing - specialized marine contractor
PKG-08::L820 | PKG-08 |  | L820 | CD | PKG-08 |  | Trestle Steel Erection - marine steel erection including barge/crane welding bolting field inspection (150 tonnes) | 1 | LS | 425000 | 425000 | CAD | ALLOWANCE | A-820 | LOW | Placeholder for trestle erection; marine steel erection requires barge/crane access welding/bolting field QA/QC - specialized marine contractor
PKG-08::L821 | PKG-08 |  | L821 | CD | PKG-08 |  | Loading Platform Steel Erection - platform structure erection equipment support installation welding inspection (80 tonnes) | 1 | LS | 275000 | 275000 | CAD | ALLOWANCE | A-821 | LOW | Placeholder for platform erection; includes marine crane work welding/bolting alignment and field inspection
PKG-08::L822 | PKG-08 |  | L822 | CD | PKG-08 |  | Catwalk and Abutment Installation - catwalk erection abutment construction landside tie-in work (50m catwalk 2 abutments) | 1 | LS | 195000 | 195000 | CAD | ALLOWANCE | A-822 | LOW | Placeholder for catwalk and abutment work; includes catwalk installation abutment formwork/concrete/rebar tie-in connections
PKG-08::L823 | PKG-08 |  | L823 | CD | PKG-08 |  | Marine Hardware Installation - ladder installation platform accessories cathodic protection system installation commissioning | 1 | LS | 75000 | 75000 | CAD | ALLOWANCE | A-823 | LOW | Placeholder for marine accessories installation; includes ladders platforms anodes and miscellaneous marine hardware
PKG-08::L824 | PKG-08 |  | L824 | CD | PKG-08 |  | Marine Coatings and Touch-Up - field coating repairs touch-up welding corrosion protection field application | 1 | LS | 125000 | 125000 | CAD | ALLOWANCE | A-824 | LOW | Placeholder for field coating work; marine environment requires comprehensive corrosion protection system touch-up after installation
PKG-08::L825 | PKG-08 |  | L825 | CD | PKG-08 |  | NDT and Inspection Services - weld inspection (UT RT VT) pile integrity testing structural inspection third-party QA | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-825 | LOW | Placeholder for NDT and third-party inspection; marine structures require extensive weld inspection and pile integrity testing
PKG-08::L826 | PKG-08 |  | L826 | CI | PKG-08 |  | Construction Indirects - field supervision marine safety oversight QA/QC coordination marine operations coordination (factor-based) | 1 | LS | 329400 | 329400 | CAD | PARAMETRIC | D-808 | LOW | 18% of CD base ($1
PKG-08::L827 | PKG-08 |  | L827 | PM | PKG-08 |  | EPCM / Project Management - PKG-08 allocation marine engineering coordination (factor-based) | 1 | LS | 276864 | 276864 | CAD | PARAMETRIC | D-808 | MED | 6% of (CD+CI+MAT+FRT) = 6% x ($1
PKG-08::L828 | PKG-08 |  | L828 | P | PKG-08 |  | Procurement Services - marine equipment vendor coordination expediting inspection (factor-based) | 1 | LS | 49100 | 49100 | CAD | PARAMETRIC | D-808 | MED | 2% of (MAT+FRT) = 2% x ($2
PKG-08::L829 | PKG-08 |  | L829 | COM | PKG-08 |  | Marine Structures Commissioning - structural load testing proof testing as-built survey acceptance testing | 1 | LS | 133182 | 133182 | CAD | PARAMETRIC | D-808 | LOW | 3% of (CD+CI+MAT) = 3% x ($1
PKG-09::L-001 | PKG-09 | DEL-09.01 | L-001 | E | PKG-09 | DEL-09.01 | Marine Outfitting Design Drawing Set | 1 | LS | 38000 | 38000 | CAD | ALLOWANCE | A-006 | LOW | Fender arrangement drawings + bollard installation details + ladder details
PKG-09::L-002 | PKG-09 | DEL-09.02 | L-002 | E | PKG-09 | DEL-09.02 | Marine Outfitting Technical Specification | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-007 | LOW | Fender spec + bollard spec + marine hardware spec
PKG-09::L-003 | PKG-09 | DEL-09.03 | L-003 | E | PKG-09 | DEL-09.03 | Marine Outfitting Design Calculations | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-008 | LOW | Fender reaction calculations + bollard load calculations
PKG-09::L-004 | PKG-09 | DEL-09.04 | L-004 | E | PKG-09 | DEL-09.04 | Marine Outfitting Data Sheet Package | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-009 | LOW | Fender data sheets + bollard data sheets
PKG-09::L-005 | PKG-09 | DEL-09.05 | L-005 | E | PKG-09 | DEL-09.05 | Marine Outfitting Installation & Test Records | 1 | LS | 6000 | 6000 | CAD | ALLOWANCE | A-010 | LOW | Installation records + proof load test records
PKG-09::L-006 | PKG-09 |  | L-006 | MAT | PKG-09 |  | Marine Fenders - Supply (12 units) | 12 | EA | 85000 | 1020000 | CAD | ALLOWANCE | A-001 | LOW | Heavy-duty rubber fenders with chains/hardware for Panamax vessels; ~$70k-100k/unit typical
PKG-09::L-007 | PKG-09 |  | L-007 | MAT | PKG-09 |  | Mooring Bollards - Supply (8 units) | 8 | EA | 45000 | 360000 | CAD | ALLOWANCE | A-002 | LOW | 300-500 kN SWL bollards (cast or fabricated); ~$40k-50k/unit typical
PKG-09::L-008 | PKG-09 |  | L-008 | MAT | PKG-09 |  | Ship-to-Shore Ladders - Supply (4 units) | 4 | EA | 18000 | 72000 | CAD | ALLOWANCE | A-003 | LOW | Marine-grade aluminum or stainless ladders with safety cages; ~$15k-20k/unit
PKG-09::L-009 | PKG-09 |  | L-009 | MAT | PKG-09 |  | Life-Saving Equipment Package | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-004 | LOW | Life rings + buoys + rescue equipment + mounting hardware per safety codes
PKG-09::L-010 | PKG-09 |  | L-010 | MAT | PKG-09 |  | Berth 10 Repair Materials | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-005 | LOW | Replacement hardware + coatings + minor structural repairs
PKG-09::L-011 | PKG-09 |  | L-011 | CD | PKG-09 |  | Fender Installation - Marine Labor (12 units) | 12 | EA | 12000 | 144000 | CAD | ALLOWANCE | A-011 | LOW | Marine installation via barge/crane; ~100-120 hrs/unit @ $120/hr all-in
PKG-09::L-012 | PKG-09 |  | L-012 | CD | PKG-09 |  | Bollard Installation - Marine Labor (8 units) | 8 | EA | 8000 | 64000 | CAD | ALLOWANCE | A-012 | LOW | Marine installation with positioning/grouting; ~60-80 hrs/unit @ $120/hr all-in
PKG-09::L-013 | PKG-09 |  | L-013 | CD | PKG-09 |  | Ladder Installation - Marine Labor (4 units) | 4 | EA | 3500 | 14000 | CAD | ALLOWANCE | A-013 | LOW | Marine installation with mounting/welding; ~25-30 hrs/unit @ $120/hr all-in
PKG-09::L-014 | PKG-09 |  | L-014 | CD | PKG-09 |  | Life-Saving Equipment Installation | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-014 | LOW | Installation of life rings + buoys + rescue equipment
PKG-09::L-015 | PKG-09 |  | L-015 | CD | PKG-09 |  | Berth 10 Repairs - Marine Labor | 1 | LS | 40000 | 40000 | CAD | ALLOWANCE | A-015 | LOW | Repair work via barge/access; ~300-350 hrs @ $120/hr all-in
PKG-09::L-016 | PKG-09 |  | L-016 | CD | PKG-09 |  | Marine Crane/Barge Mobilization | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-016 | LOW | Crane barge mobilization + demobilization + standby for installation sequence
PKG-09::L-017 | PKG-09 |  | L-017 | CD | PKG-09 |  | Setting Out and Survey | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-017 | LOW | Marine setting-out + as-built survey for fenders/bollards/ladders
PKG-09::L-018 | PKG-09 |  | L-018 | CD | PKG-09 |  | Coating Touch-Up and Protection | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-018 | LOW | Field coating touch-up post-installation + temporary protection
PKG-09::L-019 | PKG-09 |  | L-019 | MAT | PKG-09 |  | Installation Consumables and Fasteners | 1 | LS | 22000 | 22000 | CAD | ALLOWANCE | A-019 | LOW | Grout + anchor bolts + welding consumables + sealants + misc hardware
PKG-09::L-020 | PKG-09 |  | L-020 | CI | PKG-09 |  | Construction Indirects | 1 | LS | 64000 | 64000 | CAD | PARAMETRIC | D-008 (18% factor on CD) | MED | 18% of CD base for supervision + temp facilities + HSE + QA/QC
PKG-09::L-021 | PKG-09 |  | L-021 | P | PKG-09 |  | Procurement Services | 1 | LS | 31000 | 31000 | CAD | PARAMETRIC | D-008 (2% factor on MAT) | MED | 2% of MAT for purchasing + expediting + inspection
PKG-09::L-022 | PKG-09 |  | L-022 | PM | PKG-09 |  | Project Management / EPCM | 1 | LS | 114000 | 114000 | CAD | PARAMETRIC | D-008 (6% factor) | MED | 6% of (CD + CI + MAT) for project management + EPCM
PKG-09::L-023 | PKG-09 |  | L-023 | COM | PKG-09 |  | Proof Load Testing (Bollards) | 8 | EA | 4500 | 36000 | CAD | ALLOWANCE | A-022 | LOW | Bollard proof load testing @ 1.5x SWL per codes; ~$4k-5k/test
PKG-09::L-024 | PKG-09 |  | L-024 | COM | PKG-09 |  | Fender Inspection and Testing | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-023 | LOW | Visual inspection + deflection testing + performance verification
PKG-09::L-025 | PKG-09 |  | L-025 | COM | PKG-09 |  | Final Inspection and Commissioning | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-024 | LOW | Final inspection + safety checks + handover documentation
PKG-10::L-001 | PKG-10 | DEL-10.01 | L-001 | E | PKG-10 | DEL-10.01 | Railcar Unloading Design Drawing Set | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-006 | LOW | GA + 32 arm arrangements + header layout + containment details
PKG-10::L-002 | PKG-10 | DEL-10.02 | L-002 | E | PKG-10 | DEL-10.02 | Railcar Unloading Technical Specification | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-007 | LOW | Unloading arm spec + header pipe spec + containment spec
PKG-10::L-003 | PKG-10 | DEL-10.03 | L-003 | E | PKG-10 | DEL-10.03 | Railcar Unloading Design Calculations | 1 | LS | 28000 | 28000 | CAD | ALLOWANCE | A-008 | LOW | Header sizing + throughput analysis + containment volume calcs
PKG-10::L-004 | PKG-10 | DEL-10.04 | L-004 | E | PKG-10 | DEL-10.04 | Railcar Unloading Data Sheet Package | 1 | LS | 22000 | 22000 | CAD | ALLOWANCE | A-009 | LOW | 32 arm data sheets + quick-connect sheets + pump sheets
PKG-10::L-005 | PKG-10 | DEL-10.05 | L-005 | E | PKG-10 | DEL-10.05 | Railcar Unloading Installation & Test Records | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-010 | LOW | FAT records + installation records + hydrostatic test records
PKG-10::L-006 | PKG-10 |  | L-006 | MAT | PKG-10 |  | Railcar Unloading Arms - Supply (32 units) | 32 | EA | 50000 | 1600000 | CAD | ALLOWANCE | A-001 | LOW | Articulating bottom-loading arms with swivels; ~$45k-60k/unit typical
PKG-10::L-007 | PKG-10 |  | L-007 | MAT | PKG-10 |  | Quick-Connect Couplers - Supply (32 units) | 32 | EA | 3000 | 96000 | CAD | ALLOWANCE | A-002 | LOW | Dry-break cam-lock couplers for railcar connection; ~$2.5k-3.5k/unit
PKG-10::L-008 | PKG-10 |  | L-008 | MAT | PKG-10 |  | Gravity Flow Header Piping - Supply | 400 | LM | 700 | 280000 | CAD | ALLOWANCE | A-003 | LOW | 8-12 inch carbon steel or SS pipe with fittings; ~$600-800/lm
PKG-10::L-009 | PKG-10 |  | L-009 | MAT | PKG-10 |  | Spill Containment Pans - Supply (32 units) | 32 | EA | 8000 | 256000 | CAD | ALLOWANCE | A-004 | LOW | Under-track containment pans with drains; ~$7k-9k/unit fabricated
PKG-10::L-010 | PKG-10 |  | L-010 | MAT | PKG-10 |  | Sump Pumps - Supply (8 units) | 8 | EA | 6000 | 48000 | CAD | ALLOWANCE | A-005 | LOW | Submersible or external pumps for containment drainage; ~$5k-7k/unit
PKG-10::L-011 | PKG-10 |  | L-011 | MAT | PKG-10 |  | Flow Indicators - Supply (32 units) | 32 | EA | 2500 | 80000 | CAD | ALLOWANCE | A-011 | LOW | Local flow indicators at each station; ~$2k-3k/unit
PKG-10::L-012 | PKG-10 |  | L-012 | MAT | PKG-10 |  | Atmospheric Vent Piping & Components | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-012 | LOW | 32 vent connections + routing + flame arrestors + supports
PKG-10::L-013 | PKG-10 |  | L-013 | MAT | PKG-10 |  | Isolation Valves & Fittings | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-013 | LOW | Header isolation valves + branch valves + pipe fittings + supports
PKG-10::L-014 | PKG-10 |  | L-014 | MAT | PKG-10 |  | Installation Consumables and Fasteners | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-014 | LOW | Welding consumables + anchor bolts + gaskets + sealants + misc hardware
PKG-10::L-015 | PKG-10 |  | L-015 | CD | PKG-10 |  | Unloading Arm Installation - Labor (32 units) | 32 | EA | 8000 | 256000 | CAD | ALLOWANCE | A-015 | LOW | Arm mounting + alignment + connection + testing; ~70-80 hrs/unit @ $110/hr
PKG-10::L-016 | PKG-10 |  | L-016 | CD | PKG-10 |  | Header Piping Installation - Labor | 400 | LM | 450 | 180000 | CAD | ALLOWANCE | A-016 | LOW | Pipe welding + support installation + testing; ~4-5 hrs/lm @ $110/hr
PKG-10::L-017 | PKG-10 |  | L-017 | CD | PKG-10 |  | Containment Pan Installation - Labor | 32 | EA | 4500 | 144000 | CAD | ALLOWANCE | A-017 | LOW | Pan placement + leveling + seal welding + drain connections; ~40 hrs/unit
PKG-10::L-018 | PKG-10 |  | L-018 | CD | PKG-10 |  | Sump Pump Installation - Labor | 8 | EA | 3000 | 24000 | CAD | ALLOWANCE | A-018 | LOW | Pump installation + piping connections + electrical rough-in; ~25 hrs/unit
PKG-10::L-019 | PKG-10 |  | L-019 | CD | PKG-10 |  | Flow Indicator Installation - Labor | 32 | EA | 1000 | 32000 | CAD | ALLOWANCE | A-019 | LOW | Indicator mounting + connections + calibration; ~8-10 hrs/unit @ $110/hr
PKG-10::L-020 | PKG-10 |  | L-020 | CD | PKG-10 |  | Venting System Installation - Labor | 1 | LS | 28000 | 28000 | CAD | ALLOWANCE | A-020 | LOW | 32 vent connections + piping + flame arrestor installation
PKG-10::L-021 | PKG-10 |  | L-021 | CD | PKG-10 |  | Setting Out and Survey | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-021 | LOW | Station layout + as-built survey for 32 stations + header + containment
PKG-10::L-022 | PKG-10 |  | L-022 | CD | PKG-10 |  | Hydrostatic Testing and Flushing | 1 | LS | 22000 | 22000 | CAD | ALLOWANCE | A-022 | LOW | Header hydrostatic test + flushing + drying + system prep
PKG-10::L-023 | PKG-10 |  | L-023 | CD | PKG-10 |  | Coating Touch-Up and Protection | 1 | LS | 13000 | 13000 | CAD | ALLOWANCE | A-023 | LOW | Field coating touch-up post-installation + temporary protection
PKG-10::L-024 | PKG-10 |  | L-024 | CI | PKG-10 |  | Construction Indirects | 1 | LS | 129000 | 129000 | CAD | PARAMETRIC | D-008 (18% factor on CD) | MED | 18% of CD base for supervision + temp facilities + HSE + QA/QC
PKG-10::L-025 | PKG-10 |  | L-025 | P | PKG-10 |  | Procurement Services | 1 | LS | 51000 | 51000 | CAD | PARAMETRIC | D-008 (2% factor on MAT) | MED | 2% of MAT for purchasing + expediting + inspection
PKG-10::L-026 | PKG-10 |  | L-026 | PM | PKG-10 |  | Project Management / EPCM | 1 | LS | 204000 | 204000 | CAD | PARAMETRIC | D-008 (6% factor) | MED | 6% of (CD + CI + MAT) for project management + EPCM
PKG-10::L-027 | PKG-10 |  | L-027 | COM | PKG-10 |  | Unloading Arm FAT and Commissioning (32 units) | 32 | EA | 1800 | 58000 | CAD | ALLOWANCE | A-024 | LOW | Factory acceptance testing + functional testing; ~15 hrs/unit @ $120/hr
PKG-10::L-028 | PKG-10 |  | L-028 | COM | PKG-10 |  | System Integration Testing | 1 | LS | 28000 | 28000 | CAD | ALLOWANCE | A-025 | LOW | Integrated system testing + flow verification + control logic testing
PKG-10::L-029 | PKG-10 |  | L-029 | COM | PKG-10 |  | Performance Testing and Verification | 1 | LS | 22000 | 22000 | CAD | ALLOWANCE | A-026 | LOW | Throughput verification + containment testing + acceptance testing
PKG-10::L-030 | PKG-10 |  | L-030 | COM | PKG-10 |  | Final Inspection and Documentation | 1 | LS | 14000 | 14000 | CAD | ALLOWANCE | A-027 | LOW | Final inspection + punch list + commissioning records + handover
PKG-11::L001 | PKG-11 | DEL-11.01 | L001 | E | PKG-11 | DEL-11.01 | Marine Loading Design Drawing Set - CAD drafting (loading arm GA double-walled pipe arrangement leak detection layout operator shelter) | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-007 | LOW | ~12-15 sheets at $3k/sheet average for process/mechanical
PKG-11::L002 | PKG-11 | DEL-11.02 | L002 | E | PKG-11 | DEL-11.02 | Marine Loading Technical Specification - specification writing (loading arm double-walled pipe leak detection nitrogen operator shelter) | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-008 | LOW | ~100-120 hours at $200/hr for process specialist
PKG-11::L003 | PKG-11 | DEL-11.03 | L003 | E | PKG-11 | DEL-11.03 | Marine Loading Design Calculations - envelope calcs drainage calcs nitrogen purge calcs | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-009 | LOW | ~80 hours at $250/hr for process engineer
PKG-11::L004 | PKG-11 | DEL-11.04 | L004 | E | PKG-11 | DEL-11.04 | Marine Loading Data Sheet Package - equipment datasheets (loading arm leak detection sump pump) | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-010 | LOW | ~40 hours at $200/hr
PKG-11::L005 | PKG-11 | DEL-11.05 | L005 | E | PKG-11 | DEL-11.05 | Marine Loading Installation & Test Records - test procedures test record compilation | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-011 | LOW | ~60 hours at $250/hr QA/QC
PKG-11::L006 | PKG-11 | DEL-11.06 | L006 | E | PKG-11 | DEL-11.06 | Marine Loading Arm OEM Qualification Package - vendor qualification review compliance assessment | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-012 | LOW | ~60 hours at $200/hr
PKG-11::L007 | PKG-11 |  | L007 | MAT | PKG-11 |  | Marine Loading Arm - powered articulated boom with ERC hydraulics controls (OCIMF compliant) | 1 | LS | 950000 | 950000 | CAD | ALLOWANCE | A-001 | LOW | Typical 12-16 inch arm with ERC for vegetable oil service
PKG-11::L008 | PKG-11 |  | L008 | MAT | PKG-11 |  | Double-Walled Export Pipe Supply - carbon steel inner/outer 12-inch nominal (~150 lm) | 1 | LS | 225000 | 225000 | CAD | ALLOWANCE | A-002 | LOW | ~$1500/lm for double-walled construction with leak detection taps
PKG-11::L009 | PKG-11 |  | L009 | MAT | PKG-11 |  | Leak Detection System - annulus monitoring drip tray sensors sump level switches control panel | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-003 | LOW | Complete system with 3-zone coverage
PKG-11::L010 | PKG-11 |  | L010 | MAT | PKG-11 |  | Sump Pump Package - submersible pump stainless steel motor starter | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-004 | LOW | 5 HP typical for containment sump
PKG-11::L011 | PKG-11 |  | L011 | MAT | PKG-11 |  | Operator Shelter - prefabricated weather shelter with HVAC lighting electrical panels | 1 | LS | 75000 | 75000 | CAD | ALLOWANCE | A-005 | LOW | Typical 3m x 4m insulated shelter
PKG-11::L012 | PKG-11 |  | L012 | MAT | PKG-11 |  | Nitrogen Connection Package - valves piping pressure regulation to Employer skid | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-006 | LOW | Connection components only (skid by Employer per DEC-07)
PKG-11::L013 | PKG-11 |  | L013 | MAT | PKG-11 |  | Pipe Supports and Expansion - double-walled pipe supports expansion loops/joints | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-013 | LOW | ~$300/lm for support steelwork
PKG-11::L014 | PKG-11 |  | L014 | MAT | PKG-11 |  | Electrical and Instrumentation Materials - cables trays junction boxes terminations for PKG-11 scope | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-014 | LOW | E&I materials for loading arm and leak detection
PKG-11::L015 | PKG-11 |  | L015 | CD | PKG-11 |  | Marine Loading Arm Installation - rigging setting alignment grouting hydraulic connection | 1 | LS | 120000 | 120000 | CAD | ALLOWANCE | A-001 | LOW | Heavy lift marine installation; crane barge may be required
PKG-11::L016 | PKG-11 |  | L016 | CD | PKG-11 |  | Double-Walled Pipe Installation - welding testing support installation (~150 lm) | 1 | LS | 180000 | 180000 | CAD | ALLOWANCE | A-002 | LOW | ~$1200/lm for double-wall fabrication and installation
PKG-11::L017 | PKG-11 |  | L017 | CD | PKG-11 |  | Leak Detection System Installation - sensor mounting wiring testing calibration | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-003 | LOW | 3-zone system with ESD integration
PKG-11::L018 | PKG-11 |  | L018 | CD | PKG-11 |  | Sump Construction - concrete sump liner pumping piping | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-015 | LOW | Containment sump with liner
PKG-11::L019 | PKG-11 |  | L019 | CD | PKG-11 |  | Operator Shelter Installation - foundation installation services connection | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-005 | LOW | Prefab shelter installation
PKG-11::L020 | PKG-11 |  | L020 | CD | PKG-11 |  | Nitrogen System Installation - piping valves connection to Employer skid | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-006 | LOW | Connection scope only
PKG-11::L021 | PKG-11 |  | L021 | CD | PKG-11 |  | Electrical Installation - power to loading arm shelter sump pump | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-014 | LOW | Cable pulling termination testing
PKG-11::L022 | PKG-11 |  | L022 | CD | PKG-11 |  | Instrumentation Installation - leak detection loop wiring signal testing ESD integration | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-014 | LOW | I&C installation and loop testing
PKG-11::L023 | PKG-11 |  | L023 | CD | PKG-11 |  | Pipe Support Steelwork Installation - fabrication erection painting | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-013 | LOW | Support steelwork installation
PKG-11::L024 | PKG-11 |  | L024 | CD | PKG-11 |  | Testing and Inspection - pressure testing leak testing NDE welds | 1 | LS | 40000 | 40000 | CAD | ALLOWANCE | A-016 | LOW | QC testing during construction
PKG-11::L025 | PKG-11 |  | L025 | CI | PKG-11 |  | Construction Indirects - field supervision site overhead QA/QC marine coordination (factor-based) | 1 | LS | 107000 | 107000 | CAD | PARAMETRIC | D-008 | LOW | 18% of CD base ($595k × 0.18)
PKG-11::L026 | PKG-11 |  | L026 | PM | PKG-11 |  | EPCM / Project Management - PKG-11 allocation (factor-based) | 1 | LS | 119000 | 119000 | CAD | PARAMETRIC | D-008 | MED | 6% of (CD+CI+MAT) base
PKG-11::L027 | PKG-11 |  | L027 | P | PKG-11 |  | Procurement Services - vendor coordination expediting inspection (factor-based) | 1 | LS | 30000 | 30000 | CAD | PARAMETRIC | D-008 | MED | 2% of MAT ($1.485M × 0.02)
PKG-11::L028 | PKG-11 |  | L028 | COM | PKG-11 |  | Commissioning - FAT witnessing functional testing ESD verification acceptance testing | 1 | LS | 79000 | 79000 | CAD | PARAMETRIC | D-008 | LOW | 4% of (CD+CI+MAT) base (elevated for marine loading complexity)
PKG-12::L-001 | PKG-12 | DEL-12.01 | L-001 | E | PKG-12 | DEL-12.01 | Metering Design Drawing Set | 1 | LS | 28000 | 28000 | CAD | ALLOWANCE | A-011 | LOW | Metering skid GAs + flow meter installation details + proving connection details (6-12 sheets estimated)
PKG-12::L-002 | PKG-12 | DEL-12.02 | L-002 | E | PKG-12 | DEL-12.02 | Metering Technical Specification | 1 | LS | 38000 | 38000 | CAD | ALLOWANCE | A-012 | LOW | Custody transfer flow meter spec + metering system spec (30-50 pages estimated)
PKG-12::L-003 | PKG-12 | DEL-12.03 | L-003 | E | PKG-12 | DEL-12.03 | Metering Design Calculations | 1 | LS | 42000 | 42000 | CAD | ALLOWANCE | A-013 | LOW | Flow meter sizing + accuracy/uncertainty analysis + proving calculations
PKG-12::L-004 | PKG-12 | DEL-12.04 | L-004 | E | PKG-12 | DEL-12.04 | Metering Data Sheet Package | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-014 | LOW | Flow meter data sheets (x2) + transmitter data sheets (4+ sheets)
PKG-12::L-005 | PKG-12 | DEL-12.05 | L-005 | E | PKG-12 | DEL-12.05 | Metering Installation & Test Records | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-015 | LOW | Calibration certificates + proving records + FAT/SAT records
PKG-12::L-006 | PKG-12 |  | L-006 | MAT | PKG-12 |  | Custody Transfer Flow Meter - Rail Unloading (6 inch Coriolis) | 1 | EA | 180000 | 180000 | CAD | ALLOWANCE | A-016 | LOW | 6 inch Coriolis mass flowmeter with integral density; custody transfer accuracy; HART/Modbus; Measurement Canada approval
PKG-12::L-007 | PKG-12 |  | L-007 | MAT | PKG-12 |  | Custody Transfer Flow Meter - Marine Loading (10 inch Coriolis) | 1 | EA | 230000 | 230000 | CAD | ALLOWANCE | A-017 | LOW | 10 inch Coriolis mass flowmeter with integral density; custody transfer accuracy; HART/Modbus; range $200k-250k
PKG-12::L-008 | PKG-12 |  | L-008 | MAT | PKG-12 |  | Temperature Transmitters (RTD Pt100) | 4 | EA | 6000 | 24000 | CAD | ALLOWANCE | A-018 | MED | RTD Pt100 Class A with 4-20mA + HART; ±0.1°C accuracy for custody transfer compensation
PKG-12::L-009 | PKG-12 |  | L-009 | MAT | PKG-12 |  | Pressure Transmitters | 2 | EA | 5000 | 10000 | CAD | ALLOWANCE | A-019 | MED | Process pressure transmitters 0-10 bar; ±0.1% accuracy; 4-20mA + HART
PKG-12::L-010 | PKG-12 |  | L-010 | MAT | PKG-12 |  | Portable Prover System | 1 | LS | 120000 | 120000 | CAD | ALLOWANCE | A-020 | LOW | Portable prover with traceability and Measurement Canada certification; suitable for 6 inch and 10 inch meters
PKG-12::L-011 | PKG-12 |  | L-011 | MAT | PKG-12 |  | Metering Skid Structural Steel | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-021 | LOW | Structural steel for metering skids (rail and marine) with access platforms; 8-12 tonnes estimated; coordinate with PKG-06
PKG-12::L-012 | PKG-12 |  | L-012 | MAT | PKG-12 |  | Meter Run Piping (Stainless Steel) | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-022 | MED | SS316L piping for meter runs with straight-run sections (10D upstream 5D downstream typical); includes flanges and supports
PKG-12::L-013 | PKG-12 |  | L-013 | MAT | PKG-12 |  | Metering System Installation Consumables | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-023 | MED | Gaskets + fasteners + welding materials + sealants + calibration fluids
PKG-12::L-014 | PKG-12 |  | L-014 | MAT | PKG-12 |  | Flow Computers / Totalizers | 2 | EA | 18000 | 36000 | CAD | ALLOWANCE | A-031 | LOW | Flow computers for custody transfer totalizing (1 for rail 1 for marine); or integrated in control system (PKG-19); TBD
PKG-12::L-015 | PKG-12 |  | L-015 | MAT | PKG-12 |  | Junction Boxes and Marshalling | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-032 | MED | Junction boxes + instrument marshalling panels for metering system; coordinate with PKG-20
PKG-12::L-016 | PKG-12 |  | L-016 | CD | PKG-12 |  | Metering System Installation Labor | 2400 | MH | 120 | 288000 | CAD | ALLOWANCE | A-024 | LOW | Meter installation + piping + electrical/instrument connections; 2000-2800 hrs estimated at $120/hr all-in
PKG-12::L-017 | PKG-12 |  | L-017 | CD | PKG-12 |  | Survey and Setting Out | 40 | MH | 120 | 5000 | CAD | ALLOWANCE | A-025 | MED | Survey and setting out for metering skid installation
PKG-12::L-018 | PKG-12 |  | L-018 | CD | PKG-12 |  | Specialist Installation Equipment | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-026 | MED | Crane/hoist + alignment tools + torque tools + welding equipment for precision meter installation
PKG-12::L-019 | PKG-12 |  | L-019 | CI | PKG-12 |  | Construction Indirects | 1 | LS | 56000 | 56000 | CAD | PARAMETRIC | D-007 (18% factor on CD) | MED | 18% of CD base for supervision + temp facilities + HSE + QA/QC
PKG-12::L-020 | PKG-12 |  | L-020 | P | PKG-12 |  | Procurement Services | 1 | LS | 13000 | 13000 | CAD | PARAMETRIC | D-007 (2% factor on MAT) | MED | 2% of MAT for purchasing + expediting + inspection of custody transfer equipment
PKG-12::L-021 | PKG-12 |  | L-021 | PM | PKG-12 |  | Project Management / EPCM | 1 | LS | 71000 | 71000 | CAD | PARAMETRIC | D-007 (6% factor) | MED | 6% of (CD + CI + MAT) for project management + EPCM
PKG-12::L-022 | PKG-12 |  | L-022 | COM | PKG-12 |  | Factory Acceptance Test (FAT) - Flow Meters | 1 | LS | 32000 | 32000 | CAD | ALLOWANCE | A-027 | LOW | FAT for 2 custody transfer flow meters at vendor facility; includes witness travel
PKG-12::L-023 | PKG-12 |  | L-023 | COM | PKG-12 |  | Site Acceptance Test (SAT) - Metering System | 1 | LS | 28000 | 28000 | CAD | ALLOWANCE | A-028 | LOW | Functional testing of installed metering system (2 services); integration testing with control system
PKG-12::L-024 | PKG-12 |  | L-024 | COM | PKG-12 |  | Initial Proving (Commissioning) | 1 | LS | 48000 | 48000 | CAD | ALLOWANCE | A-029 | LOW | Initial proving for 2 meters to establish baseline meter factors; proving specialist + equipment mobilization
PKG-12::L-025 | PKG-12 |  | L-025 | COM | PKG-12 |  | Calibration Verification and Record Compilation | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-030 | MED | Final calibration verification + QA record package compilation per DEL-12.05
PKG-13::L001 | PKG-13 | DEL-13.01 | L001 | E | PKG-13 | DEL-13.01 | Storage Tank Design Drawing Set - CAD drafting (3 tank GAs foundations nozzle schedules roof details agitator drawings) | 1 | LS | 180000 | 180000 | CAD | ALLOWANCE | A-011 | LOW | ~60 sheets at $3k/sheet average for mechanical
PKG-13::L002 | PKG-13 | DEL-13.02 | L002 | E | PKG-13 | DEL-13.02 | Storage Tank Technical Specification - API 650 specification agitator specification appurtenance specification | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-012 | LOW | ~400 hours at $210/hr for mechanical/process specialist
PKG-13::L003 | PKG-13 | DEL-13.03 | L003 | E | PKG-13 | DEL-13.03 | Storage Tank Design Calculations - API 650 tank design (3 sets) foundation calculations seismic calculations | 1 | LS | 150000 | 150000 | CAD | ALLOWANCE | A-013 | LOW | ~600 hours at $250/hr for structural/mechanical engineer
PKG-13::L004 | PKG-13 | DEL-13.04 | L004 | E | PKG-13 | DEL-13.04 | Storage Tank Data Sheet Package - tank data sheets (3) agitator data sheets (3) overflow protection data sheets | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-014 | LOW | ~180 hours at $250/hr for equipment engineer
PKG-13::L005 | PKG-13 | DEL-13.05 | L005 | E | PKG-13 | DEL-13.05 | Storage Tank Installation & Test Records - test procedures hydrostatic test plans QC record compilation | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-015 | LOW | ~220 hours at $250/hr QA/QC engineer
PKG-13::L006 | PKG-13 | DEL-13.06 | L006 | E | PKG-13 | DEL-13.06 | Storage Tank Fabrication Quality Documentation Package - ITP WPS PQR review MTR compilation weld map prep | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-016 | LOW | ~260 hours at $250/hr QA specialist
PKG-13::L007 | PKG-13 |  | L007 | MAT | PKG-13 |  | API 650 Storage Tank No. 1 - supply (shell bottom roof structure appurtenances) ~420 tonnes steel 16300 m3 | 1 | LS | 3200000 | 3200000 | CAD | ALLOWANCE | A-001 | LOW | Typical mid-range API 650 tank supply ~$7600/tonne fabricated
PKG-13::L008 | PKG-13 |  | L008 | MAT | PKG-13 |  | API 650 Storage Tank No. 2 - supply (shell bottom roof structure appurtenances) ~420 tonnes steel 16300 m3 | 1 | LS | 3200000 | 3200000 | CAD | ALLOWANCE | A-001 | LOW | Typical mid-range API 650 tank supply ~$7600/tonne fabricated
PKG-13::L009 | PKG-13 |  | L009 | MAT | PKG-13 |  | API 650 Storage Tank No. 3 - supply (shell bottom roof structure appurtenances) ~420 tonnes steel 16300 m3 | 1 | LS | 3200000 | 3200000 | CAD | ALLOWANCE | A-001 | LOW | Typical mid-range API 650 tank supply ~$7600/tonne fabricated
PKG-13::L010 | PKG-13 |  | L010 | MAT | PKG-13 |  | Agitator No. 1 - side-entry agitator 75 HP motor VFD seal assembly mounting | 1 | LS | 125000 | 125000 | CAD | ALLOWANCE | A-006 | LOW | Typical side-entry agitator for large oil storage
PKG-13::L011 | PKG-13 |  | L011 | MAT | PKG-13 |  | Agitator No. 2 - side-entry agitator 75 HP motor VFD seal assembly mounting | 1 | LS | 125000 | 125000 | CAD | ALLOWANCE | A-006 | LOW | Typical side-entry agitator for large oil storage
PKG-13::L012 | PKG-13 |  | L012 | MAT | PKG-13 |  | Agitator No. 3 - side-entry agitator 75 HP motor VFD seal assembly mounting | 1 | LS | 125000 | 125000 | CAD | ALLOWANCE | A-006 | LOW | Typical side-entry agitator for large oil storage
PKG-13::L013 | PKG-13 |  | L013 | MAT | PKG-13 |  | Overflow Protection System - high-level switches alarms piping for 3 tanks | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-017 | LOW | Level instrumentation and overflow piping for 3 tanks
PKG-13::L014 | PKG-13 |  | L014 | MAT | PKG-13 |  | Water Draw-off System - drain valves piping sampling for 3 tanks | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-018 | LOW | Water draw-off system typical for edible oil tanks
PKG-13::L015 | PKG-13 |  | L015 | MAT | PKG-13 |  | Internal Coating System - food-grade epoxy lining (~11000 m2 total 3 tanks) | 1 | LS | 550000 | 550000 | CAD | ALLOWANCE | A-009 | LOW | ~$50/m2 for food-grade coating supply and application
PKG-13::L016 | PKG-13 |  | L016 | MAT | PKG-13 |  | External Coating System - primer and topcoat (~9000 m2 total 3 tanks) | 1 | LS | 180000 | 180000 | CAD | ALLOWANCE | A-010 | LOW | ~$20/m2 for external coating supply and application
PKG-13::L017 | PKG-13 |  | L017 | MAT | PKG-13 |  | Tank Appurtenances - vents relief valves gauging hatches sampling nozzles for 3 tanks | 1 | LS | 120000 | 120000 | CAD | ALLOWANCE | A-007 | LOW | Typical appurtenance package for API 650 tanks
PKG-13::L018 | PKG-13 |  | L018 | MAT | PKG-13 |  | Access Equipment - ladders platforms handrails gauger platforms for 3 tanks | 1 | LS | 180000 | 180000 | CAD | ALLOWANCE | A-019 | LOW | Access equipment for 3 large tanks
PKG-13::L019 | PKG-13 |  | L019 | MAT | PKG-13 |  | Phase 2 Connection Provisions - blind flanges stubs reinforcement for future expansion | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-020 | LOW | Phase 2 provisions per OBJ-8
PKG-13::L020 | PKG-13 |  | L020 | CD | PKG-13 |  | Tank No. 1 Erection - field assembly welding rigging shell courses roof bottom (~420 tonnes) | 1 | LS | 850000 | 850000 | CAD | ALLOWANCE | A-001 | LOW | Typical tank erection ~$2000/tonne installed
PKG-13::L021 | PKG-13 |  | L021 | CD | PKG-13 |  | Tank No. 2 Erection - field assembly welding rigging shell courses roof bottom (~420 tonnes) | 1 | LS | 850000 | 850000 | CAD | ALLOWANCE | A-001 | LOW | Typical tank erection ~$2000/tonne installed
PKG-13::L022 | PKG-13 |  | L022 | CD | PKG-13 |  | Tank No. 3 Erection - field assembly welding rigging shell courses roof bottom (~420 tonnes) | 1 | LS | 850000 | 850000 | CAD | ALLOWANCE | A-001 | LOW | Typical tank erection ~$2000/tonne installed
PKG-13::L023 | PKG-13 |  | L023 | CD | PKG-13 |  | Tank No. 1 Hydrostatic Test - fill test hold drain including water supply and disposal | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-021 | LOW | Hydrostatic test for ~16000 m3 tank
PKG-13::L024 | PKG-13 |  | L024 | CD | PKG-13 |  | Tank No. 2 Hydrostatic Test - fill test hold drain including water supply and disposal | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-021 | LOW | Hydrostatic test for ~16000 m3 tank
PKG-13::L025 | PKG-13 |  | L025 | CD | PKG-13 |  | Tank No. 3 Hydrostatic Test - fill test hold drain including water supply and disposal | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-021 | LOW | Hydrostatic test for ~16000 m3 tank
PKG-13::L026 | PKG-13 |  | L026 | CD | PKG-13 |  | Agitator Installation (3 units) - rigging setting alignment coupling electrical connection | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-006 | LOW | Installation of 3 side-entry agitators
PKG-13::L027 | PKG-13 |  | L027 | CD | PKG-13 |  | NDE and Inspection - radiography UT MT PT weld inspection (3 tanks) | 1 | LS | 280000 | 280000 | CAD | ALLOWANCE | A-022 | LOW | NDE for API 650 tank welds ~$67k per tank plus mobilization
PKG-13::L028 | PKG-13 |  | L028 | CD | PKG-13 |  | Appurtenance Installation - nozzles manholes vents relief devices gauging for 3 tanks | 1 | LS | 120000 | 120000 | CAD | ALLOWANCE | A-007 | LOW | Installation of tank appurtenances
PKG-13::L029 | PKG-13 |  | L029 | CD | PKG-13 |  | Access Equipment Installation - ladders platforms handrails gauger platforms for 3 tanks | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-019 | LOW | Installation of access equipment
PKG-13::L030 | PKG-13 |  | L030 | CD | PKG-13 |  | Overflow and Water Draw-off Installation - piping valves instrumentation connections | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-018 | LOW | Installation of overflow and drain systems
PKG-13::L031 | PKG-13 |  | L031 | CD | PKG-13 |  | Electrical Installation - power to agitators area lighting junction boxes | 1 | LS | 145000 | 145000 | CAD | ALLOWANCE | A-023 | LOW | Electrical installation for 3 agitator motors
PKG-13::L032 | PKG-13 |  | L032 | CD | PKG-13 |  | Instrumentation Installation - level temperature gauging calibration loop testing | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-024 | LOW | I&C installation for 3 tanks
PKG-13::L033 | PKG-13 |  | L033 | CD | PKG-13 |  | Crane and Heavy Equipment - crawler crane rental for tank erection (200+ ton class) | 1 | LS | 420000 | 420000 | CAD | ALLOWANCE | A-025 | LOW | Large crane mobilization and rental for 3 tank erections
PKG-13::L034 | PKG-13 |  | L034 | CI | PKG-13 |  | Construction Indirects - field supervision site overhead QA/QC scaffolding temporary works (factor-based) | 1 | LS | 918000 | 918000 | CAD | PARAMETRIC | D-010 | LOW | 18% of CD base ($5.10M × 0.18)
PKG-13::L035 | PKG-13 |  | L035 | PM | PKG-13 |  | EPCM / Project Management - PKG-13 allocation (factor-based) | 1 | LS | 1020000 | 1020000 | CAD | PARAMETRIC | D-010 | MED | 6% of (CD+CI+MAT) base
PKG-13::L036 | PKG-13 |  | L036 | P | PKG-13 |  | Procurement Services - tank vendor qualification expediting shop inspection (factor-based) | 1 | LS | 237000 | 237000 | CAD | PARAMETRIC | D-010 | MED | 2% of MAT ($11.85M × 0.02)
PKG-13::L037 | PKG-13 |  | L037 | COM | PKG-13 |  | Commissioning - agitator FAT tank cleaning drying acceptance testing pre-operational checks | 1 | LS | 535000 | 535000 | CAD | PARAMETRIC | D-010 | LOW | 3% of (CD+CI+MAT) base
PKG-14::L001 | PKG-14 | DEL-14.01 | L001 | E | PKG-14 | DEL-14.01 | Process Piping Design Drawing Set - P&IDs piping GAs isometrics pipe support drawings Phase 2 connections | 1 | LS | 185000 | 185000 | CAD | ALLOWANCE | A-009 | LOW | ~50-60 sheets at $3k/sheet for complex piping package with multiple systems
PKG-14::L002 | PKG-14 | DEL-14.02 | L002 | E | PKG-14 | DEL-14.02 | Process Piping Technical Specification - piping material spec pipe support spec insulation spec | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-010 | LOW | ~200 hours at $225/hr for mechanical/piping specialist
PKG-14::L003 | PKG-14 | DEL-14.03 | L003 | E | PKG-14 | DEL-14.03 | Process Piping Design Calculations - pipe sizing stress analysis flexibility analysis | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-011 | LOW | ~340 hours at $250/hr for pipe stress engineer; Caesar II or similar modeling
PKG-14::L004 | PKG-14 | DEL-14.04 | L004 | E | PKG-14 | DEL-14.04 | Process Piping Data Sheet Package - line list piping material data sheets | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-012 | LOW | ~100 hours at $250/hr; 50+ lines expected
PKG-14::L005 | PKG-14 | DEL-14.05 | L005 | E | PKG-14 | DEL-14.05 | Process Piping Installation & Test Records - material certs weld records hydro test records | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-013 | LOW | ~140 hours at $250/hr QA/QC for test pack compilation
PKG-14::L006 | PKG-14 | DEL-14.06 | L006 | E | PKG-14 | DEL-14.06 | Transient Analysis Study Report - Railcar Unloading Line - surge modeling mitigation recommendations | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-014 | LOW | Specialist transient analysis; ~200+ hours including model development
PKG-14::L007 | PKG-14 | DEL-14.07 | L007 | E | PKG-14 | DEL-14.07 | Transient Analysis Study Report - Marine Loading Line - surge modeling mitigation recommendations | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-015 | LOW | Specialist transient analysis; ~180 hours including model development
PKG-14::L008 | PKG-14 | DEL-14.08 | L008 | E | PKG-14 | DEL-14.08 | Valve Closing Time Verification Summary - valve timing analysis compliance documentation | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-016 | LOW | ~80 hours at $250/hr linked to transient studies
PKG-14::L009 | PKG-14 |  | L009 | MAT | PKG-14 |  | Rail Unloading Header Pipe Supply - 16-20 inch carbon steel ASME B31.3 (~250 lm) | 1 | LS | 375000 | 375000 | CAD | ALLOWANCE | A-001 | LOW | ~$1500/lm for large diameter CS pipe with fittings
PKG-14::L010 | PKG-14 |  | L010 | MAT | PKG-14 |  | Header Lateral Pipe Supply - 8-10 inch carbon steel from unloading stations (~100 lm) | 1 | LS | 80000 | 80000 | CAD | ALLOWANCE | A-001 | LOW | ~$800/lm for medium diameter CS pipe with fittings
PKG-14::L011 | PKG-14 |  | L011 | MAT | PKG-14 |  | Tank Inlet Header Pipe Supply - 16-20 inch carbon steel to tank farm (~150 lm) | 1 | LS | 225000 | 225000 | CAD | ALLOWANCE | A-002 | LOW | ~$1500/lm for large diameter CS pipe with fittings
PKG-14::L012 | PKG-14 |  | L012 | MAT | PKG-14 |  | Tank Outlet Manifold Pipe Supply - 16-20 inch carbon steel from tanks (~100 lm) | 1 | LS | 150000 | 150000 | CAD | ALLOWANCE | A-002 | LOW | ~$1500/lm for large diameter CS pipe with fittings
PKG-14::L013 | PKG-14 |  | L013 | MAT | PKG-14 |  | Export Piping Supply - 12-16 inch carbon steel to PKG-11 interface (~350 lm) | 1 | LS | 420000 | 420000 | CAD | ALLOWANCE | A-003 | LOW | ~$1200/lm for export line with fittings
PKG-14::L014 | PKG-14 |  | L014 | MAT | PKG-14 |  | Recycle/Return Piping Supply - 8-12 inch carbon steel (~150 lm) | 1 | LS | 120000 | 120000 | CAD | ALLOWANCE | A-004 | LOW | ~$800/lm for recirculation piping
PKG-14::L015 | PKG-14 |  | L015 | MAT | PKG-14 |  | Nitrogen Distribution Piping Supply - 2-4 inch carbon steel (~400 lm) | 1 | LS | 120000 | 120000 | CAD | ALLOWANCE | A-005 | LOW | ~$300/lm for small bore N2 piping
PKG-14::L016 | PKG-14 |  | L016 | MAT | PKG-14 |  | Small Bore Utility Piping Supply - 1-2 inch SS/CS drains vents samples (~200 lm) | 1 | LS | 60000 | 60000 | CAD | ALLOWANCE | A-006 | LOW | ~$300/lm for small bore utility piping
PKG-14::L017 | PKG-14 |  | L017 | MAT | PKG-14 |  | Pipe Support Steel Supply - structural supports guides anchors (~300 units) | 1 | LS | 180000 | 180000 | CAD | ALLOWANCE | A-007 | LOW | ~$600/unit average for support fabrications
PKG-14::L018 | PKG-14 |  | L018 | MAT | PKG-14 |  | Pipe Insulation and Heat Tracing Supply - cold weather protection for product lines | 1 | LS | 245000 | 245000 | CAD | ALLOWANCE | A-008 | LOW | ~$200/lm for insulation + heat trace on ~1200 lm major lines
PKG-14::L019 | PKG-14 |  | L019 | MAT | PKG-14 |  | Gaskets Bolting and Small Fittings - flange sets blind flanges specialty fittings | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-017 | LOW | ~5% of pipe material for gaskets bolts specialty items
PKG-14::L020 | PKG-14 |  | L020 | MAT | PKG-14 |  | Expansion Joints and Loops - thermal expansion provisions per stress analysis | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-018 | LOW | Allowance for expansion provisions; qty TBD from DEL-14.03
PKG-14::L021 | PKG-14 |  | L021 | CD | PKG-14 |  | Rail Unloading Header Fabrication and Installation - shop prefab field assembly welding NDE | 1 | LS | 280000 | 280000 | CAD | ALLOWANCE | A-001 | LOW | ~250 lm × $1100/lm install + elevated work
PKG-14::L022 | PKG-14 |  | L022 | CD | PKG-14 |  | Header Lateral Installation - field fit-up welding from unloading stations | 1 | LS | 80000 | 80000 | CAD | ALLOWANCE | A-001 | LOW | ~100 lm × $800/lm for smaller diameter laterals
PKG-14::L023 | PKG-14 |  | L023 | CD | PKG-14 |  | Tank Farm Piping Installation - inlet headers outlet manifold (~250 lm total) | 1 | LS | 275000 | 275000 | CAD | ALLOWANCE | A-002 | LOW | ~$1100/lm for large diameter tank farm piping
PKG-14::L024 | PKG-14 |  | L024 | CD | PKG-14 |  | Export Line Installation - welding testing support installation (~350 lm) | 1 | LS | 350000 | 350000 | CAD | ALLOWANCE | A-003 | LOW | ~$1000/lm for export piping installation
PKG-14::L025 | PKG-14 |  | L025 | CD | PKG-14 |  | Recycle Piping Installation - fabrication welding testing (~150 lm) | 1 | LS | 120000 | 120000 | CAD | ALLOWANCE | A-004 | LOW | ~$800/lm for medium diameter piping
PKG-14::L026 | PKG-14 |  | L026 | CD | PKG-14 |  | Nitrogen Distribution Installation - small bore piping threading welding (~400 lm) | 1 | LS | 160000 | 160000 | CAD | ALLOWANCE | A-005 | LOW | ~$400/lm for small bore N2 system
PKG-14::L027 | PKG-14 |  | L027 | CD | PKG-14 |  | Small Bore Utility Installation - drains vents samples (~200 lm) | 1 | LS | 80000 | 80000 | CAD | ALLOWANCE | A-006 | LOW | ~$400/lm for utility piping
PKG-14::L028 | PKG-14 |  | L028 | CD | PKG-14 |  | Pipe Support Installation - fabrication erection alignment (~300 units) | 1 | LS | 180000 | 180000 | CAD | ALLOWANCE | A-007 | LOW | ~$600/unit for support installation
PKG-14::L029 | PKG-14 |  | L029 | CD | PKG-14 |  | Insulation and Heat Trace Installation - jacketing tracing testing | 1 | LS | 185000 | 185000 | CAD | ALLOWANCE | A-008 | LOW | ~$150/lm for insulation + heat trace install on ~1200 lm
PKG-14::L030 | PKG-14 |  | L030 | CD | PKG-14 |  | Hydrostatic Testing - all process piping systems test and flush | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-019 | LOW | Multi-system hydro testing; ~10-15 test packages
PKG-14::L031 | PKG-14 |  | L031 | CD | PKG-14 |  | NDE and Weld Inspection - radiography UT visual per spec | 1 | LS | 125000 | 125000 | CAD | ALLOWANCE | A-020 | LOW | ~$250/weld average for 500+ welds
PKG-14::L032 | PKG-14 |  | L032 | CD | PKG-14 |  | Piping Specialty Work - tie-ins to existing hot taps valve installation | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-021 | LOW | Allowance for specialty piping connections
PKG-14::L033 | PKG-14 |  | L033 | CI | PKG-14 |  | Construction Indirects - field supervision site overhead QA/QC piping coordinator (factor-based) | 1 | LS | 359000 | 359000 | CAD | PARAMETRIC | D-010 | LOW | 18% of CD base ($1.975M × 0.18)
PKG-14::L034 | PKG-14 |  | L034 | PM | PKG-14 |  | EPCM / Project Management - PKG-14 allocation (factor-based) | 1 | LS | 298000 | 298000 | CAD | PARAMETRIC | D-010 | MED | 6% of (CD+CI+MAT) base
PKG-14::L035 | PKG-14 |  | L035 | P | PKG-14 |  | Procurement Services - vendor coordination expediting inspection (factor-based) | 1 | LS | 42000 | 42000 | CAD | PARAMETRIC | D-010 | MED | 2% of MAT ($2.125M × 0.02)
PKG-14::L036 | PKG-14 |  | L036 | COM | PKG-14 |  | Commissioning - piping flushing cleaning drying system turnover | 1 | LS | 136000 | 136000 | CAD | PARAMETRIC | D-010 | LOW | 3% of (CD+CI+MAT) base for piping commissioning
PKG-15::L-001 | PKG-15 | DEL-15.01 | L-001 | E | PKG-15 | DEL-15.01 | Pump arrangement drawings and installation design | 192 | hr | 208 | 39936 | CAD | PARAMETRIC | A-010 (Engineering hours distribution) | MEDIUM | 40% of total engineering effort; includes pump layout GA drawings foundation interface piping interface
PKG-15::L-002 | PKG-15 | DEL-15.02 | L-002 | E | PKG-15 | DEL-15.02 | Pump technical specifications development | 120 | hr | 208 | 24960 | CAD | PARAMETRIC | A-010 (Engineering hours distribution) | MEDIUM | 25% of total engineering effort; railcar marine sump transfer pump specs per API 610
PKG-15::L-003 | PKG-15 | DEL-15.03 | L-003 | E | PKG-15 | DEL-15.03 | Pump sizing calculations NPSH analysis system curves | 96 | hr | 208 | 19968 | CAD | PARAMETRIC | A-010 (Engineering hours distribution) | MEDIUM | 20% of total engineering effort; hydraulic calculations for all pump services
PKG-15::L-004 | PKG-15 | DEL-15.04 | L-004 | E | PKG-15 | DEL-15.04 | Vendor data review and approval (data sheets) | 48 | hr | 208 | 9984 | CAD | PARAMETRIC | A-010 (Engineering hours distribution) | MEDIUM | 10% of total engineering effort; review performance curves outline drawings foundation loads
PKG-15::L-005 | PKG-15 | DEL-15.05 | L-005 | E | PKG-15 | DEL-15.05 | Commissioning documentation and test record review | 24 | hr | 208 | 4992 | CAD | PARAMETRIC | A-010 (Engineering hours distribution) | MEDIUM | 5% of total engineering effort; FAT witness test procedures acceptance criteria
PKG-15::L-006 | PKG-15 |  | L-006 | MAT | PKG-15 |  | Marine loading pump 400 m3/hr 50kW API 610 (2 units) | 2 | ea | 125000 | 250000 | CAD | ALLOWANCE | A-001 A-002 (Parametric pump quantities and costs) | LOW | Duty/standby configuration; API 610 OH2 or BB2 type; 316SS wetted parts food-grade service
PKG-15::L-007 | PKG-15 |  | L-007 | MAT | PKG-15 |  | Railcar unloading transfer pump 200 m3/hr 30kW API 610 (4 units) | 4 | ea | 75000 | 300000 | CAD | ALLOWANCE | A-001 A-002 (Parametric pump quantities and costs) | LOW | 2 duty + 2 standby supporting 32 railcar stations; horizontal centrifugal API 610
PKG-15::L-008 | PKG-15 |  | L-008 | MAT | PKG-15 |  | Tank transfer pump 150 m3/hr 15kW API 610 (2 units) | 2 | ea | 45000 | 90000 | CAD | ALLOWANCE | A-001 A-002 (Parametric pump quantities and costs) | LOW | Tank-to-tank transfer and recirculation; operational flexibility OBJ-4
PKG-15::L-009 | PKG-15 |  | L-009 | MAT | PKG-15 |  | Sump pump 25 m3/hr 3kW (6 units) | 6 | ea | 12000 | 72000 | CAD | ALLOWANCE | A-001 A-002 (Parametric pump quantities and costs) | LOW | Containment sumps at railcar marine and tank areas; canola oil + water mixture service
PKG-15::L-010 | PKG-15 |  | L-010 | MAT | PKG-15 |  | Electric motors NEMA Premium efficiency TEFC (14 units) | 406 | kW | 500 | 203000 | CAD | ALLOWANCE | A-004 (Motor cost per kW) | MEDIUM | Total 406 kW across all pumps; 460V 3-phase typical; coordinate PKG-17/19 for final voltage
PKG-15::L-011 | PKG-15 |  | L-011 | MAT | PKG-15 |  | Variable frequency drives VFDs (7 units for critical pumps) | 203 | kW | 300 | 60900 | CAD | ALLOWANCE | A-004 (VFD cost per kW; 50% of pumps) | MEDIUM | VFDs for process control and energy efficiency; critical pumps only
PKG-15::L-012 | PKG-15 |  | L-012 | MAT | PKG-15 |  | Mechanical seal systems API 682 Type 2 with flush systems | 1 | LS | 127500 | 127500 | CAD | ALLOWANCE | A-011 (15% of pump cost for seal systems) | LOW | Cartridge seals with Plan 11 or Plan 32 support systems; dual seals for critical services TBD
PKG-15::L-013 | PKG-15 |  | L-013 | MAT | PKG-15 |  | Pump couplings (flexible spacer type) and fabricated baseplates | 1 | LS | 102000 | 102000 | CAD | ALLOWANCE | A-012 (12% of pump cost) | MEDIUM | API 610 Section 5.4 spacer couplings; grouted structural steel baseplates
PKG-15::L-014 | PKG-15 |  | L-014 | MAT | PKG-15 |  | Initial spare parts (seals impellers wear rings bearings) | 1 | LS | 68000 | 68000 | CAD | ALLOWANCE | A-013 (8% of pump equipment cost) | LOW | 1 spare seal per pump type; critical wear parts; spare parts philosophy TBD per ER and OBJ-9
PKG-15::L-015 | PKG-15 | DEL-15.01 | L-015 | CD | PKG-15 | DEL-15.01 | Pump rigging and setting (14 units) | 14 | ea | 1200 | 16800 | CAD | PARAMETRIC | A-003 (Installation productivity) | MEDIUM | Crane rental rigging unloading setting on baseplate; 8 manhours per pump avg
PKG-15::L-016 | PKG-15 | DEL-15.01 | L-016 | CD | PKG-15 | DEL-15.01 | Pump-motor alignment and coupling installation (14 units) | 14 | ea | 1520 | 21280 | CAD | PARAMETRIC | A-003 (Installation productivity) | MEDIUM | Rough and final alignment per API 610 Section 6.3; dial indicator or laser; 16 manhours per pump
PKG-15::L-017 | PKG-15 | DEL-15.01 | L-017 | CD | PKG-15 | DEL-15.01 | Baseplate grouting non-shrink grout min 25mm (14 units) | 14 | ea | 760 | 10640 | CAD | PARAMETRIC | A-003 (Installation productivity) | MEDIUM | API 610 Section 6.1.4 grouting requirements; 8 manhours per pump
PKG-15::L-018 | PKG-15 | DEL-15.05 | L-018 | CD | PKG-15 | DEL-15.05 | Mechanical completion and pre-comm inspection (14 units) | 14 | ea | 380 | 5320 | CAD | PARAMETRIC | A-003 (Installation productivity) | MEDIUM | Rotation check bolt torque lubrication check; 4 manhours per pump
PKG-15::L-019 | PKG-15 |  | L-019 | CI | PKG-15 |  | Construction indirects supervision temp facilities small tools HSE | 1 | LS | 9730 | 9730 | CAD | PARAMETRIC | D-010 (18% of CD per fallback model) | MEDIUM | Site supervision temporary laydown area small tools consumables safety equipment
PKG-15::L-020 | PKG-15 |  | L-020 | P | PKG-15 |  | Procurement services vendor solicitation expediting inspection | 1 | LS | 22000 | 22000 | CAD | PARAMETRIC | A-006 (2% of MAT) | MEDIUM | Technical bid evaluation purchase order management expediting receiving inspection
PKG-15::L-021 | PKG-15 |  | L-021 | PM | PKG-15 |  | EPCM and project management for PKG-15 | 1 | LS | 70620 | 70620 | CAD | PARAMETRIC | A-008 (6% of CD+CI+MAT per fallback model) | MEDIUM | Project management engineering management document control coordination meetings
PKG-15::L-022 | PKG-15 | DEL-15.05 | L-022 | COM | PKG-15 | DEL-15.05 | Performance testing flow head power vibration (14 units) | 14 | ea | 1140 | 15960 | CAD | PARAMETRIC | A-009 (Commissioning effort) | MEDIUM | Field performance test per API 610 Section 6.9; 12 manhours per pump @ $95/hr
PKG-15::L-023 | PKG-15 | DEL-15.05 | L-023 | COM | PKG-15 | DEL-15.05 | Vibration analysis and alignment verification (14 units) | 14 | ea | 380 | 5320 | CAD | PARAMETRIC | A-009 (Commissioning effort) | MEDIUM | Vibration measurement per API 610 Figure 15 or ISO 10816; 4 manhours per pump
PKG-15::L-024 | PKG-15 | DEL-15.05 | L-024 | COM | PKG-15 | DEL-15.05 | FAT witness travel allowance (major pumps) | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | D-015 (FAT witness for critical equipment) | LOW | Travel to vendor shop for Factory Acceptance Test witness; 6 major pumps assumed
PKG-16::L-001 | PKG-16 | DEL-16.01 | L-001 | E | PKG-16 | DEL-16.01 | Mechanical engineering design - Valve Design Drawing Set | 1 | LS | 155000 | 155000 | CAD | ALLOWANCE | A-1613 | MEDIUM | Valve arrangement drawings and actuator details for ~220 valves; includes CAD production; 1000 hours @ $155/hr blended rate per A-1613 and A-1614
PKG-16::L-002 | PKG-16 | DEL-16.02 | L-002 | E | PKG-16 | DEL-16.02 | Mechanical engineering design - Valve Technical Specification | 1 | LS | 77500 | 77500 | CAD | ALLOWANCE | A-1613 | MEDIUM | Three procurement specifications (control valve; isolation valve; relief valve); materials and performance requirements; 500 hours @ $155/hr per A-1613 and A-1614
PKG-16::L-003 | PKG-16 | DEL-16.03 | L-003 | E | PKG-16 | DEL-16.03 | Mechanical engineering design - Valve Design Calculations | 1 | LS | 116250 | 116250 | CAD | ALLOWANCE | A-1613 | MEDIUM | Control valve sizing (Cv calculations); relief valve sizing (API 520/521); actuator sizing; 750 hours @ $155/hr per A-1613 and A-1614
PKG-16::L-004 | PKG-16 | DEL-16.04 | L-004 | E | PKG-16 | DEL-16.04 | Mechanical engineering design - Valve Data Sheet Package | 1 | LS | 178250 | 178250 | CAD | ALLOWANCE | A-1613 | MEDIUM | Individual valve datasheets for ~220 valves (control; isolation; relief; strainers; specialty); 1150 hours @ $155/hr (avg 5 hrs per datasheet) per A-1613 and A-1614
PKG-16::L-005 | PKG-16 | DEL-16.04 | L-005 | MAT | PKG-16 | DEL-16.04 | Control valves with pneumatic actuators and positioners | 30 | EA | 13900 | 417000 | CAD | ALLOWANCE | A-1601 + A-1606 + A-1622 | LOW | 30 control valves (flow; pressure; level control) including pneumatic actuators; smart positioners; accessories; stainless steel 316SS; DN50-DN200 range per A-1602; unit cost per A-1606; includes positioners per A-1622
PKG-16::L-006 | PKG-16 | DEL-16.04 | L-006 | MAT | PKG-16 | DEL-16.04 | Isolation valves - manual (gate/ball/butterfly) | 92 | EA | 3880 | 357000 | CAD | ALLOWANCE | A-1601 + A-1606 + A-1608 | LOW | 92 manual isolation valves (block service; maintenance isolation); stainless steel 316SS; handwheel operated; DN50-DN300 range per A-1602; unit cost per A-1606; 68% of isolation valves manual per A-1604
PKG-16::L-007 | PKG-16 | DEL-16.04 | L-007 | MAT | PKG-16 | DEL-16.04 | Isolation valves - pneumatic actuated | 36 | EA | 8940 | 322000 | CAD | ALLOWANCE | A-1601 + A-1606 + A-1604 | LOW | 36 pneumatic automated isolation valves (ESD service; seasonal operation); stainless steel 316SS; includes pneumatic actuators; limit switches; DN50-DN200 range per A-1602 and A-1604; unit cost per A-1606
PKG-16::L-008 | PKG-16 | DEL-16.04 | L-008 | MAT | PKG-16 | DEL-16.04 | Isolation valves - electric actuated (MOV) | 22 | EA | 14270 | 314000 | CAD | ALLOWANCE | A-1601 + A-1606 + A-1604 | LOW | 22 electric motor-operated valves (large isolation; tank isolation); stainless steel 316SS; includes motor operators; limit switches; DN150-DN300 range per A-1602 and A-1604; hazardous area rated per A-1639; unit cost per A-1606 and A-1626
PKG-16::L-009 | PKG-16 | DEL-16.04 | L-009 | MAT | PKG-16 | DEL-16.04 | Relief valves (API 526 pressure relief) | 20 | EA | 6700 | 134000 | CAD | ALLOWANCE | A-1601 + A-1606 + A-1609 | LOW | 20 pressure relief valves (tank relief; pump relief; thermal relief); API 526 flanged steel PRVs; stainless steel; ASME stamped; DN25-DN150 range per A-1602; includes set pressure FAT per A-1624; unit cost per A-1606
PKG-16::L-010 | PKG-16 | DEL-16.04 | L-010 | MAT | PKG-16 | DEL-16.04 | Strainers (Y-type and basket) | 20 | EA | 3550 | 71000 | CAD | ALLOWANCE | A-1601 + A-1606 + A-1610 | LOW | 20 strainers (pump suction protection; meter protection); Y-type or basket style; stainless steel 316SS; DN50-DN200 range per A-1610; unit cost per A-1606
PKG-16::L-011 | PKG-16 | DEL-16.04 | L-011 | MAT | PKG-16 | DEL-16.04 | Check valves (swing/wafer/dual-plate) | 20 | EA | 3120 | 62400 | CAD | ALLOWANCE | A-1601 + A-1606 + A-1611 | LOW | 20 check valves (backflow prevention; pump discharge; gravity feed protection); swing or wafer style; stainless steel 316SS; DN50-DN300 range per A-1611; unit cost per A-1606
PKG-16::L-012 | PKG-16 | DEL-16.05 | L-012 | CD | PKG-16 | DEL-16.05 | Control valve installation and hookup | 30 | EA | 760 | 22800 | CAD | ALLOWANCE | A-1607 + A-1612 + A-1620 + A-1621 | MEDIUM | Control valve installation (rigging; bolting; alignment; pneumatic hookup; positioner calibration; stroking test); avg 8 hrs per valve @ $95/hr all-in rate per A-1607 and A-1612
PKG-16::L-013 | PKG-16 | DEL-16.05 | L-013 | CD | PKG-16 | DEL-16.05 | Isolation valve installation - manual | 92 | EA | 600 | 55200 | CAD | ALLOWANCE | A-1607 + A-1612 + A-1620 | MEDIUM | Manual isolation valve installation (rigging; bolting; gasket installation; alignment; hydrostatic test support); avg 6 hrs per valve @ $95/hr per A-1607 and A-1620
PKG-16::L-014 | PKG-16 | DEL-16.05 | L-014 | CD | PKG-16 | DEL-16.05 | Isolation valve installation - pneumatic actuated | 36 | EA | 855 | 30800 | CAD | ALLOWANCE | A-1607 + A-1612 + A-1620 + A-1621 | MEDIUM | Pneumatic automated isolation valve installation (valve installation 6 hrs + pneumatic hookup 3 hrs per A-1621); avg 9 hrs per valve @ $95/hr; includes air tubing; air set; limit switch wiring; leak check; stroking test per A-1620 and A-1621
PKG-16::L-015 | PKG-16 | DEL-16.05 | L-015 | CD | PKG-16 | DEL-16.05 | Isolation valve installation - electric actuated (MOV) | 22 | EA | 1200 | 26400 | CAD | ALLOWANCE | A-1607 + A-1612 + A-1620 + A-1621 | MEDIUM | Electric motor-operated valve installation (valve installation 8 hrs + electrical hookup 4 hrs per A-1621); avg 12 hrs per valve @ $95/hr; includes conduit/cable; terminations; motor test; limit switch wiring; stroking test per A-1620 and A-1621
PKG-16::L-016 | PKG-16 | DEL-16.05 | L-016 | CD | PKG-16 | DEL-16.05 | Relief valve installation and verification | 20 | EA | 475 | 9500 | CAD | ALLOWANCE | A-1607 + A-1612 + A-1620 | MEDIUM | Relief valve installation (rigging; bolting; alignment; discharge piping interface; field verification per A-1630); avg 5 hrs per valve @ $95/hr per A-1607 and A-1620; set pressure FAT by vendor (included in valve cost per A-1624)
PKG-16::L-017 | PKG-16 | DEL-16.05 | L-017 | CD | PKG-16 | DEL-16.05 | Strainer installation | 20 | EA | 380 | 7600 | CAD | ALLOWANCE | A-1607 + A-1612 + A-1620 | MEDIUM | Strainer installation (rigging; bolting; alignment; blowdown piping; access platform if required); avg 4 hrs per valve @ $95/hr per A-1607 and A-1620
PKG-16::L-018 | PKG-16 | DEL-16.05 | L-018 | CD | PKG-16 | DEL-16.05 | Check valve installation | 20 | EA | 285 | 5700 | CAD | ALLOWANCE | A-1607 + A-1612 + A-1620 | MEDIUM | Check valve installation (rigging; bolting; orientation verification; flow direction marking); avg 3 hrs per valve @ $95/hr per A-1607 and A-1620
PKG-16::L-019 | PKG-16 | DEL-16.05 | L-019 | CD | PKG-16 | DEL-16.05 | Special tools and equipment allowance | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-1633 | MEDIUM | Torque wrenches; hydrostatic test pump; valve repair tools; stroking test equipment; calibration tools per A-1633
PKG-16::L-020 | PKG-16 |  | L-020 | CI | PKG-16 |  | Construction Indirects (factor-based) | 1 | LS | 29700 | 29700 | CAD | PARAMETRIC | D-1620 (factor=0.18) | MEDIUM | CI = 0.18 × CD ($165k); includes field supervision; QA/QC; HSE; site overhead; temporary facilities per fallback typical model and D-1608
PKG-16::L-021 | PKG-16 |  | L-021 | P | PKG-16 |  | Procurement Services (factor-based) | 1 | LS | 33600 | 33600 | CAD | PARAMETRIC | D-1620 (factor=0.02) | MEDIUM | P = 0.02 × MAT ($1678k); includes vendor sourcing; PO processing; expediting; receiving inspection; material documentation; valve vendor coordination per fallback typical model and D-1608
PKG-16::L-022 | PKG-16 |  | L-022 | PM | PKG-16 |  | EPCM / Project Management (factor-based) | 1 | LS | 111000 | 111000 | CAD | PARAMETRIC | D-1620 (factor=0.06) | MEDIUM | PM = 0.06 × (CD + CI + MAT) ($1873k); includes project management; engineering management; cost/schedule control; contract administration; stakeholder coordination per fallback typical model and D-1608
PKG-16::L-023 | PKG-16 |  | L-023 | COM | PKG-16 |  | Commissioning (factor-based) | 1 | LS | 56200 | 56200 | CAD | PARAMETRIC | D-1620 (factor=0.03) | MEDIUM | COM = 0.03 × (CD + CI + MAT) ($1873k); includes pre-commissioning; valve stroking and functional testing per DEL-16.05; control loop checks per A-1629; relief valve field verification per A-1630; system acceptance; handover per fallback typical model and D-1608
PKG-17::L1701 | PKG-17 | DEL-17.01 | L1701 | E | PKG-17 | DEL-17.01 | Electrical Power Design Drawing Set - single line diagrams MV/LV distribution cable schedules grounding drawings (~25 drawings) | 1 | LS | 72000 | 72000 | CAD | ALLOWANCE | A-1701 | LOW | Allowance for electrical power drawing production; includes SLDs distribution layouts cable schedules grounding plans - typical electrical package complexity
PKG-17::L1702 | PKG-17 | DEL-17.02 | L1702 | E | PKG-17 | DEL-17.02 | Electrical Power Technical Specification - specification writing (transformer switchgear MCC cable grounding specs) | 1 | LS | 38000 | 38000 | CAD | ALLOWANCE | A-1702 | LOW | Allowance for electrical specification writing; includes transformer spec switchgear spec MCC spec cable spec grounding spec
PKG-17::L1703 | PKG-17 | DEL-17.03 | L1703 | E | PKG-17 | DEL-17.03 | Electrical Power Design Calculations - load calculations short circuit protection coordination voltage drop analysis | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-1703 | LOW | Allowance for electrical calculations; includes load flow short circuit coordination studies voltage drop cable sizing - requires P.Eng. stamp
PKG-17::L1704 | PKG-17 | DEL-17.04 | L1704 | E | PKG-17 | DEL-17.04 | Electrical Power Data Sheet Package - equipment data sheets (transformer MCC switchgear UPS panels) | 1 | LS | 22000 | 22000 | CAD | ALLOWANCE | A-1704 | LOW | Allowance for electrical data sheet compilation; includes transformer datasheets MCC datasheets switchgear datasheets UPS datasheet
PKG-17::L1705 | PKG-17 | DEL-17.05 | L1705 | E | PKG-17 | DEL-17.05 | Electrical Power Installation & Test Records - QA/QC documentation setup and record preparation (insulation tests relay tests FAT records) | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-1705 | LOW | Allowance for QA/QC documentation templates and record closeout for electrical installation and testing
PKG-17::L1706 | PKG-17 |  | L1706 | MAT | PKG-17 |  | MV/LV Transformers - pad-mounted transformers (assume 2 units 1000-1500 kVA each) with protection and auxiliaries | 2 | EA | 145000 | 290000 | CAD | ALLOWANCE | A-1706 | LOW | Placeholder for transformer supply; actual size depends on load calculations - assumes 2 transformers for redundancy/load distribution
PKG-17::L1707 | PKG-17 |  | L1707 | MAT | PKG-17 |  | MV Switchgear - medium voltage metal-clad switchgear lineup (assume 5-bay lineup with main breaker and feeders) | 1 | LS | 385000 | 385000 | CAD | ALLOWANCE | A-1707 | LOW | Placeholder for MV switchgear; includes main incoming breaker transformer feeders metering and protection relays - marine/industrial rated
PKG-17::L1708 | PKG-17 |  | L1708 | MAT | PKG-17 |  | LV Switchgear - low voltage switchboard/panelboard lineup (assume main-tie-main configuration) | 1 | LS | 165000 | 165000 | CAD | ALLOWANCE | A-1708 | LOW | Placeholder for LV switchgear; includes main breakers bus ties distribution feeders - rated for industrial duty
PKG-17::L1709 | PKG-17 |  | L1709 | MAT | PKG-17 |  | Motor Control Centers (MCCs) - MCCs for pump motors and process equipment (assume 3 MCCs total - railcar area tank farm marine area) | 3 | EA | 125000 | 375000 | CAD | ALLOWANCE | A-1709 | LOW | Placeholder for MCC supply; assumes 3 MCCs distributed across facility areas - each MCC sized for local motor loads with VFDs where required
PKG-17::L1710 | PKG-17 |  | L1710 | MAT | PKG-17 |  | Distribution Panels and Subpanels - local distribution panels for lighting receptacles small power (assume 8 panels) | 8 | EA | 8500 | 68000 | CAD | ALLOWANCE | A-1710 | LOW | Placeholder for distribution panel supply; includes panels for MCC building operator shelters field locations
PKG-17::L1711 | PKG-17 |  | L1711 | MAT | PKG-17 |  | UPS System - uninterruptible power supply for control systems and critical loads (assume 10 kVA unit) | 1 | EA | 22000 | 22000 | CAD | ALLOWANCE | A-1711 | LOW | Placeholder for UPS system; sized for control system DCS HMI and critical instrumentation loads
PKG-17::L1712 | PKG-17 |  | L1712 | MAT | PKG-17 |  | Grounding Materials - ground grid electrodes bonding conductors exothermic welds test wells (assume 1200m ground conductor 15 electrodes) | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-1712 | LOW | Placeholder for grounding system materials; includes ground grid buried conductors driven electrodes bonding to structures/equipment/tanks
PKG-17::L1713 | PKG-17 |  | L1713 | MAT | PKG-17 |  | MV Power Cable - medium voltage power cable 5kV-15kV (assume 800m total MV cable runs transformer feeders) | 800 | M | 185 | 148000 | CAD | ALLOWANCE | A-1713 | LOW | Placeholder for MV cable; actual length depends on equipment layout and routing - assumes shielded EPR/XLPE cable rated 5-15kV
PKG-17::L1714 | PKG-17 |  | L1714 | MAT | PKG-17 |  | LV Power Cable - low voltage power cable 600V (assume 3500m total LV feeder and branch cable) | 3500 | M | 42 | 147000 | CAD | ALLOWANCE | A-1714 | LOW | Placeholder for LV cable; includes feeder cables to MCCs panels and equipment - assumes TECK90 or equivalent 600V rated cable
PKG-17::L1715 | PKG-17 |  | L1715 | MAT | PKG-17 |  | Control Cable - control and instrumentation cable 600V (assume 2500m for motor controls I/O signals) | 2500 | M | 28 | 70000 | CAD | ALLOWANCE | A-1715 | LOW | Placeholder for control cable; multi-conductor shielded cable for motor control circuits and I/O signals to field devices
PKG-17::L1716 | PKG-17 |  | L1716 | MAT | PKG-17 |  | Cable Tray and Ladder Rack - galvanized cable tray with fittings and supports (assume 900m total tray) | 900 | M | 145 | 130500 | CAD | ALLOWANCE | A-1716 | LOW | Placeholder for cable tray system; includes tray ladder rack fittings hangers supports - marine-environment galvanized or stainless where exposed
PKG-17::L1717 | PKG-17 |  | L1717 | MAT | PKG-17 |  | Conduit and Fittings - PVC and rigid conduit for underground/embedded/local routing (assume 600m total conduit) | 600 | M | 65 | 39000 | CAD | ALLOWANCE | A-1717 | LOW | Placeholder for conduit system; includes underground duct banks rigid conduit for equipment connections PVC for concrete embedment
PKG-17::L1718 | PKG-17 |  | L1718 | MAT | PKG-17 |  | Electrical Installation Materials - termination hardware wire ferrules labels panel accessories miscellaneous | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-1718 | LOW | Placeholder for installation materials; includes lugs ferrules labels wire markers junction boxes pull boxes grounding hardware
PKG-17::L1719 | PKG-17 |  | L1719 | FRT | PKG-17 |  | Freight and Logistics - electrical equipment transport delivery coordination receiving (transformers switchgear MCCs) | 1 | LS | 58000 | 58000 | CAD | ALLOWANCE | A-1719 | LOW | Placeholder for freight; includes transport of major electrical equipment from suppliers to site - transformers and switchgear require specialized rigging
PKG-17::L1720 | PKG-17 |  | L1720 | CD | PKG-17 |  | Transformer Installation - rigging setting pad mounting grounding terminations testing (2 transformers) | 2 | EA | 28000 | 56000 | CAD | ALLOWANCE | A-1720 | LOW | Placeholder for transformer installation; includes crane rigging pad mounting HV/LV terminations grounding connections insulation/turns-ratio testing
PKG-17::L1721 | PKG-17 |  | L1721 | CD | PKG-17 |  | MV Switchgear Installation - rigging setting bus connections terminations protection relay programming testing | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-1721 | LOW | Placeholder for MV switchgear installation; includes rigging setting bus work terminations relay settings hipot testing functional testing
PKG-17::L1722 | PKG-17 |  | L1722 | CD | PKG-17 |  | LV Switchgear Installation - rigging setting bus connections terminations testing (main-tie-main configuration) | 1 | LS | 48000 | 48000 | CAD | ALLOWANCE | A-1722 | LOW | Placeholder for LV switchgear installation; includes setting terminations testing - less complex than MV switchgear
PKG-17::L1723 | PKG-17 |  | L1723 | CD | PKG-17 |  | MCC Installation and Terminations - MCC setting motor feeder terminations VFD programming testing (3 MCCs distributed areas) | 3 | EA | 42000 | 126000 | CAD | ALLOWANCE | A-1723 | LOW | Placeholder for MCC installation; includes setting motor circuit terminations VFD setup testing - 3 MCCs across railcar tank farm marine areas
PKG-17::L1724 | PKG-17 |  | L1724 | CD | PKG-17 |  | Distribution Panel Installation - panel mounting terminations circuit testing labeling (8 panels) | 8 | EA | 4500 | 36000 | CAD | ALLOWANCE | A-1724 | LOW | Placeholder for panel installation; includes mounting feeder/branch terminations circuit testing labeling
PKG-17::L1725 | PKG-17 |  | L1725 | CD | PKG-17 |  | UPS Installation and Testing - UPS setting battery installation programming load testing | 1 | EA | 8500 | 8500 | CAD | ALLOWANCE | A-1725 | LOW | Placeholder for UPS installation; includes setting battery installation programming load bank testing acceptance testing
PKG-17::L1726 | PKG-17 |  | L1726 | CD | PKG-17 |  | Grounding System Installation - ground grid installation electrode driving bonding exothermic welding testing | 1 | LS | 135000 | 135000 | CAD | ALLOWANCE | A-1726 | LOW | Placeholder for grounding installation; includes trenching grid conductor installation driven electrodes exothermic welds bonds to structures/equipment soil resistance testing
PKG-17::L1727 | PKG-17 |  | L1727 | CD | PKG-17 |  | Cable Tray and Conduit Installation - tray installation supports conduit installation underground duct bank installation | 1 | LS | 185000 | 185000 | CAD | ALLOWANCE | A-1727 | LOW | Placeholder for cable support installation; includes tray installation hangers supports conduit bending/threading underground duct bank trenching/bedding/backfill
PKG-17::L1728 | PKG-17 |  | L1728 | CD | PKG-17 |  | Cable Pulling and Termination - cable pulling terminations testing labeling (MV LV control cables ~6800m total) | 1 | LS | 295000 | 295000 | CAD | ALLOWANCE | A-1728 | LOW | Placeholder for cable installation; includes pulling/training terminations at both ends megger testing hipot testing (MV) labeling - significant labor content
PKG-17::L1729 | PKG-17 |  | L1729 | CD | PKG-17 |  | Electrical Testing and Commissioning Support - insulation testing continuity relay functional testing loop checks coordination with commissioning | 1 | LS | 75000 | 75000 | CAD | ALLOWANCE | A-1729 | LOW | Placeholder for electrical testing; includes final insulation testing protection relay testing continuity checks pre-commissioning support
PKG-17::L1730 | PKG-17 |  | L1730 | CI | PKG-17 |  | Construction Indirects - field supervision electrical safety QA/QC coordination (factor-based) | 1 | LS | 188910 | 188910 | CAD | PARAMETRIC | D-1708 | LOW | 18% of CD base ($1
PKG-17::L1731 | PKG-17 |  | L1731 | PM | PKG-17 |  | EPCM / Project Management - PKG-17 allocation electrical engineering coordination (factor-based) | 1 | LS | 197155 | 197155 | CAD | PARAMETRIC | D-1708 | MED | 6% of (CD+CI+MAT+FRT) = 6% x ($1
PKG-17::L1732 | PKG-17 |  | L1732 | P | PKG-17 |  | Procurement Services - electrical equipment vendor coordination expediting inspection FAT witness (factor-based) | 1 | LS | 40950 | 40950 | CAD | PARAMETRIC | D-1708 | MED | 2% of (MAT+FRT) = 2% x ($1
PKG-17::L1733 | PKG-17 |  | L1733 | COM | PKG-17 |  | Electrical Systems Commissioning - protection relay functional testing integrated systems testing energization support acceptance | 1 | LS | 96837 | 96837 | CAD | PARAMETRIC | D-1708 | LOW | 3% of (CD+CI+MAT) = 3% x ($1
PKG-18::L-1801 | PKG-18 | DEL-18.01 | L-1801 | E | PKG-18 | DEL-18.01 | Lighting Design Drawing Set - Exterior lighting layout | 1 | LS | 13000 | 13000 | CAD | ALLOWANCE | A-1801; D-1806 | LOW | Drawing production for exterior lighting (poles and fixtures)
PKG-18::L-1802 | PKG-18 | DEL-18.01 | L-1802 | E | PKG-18 | DEL-18.01 | Lighting Design Drawing Set - Interior lighting layout | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-1803; D-1806 | LOW | Drawing production for interior lighting (buildings and process areas)
PKG-18::L-1803 | PKG-18 | DEL-18.01 | L-1803 | E | PKG-18 | DEL-18.01 | Lighting Design Drawing Set - Emergency lighting layout | 1 | LS | 5000 | 5000 | CAD | ALLOWANCE | A-1805; D-1806 | LOW | Drawing production for emergency and egress lighting
PKG-18::L-1804 | PKG-18 | DEL-18.02 | L-1804 | E | PKG-18 | DEL-18.02 | Lighting Technical Specification - LED lighting spec | 1 | LS | 13000 | 13000 | CAD | ALLOWANCE | D-1806 | LOW | Technical specification for LED fixtures and poles (CSI format)
PKG-18::L-1805 | PKG-18 | DEL-18.02 | L-1805 | E | PKG-18 | DEL-18.02 | Lighting Technical Specification - Controls spec | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-1824; D-1806 | LOW | Technical specification for lighting controls and integration
PKG-18::L-1806 | PKG-18 | DEL-18.02 | L-1806 | E | PKG-18 | DEL-18.02 | Lighting Technical Specification - Emergency lighting spec | 1 | LS | 4000 | 4000 | CAD | ALLOWANCE | A-1825; D-1806 | LOW | Technical specification for emergency lighting systems
PKG-18::L-1807 | PKG-18 | DEL-18.03 | L-1807 | E | PKG-18 | DEL-18.03 | Lighting Design Calculations - Photometric analysis | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-1823; D-1806 | LOW | Illumination calculations for exterior and interior areas (software modeling)
PKG-18::L-1808 | PKG-18 | DEL-18.04 | L-1808 | E | PKG-18 | DEL-18.04 | Lighting Data Sheet Package - Fixture and pole data sheets | 1 | LS | 5000 | 5000 | CAD | ALLOWANCE | D-1806 | LOW | Data sheet package for fixtures and poles (vendor submittals)
PKG-18::L-1809 | PKG-18 | DEL-18.05 | L-1809 | E | PKG-18 | DEL-18.05 | Lighting Installation & Test Records - Test documentation | 1 | LS | 5000 | 5000 | CAD | ALLOWANCE | D-1806 | LOW | Installation and commissioning test records preparation
PKG-18::L-1810 | PKG-18 |  | L-1810 | MAT | PKG-18 |  | Exterior LED area lights - Pole-mounted fixtures | 40 | EA | 2200 | 88000 | CAD | ALLOWANCE | A-1801; A-1809; D-1806 | LOW | LED area lights (150-300W equivalent; IP65+; marine-grade; mid-range qty)
PKG-18::L-1811 | PKG-18 |  | L-1811 | MAT | PKG-18 |  | Exterior LED wall packs - Building-mounted fixtures | 25 | EA | 800 | 20000 | CAD | ALLOWANCE | A-1802; A-1809; D-1806 | LOW | LED wall packs (50-100W equivalent; IP65+; building-mounted)
PKG-18::L-1812 | PKG-18 |  | L-1812 | MAT | PKG-18 |  | Interior high-bay LED fixtures | 50 | EA | 1100 | 55000 | CAD | ALLOWANCE | A-1803; A-1810; D-1806 | LOW | High-bay LED fixtures (100-200W equivalent; IP54+; warehouse/process areas)
PKG-18::L-1813 | PKG-18 |  | L-1813 | MAT | PKG-18 |  | Interior office/control room LED fixtures | 40 | EA | 450 | 18000 | CAD | ALLOWANCE | A-1804; A-1811; D-1806 | LOW | Office LED fixtures (troffer or linear; IP20-40; offices and control rooms)
PKG-18::L-1814 | PKG-18 |  | L-1814 | MAT | PKG-18 |  | Emergency battery-backed LED fixtures | 32 | EA | 750 | 24000 | CAD | ALLOWANCE | A-1805; A-1812; D-1806 | LOW | Emergency LED fixtures with integral battery backup (90-min duration per NFPA 101)
PKG-18::L-1815 | PKG-18 |  | L-1815 | MAT | PKG-18 |  | Lighting control sensors and devices | 25 | EA | 1000 | 25000 | CAD | ALLOWANCE | A-1806; A-1813; D-1806 | LOW | Occupancy sensors; photocells; switches; contactors; integration devices
PKG-18::L-1816 | PKG-18 |  | L-1816 | MAT | PKG-18 |  | Exterior lighting poles - Steel or aluminum | 40 | EA | 6000 | 240000 | CAD | ALLOWANCE | A-1807; A-1814; D-1806 | LOW | Lighting poles (30-40 ft; steel or aluminum; galvanized or powder-coated; marine-grade; base plate and anchor bolts; excludes foundation)
PKG-18::L-1817 | PKG-18 |  | L-1817 | MAT | PKG-18 |  | Hazardous area lighting fixtures - Explosion-proof | 8 | EA | 4000 | 32000 | CAD | ALLOWANCE | A-1808; A-1821; D-1806 | LOW | Explosion-proof or Class I Div 1/2 LED fixtures for classified areas (10-20% of total fixtures assumed)
PKG-18::L-1818 | PKG-18 |  | L-1818 | MAT | PKG-18 |  | Wiring and conduit - Branch circuits | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-1818; A-1827; D-1806 | LOW | Lighting circuit wiring; conduit; boxes; connectors; accessories (extent TBD pending layouts)
PKG-18::L-1819 | PKG-18 |  | L-1819 | MAT | PKG-18 |  | Lighting control panel and integration hardware | 1 | LS | 28000 | 28000 | CAD | ALLOWANCE | A-1824; D-1806 | LOW | Control panels; relays; communication modules; integration with PKG-19 (scope TBD)
PKG-18::L-1820 | PKG-18 |  | L-1820 | CD | PKG-18 |  | Exterior pole installation - Setting and wiring | 40 | EA | 1500 | 60000 | CAD | ALLOWANCE | A-1807; A-1815; D-1806 | LOW | Pole erection; alignment; grounding; wiring to fixture (excludes foundation by civil)
PKG-18::L-1821 | PKG-18 |  | L-1821 | CD | PKG-18 |  | Exterior fixture installation - Pole-mounted and wall-mounted | 65 | EA | 540 | 35000 | CAD | ALLOWANCE | A-1801; A-1802; A-1815; D-1806 | LOW | Mounting of exterior fixtures to poles or building walls; aiming and alignment
PKG-18::L-1822 | PKG-18 |  | L-1822 | CD | PKG-18 |  | Interior fixture installation - High-bay and office | 90 | EA | 200 | 18000 | CAD | ALLOWANCE | A-1803; A-1804; A-1816; D-1806 | LOW | Mounting of interior fixtures to ceilings or walls; includes wiring to fixtures
PKG-18::L-1823 | PKG-18 |  | L-1823 | CD | PKG-18 |  | Emergency lighting installation | 32 | EA | 310 | 10000 | CAD | ALLOWANCE | A-1805; A-1816; D-1806 | LOW | Emergency fixture installation and battery backup wiring
PKG-18::L-1824 | PKG-18 |  | L-1824 | CD | PKG-18 |  | Lighting controls installation and programming | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-1817; A-1824; D-1806 | LOW | Installation of sensors; switches; control panels; system programming and integration with PKG-19
PKG-18::L-1825 | PKG-18 |  | L-1825 | CD | PKG-18 |  | Circuit wiring and terminations | 1 | LS | 100000 | 100000 | CAD | ALLOWANCE | A-1818; A-1827; D-1806 | LOW | Lighting circuit wiring; panel terminations; testing; labeling (labor portion)
PKG-18::L-1826 | PKG-18 |  | L-1826 | CD | PKG-18 |  | Hazardous area fixture installation premium | 8 | EA | 875 | 7000 | CAD | ALLOWANCE | A-1808; A-1821; D-1806 | LOW | Additional labor for explosion-proof fixture installation (sealing; grounding; special tools)
PKG-18::L-1827 | PKG-18 |  | L-1827 | CI | PKG-18 |  | Construction indirects - Field supervision and QA/QC | 1 | LS | 47700 | 47700 | CAD | PARAMETRIC | D-1807 (18% of CD) | MED | Field supervision; electrical safety oversight; installation QA/QC (18% of $265;000 CD)
PKG-18::L-1828 | PKG-18 |  | L-1828 | PM | PKG-18 |  | EPCM / Project management - Lighting coordination | 1 | LS | 78540 | 78540 | CAD | PARAMETRIC | D-1807 (6% of CD+CI+MAT) | MED | Electrical engineering coordination; interface management with PKG-17; PKG-19; PKG-21 (6% of $787;700)
PKG-18::L-1829 | PKG-18 |  | L-1829 | P | PKG-18 |  | Procurement services - Vendor coordination and expediting | 1 | LS | 9500 | 9500 | CAD | PARAMETRIC | D-1807 (2% of MAT) | MED | Fixture and equipment procurement; vendor coordination; expediting (2% of $475;000 MAT)
PKG-18::L-1830 | PKG-18 |  | L-1830 | COM | PKG-18 |  | Commissioning - Illumination testing and functional testing | 1 | LS | 166596 | 166596 | CAD | PARAMETRIC | D-1808 (Enhanced for testing scope) | MED | Field illumination testing (exterior and interior); emergency duration testing; control functional testing; training; acceptance
PKG-19::L-001 | PKG-19 | DEL-19.01 | L-001 | E | PKG-19 | DEL-19.01 | Control system architecture design | 1 | LS | 30000 | 30000 | CAD | ALLOWANCE | A-015 | LOW | System architecture and network design
PKG-19::L-002 | PKG-19 | DEL-19.01 | L-002 | E | PKG-19 | DEL-19.01 | Control system design drawings | 1 | LS | 30000 | 30000 | CAD | ALLOWANCE | A-015 | LOW | Cabinet layouts HMI arrangement drawings
PKG-19::L-003 | PKG-19 | DEL-19.02 | L-003 | E | PKG-19 | DEL-19.02 | DCS/PLC technical specification | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-016 | LOW | Technical specification document
PKG-19::L-004 | PKG-19 | DEL-19.02 | L-004 | E | PKG-19 | DEL-19.02 | HMI and historian specification | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-016 | LOW | HMI and historian technical specs
PKG-19::L-005 | PKG-19 | DEL-19.03 | L-005 | E | PKG-19 | DEL-19.03 | Data sheet package preparation | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-017 | LOW | Vendor submittal review and approval
PKG-19::L-006 | PKG-19 | DEL-19.04 | L-006 | E | PKG-19 | DEL-19.04 | PLC/DCS application software development | 1 | LS | 80000 | 80000 | CAD | ALLOWANCE | A-018 | LOW | Control logic interlocks sequences
PKG-19::L-007 | PKG-19 | DEL-19.04 | L-007 | E | PKG-19 | DEL-19.04 | HMI graphics development | 1 | LS | 30000 | 30000 | CAD | ALLOWANCE | A-018 | LOW | 40-60 HMI screens estimated
PKG-19::L-008 | PKG-19 | DEL-19.04 | L-008 | E | PKG-19 | DEL-19.04 | Historian configuration | 1 | LS | 10000 | 10000 | CAD | ALLOWANCE | A-018 | LOW | Tag database trending reporting
PKG-19::L-009 | PKG-19 |  | L-009 | PM | PKG-19 |  | Project management - control systems | 1 | LS | 120000 | 120000 | CAD | PARAMETRIC | D-010 | LOW | 6% of CD+CI+MAT per fallback model
PKG-19::L-010 | PKG-19 |  | L-010 | P | PKG-19 |  | Procurement services - control systems | 1 | LS | 18000 | 18000 | CAD | PARAMETRIC | D-010 | LOW | 2% of MAT per fallback model
PKG-19::L-011 | PKG-19 |  | L-011 | MAT | PKG-19 |  | DCS/PLC controllers (redundant pair) | 2 | EA | 90000 | 180000 | CAD | ALLOWANCE | A-003 | LOW | Primary and standby controllers
PKG-19::L-012 | PKG-19 |  | L-012 | MAT | PKG-19 |  | I/O modules and racks | 1 | LS | 120000 | 120000 | CAD | ALLOWANCE | A-007 | LOW | 40-50 modules for 600-800 I/O points
PKG-19::L-013 | PKG-19 |  | L-013 | MAT | PKG-19 |  | HMI workstations (control room) | 3 | EA | 25000 | 75000 | CAD | ALLOWANCE | A-004 | LOW | 2 operator + 1 engineering station
PKG-19::L-014 | PKG-19 |  | L-014 | MAT | PKG-19 |  | Remote HMI panels | 3 | EA | 15000 | 45000 | CAD | ALLOWANCE | A-005 | LOW | Railcar tankfarm marine areas
PKG-19::L-015 | PKG-19 |  | L-015 | MAT | PKG-19 |  | Historian server and software | 1 | LS | 80000 | 80000 | CAD | ALLOWANCE | A-008 | LOW | Server hardware + historian license
PKG-19::L-016 | PKG-19 |  | L-016 | MAT | PKG-19 |  | Industrial network switches | 10 | EA | 6000 | 60000 | CAD | ALLOWANCE | A-009 | LOW | Managed industrial Ethernet switches
PKG-19::L-017 | PKG-19 |  | L-017 | MAT | PKG-19 |  | Fiber optic infrastructure | 2000 | M | 40 | 80000 | CAD | ALLOWANCE | A-010 | LOW | Fiber backbone tankfarm to control room
PKG-19::L-018 | PKG-19 |  | L-018 | MAT | PKG-19 |  | Control cabinets and enclosures | 8 | EA | 15000 | 120000 | CAD | ALLOWANCE | A-011 | LOW | Main panel + field junction boxes
PKG-19::L-019 | PKG-19 |  | L-019 | MAT | PKG-19 |  | Control system software licenses | 1 | LS | 100000 | 100000 | CAD | ALLOWANCE | A-019 | LOW | DCS/PLC HMI historian licenses
PKG-19::L-020 | PKG-19 |  | L-020 | MAT | PKG-19 |  | Miscellaneous cables and terminations | 1 | LS | 60000 | 60000 | CAD | ALLOWANCE | A-020 | LOW | Control cables patch cables terminations
PKG-19::L-021 | PKG-19 |  | L-021 | CD | PKG-19 |  | Control cabinet installation | 8 | EA | 8000 | 64000 | CAD | ALLOWANCE | A-011 | LOW | Cabinet setting alignment termination
PKG-19::L-022 | PKG-19 |  | L-022 | CD | PKG-19 |  | Control system wiring and termination | 1 | LS | 150000 | 150000 | CAD | ALLOWANCE | A-020 | LOW | Field wiring to I/O modules
PKG-19::L-023 | PKG-19 |  | L-023 | CD | PKG-19 |  | Network installation (fiber and copper) | 1 | LS | 80000 | 80000 | CAD | ALLOWANCE | A-010 | LOW | Fiber optic and Ethernet installation
PKG-19::L-024 | PKG-19 |  | L-024 | CD | PKG-19 |  | HMI and server installation | 1 | LS | 30000 | 30000 | CAD | ALLOWANCE | A-004 | LOW | Control room equipment installation
PKG-19::L-025 | PKG-19 |  | L-025 | CD | PKG-19 |  | Remote HMI installation | 3 | EA | 8000 | 24000 | CAD | ALLOWANCE | A-005 | LOW | Field HMI panel installation
PKG-19::L-026 | PKG-19 | DEL-19.05 | L-026 | CD | PKG-19 | DEL-19.05 | Installation quality records | 1 | LS | 32000 | 32000 | CAD | ALLOWANCE | A-021 | LOW | QA/QC documentation completion
PKG-19::L-027 | PKG-19 |  | L-027 | CI | PKG-19 |  | Construction indirects - control systems | 1 | LS | 68000 | 68000 | CAD | PARAMETRIC | D-010 | LOW | 18% of CD per fallback model
PKG-19::L-028 | PKG-19 |  | L-028 | COM | PKG-19 |  | Factory acceptance test (FAT) | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-022 | LOW | FAT at vendor facility
PKG-19::L-029 | PKG-19 |  | L-029 | COM | PKG-19 |  | Site acceptance test (SAT) | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-022 | LOW | On-site testing with field devices
PKG-19::L-030 | PKG-19 |  | L-030 | COM | PKG-19 |  | Commissioning support | 1 | LS | 10000 | 10000 | CAD | ALLOWANCE | A-022 | LOW | Vendor commissioning assistance
PKG-20::L001 | PKG-20 | DEL-20.01 | L001 | E | PKG-20 | DEL-20.01 | Instrumentation Design Drawing Set - instrument location plans installation details cable schedules | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-011 | LOW | ~35 sheets at $2.5k/sheet average for I&C
PKG-20::L002 | PKG-20 | DEL-20.02 | L002 | E | PKG-20 | DEL-20.02 | Instrumentation Technical Specification - level pressure temperature specification development | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-012 | LOW | ~220 hours at $250/hr for I&C engineer
PKG-20::L003 | PKG-20 | DEL-20.03 | L003 | E | PKG-20 | DEL-20.03 | Instrumentation Design Calculations - instrument sizing calculations range selection verification | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-013 | LOW | ~140 hours at $250/hr for I&C engineer
PKG-20::L004 | PKG-20 | DEL-20.04 | L004 | E | PKG-20 | DEL-20.04 | Instrumentation Data Sheet Package - level pressure temperature flow instrument data sheets | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-014 | LOW | ~106 instrument data sheets at $600/sheet average
PKG-20::L005 | PKG-20 | DEL-20.05 | L005 | E | PKG-20 | DEL-20.05 | Instrumentation Installation & Test Records - calibration procedures loop check records FAT documentation | 1 | LS | 40000 | 40000 | CAD | ALLOWANCE | A-015 | LOW | ~160 hours at $250/hr QA/QC engineer
PKG-20::L006 | PKG-20 |  | L006 | MAT | PKG-20 |  | Tank Level Transmitters - guided wave radar level transmitters (3 tanks × 2 per tank redundant) | 6 | EA | 8500 | 51000 | CAD | ALLOWANCE | A-004 | LOW | HART protocol GWR transmitters for viscous oil service
PKG-20::L007 | PKG-20 |  | L007 | MAT | PKG-20 |  | Tank Level Switches - high/high-high level switches for overflow protection (3 tanks × 2 per tank) | 6 | EA | 3500 | 21000 | CAD | ALLOWANCE | A-004 | LOW | Vibrating fork or float type switches
PKG-20::L008 | PKG-20 |  | L008 | MAT | PKG-20 |  | Tank Temperature Elements - RTD assemblies with thermowells (3 tanks × 2 per tank) | 6 | EA | 2800 | 16800 | CAD | ALLOWANCE | A-004 | LOW | PT100 RTD with SS thermowell
PKG-20::L009 | PKG-20 |  | L009 | MAT | PKG-20 |  | Tank Pressure Transmitters - tank pressure/vacuum monitoring (3 tanks × 1 per tank) | 3 | EA | 4200 | 12600 | CAD | ALLOWANCE | A-004 | LOW | Low pressure transmitters for atmospheric tanks
PKG-20::L010 | PKG-20 |  | L010 | MAT | PKG-20 |  | Tank Temperature Transmitters - temperature transmitters (3 tanks × 1 per tank) | 3 | EA | 2200 | 6600 | CAD | ALLOWANCE | A-004 | LOW | HART temperature transmitters
PKG-20::L011 | PKG-20 |  | L011 | MAT | PKG-20 |  | Railcar Unloading Flow Indicators - sight flow indicators at unloading stations (32 units) | 32 | EA | 650 | 20800 | CAD | ALLOWANCE | A-005 | LOW | Sight glass flow indicators
PKG-20::L012 | PKG-20 |  | L012 | MAT | PKG-20 |  | Railcar Unloading Temperature Elements - RTD assemblies for header temperature monitoring (8 units) | 8 | EA | 2200 | 17600 | CAD | ALLOWANCE | A-005 | LOW | PT100 RTD with thermowell
PKG-20::L013 | PKG-20 |  | L013 | MAT | PKG-20 |  | Marine Loading Pressure Transmitters - loading arm and platform pressure monitoring (6 units) | 6 | EA | 4500 | 27000 | CAD | ALLOWANCE | A-006 | LOW | HART pressure transmitters
PKG-20::L014 | PKG-20 |  | L014 | MAT | PKG-20 |  | Marine Loading Level Switches - sump and containment level detection (4 units) | 4 | EA | 2800 | 11200 | CAD | ALLOWANCE | A-006 | LOW | Float switches for sump service
PKG-20::L015 | PKG-20 |  | L015 | MAT | PKG-20 |  | Marine Loading Temperature Elements - product temperature monitoring (2 units) | 2 | EA | 2800 | 5600 | CAD | ALLOWANCE | A-006 | LOW | PT100 RTD with thermowell
PKG-20::L016 | PKG-20 |  | L016 | MAT | PKG-20 |  | Transfer Piping Pressure Transmitters - pump suction/discharge headers (12 units) | 12 | EA | 4500 | 54000 | CAD | ALLOWANCE | A-007 | LOW | HART pressure transmitters
PKG-20::L017 | PKG-20 |  | L017 | MAT | PKG-20 |  | Transfer Piping Temperature Elements - process temperature monitoring (8 units) | 8 | EA | 2800 | 22400 | CAD | ALLOWANCE | A-007 | LOW | PT100 RTD with thermowell
PKG-20::L018 | PKG-20 |  | L018 | MAT | PKG-20 |  | Pump Vibration Transmitters - vibration monitoring for critical pumps (6 units) | 6 | EA | 5500 | 33000 | CAD | ALLOWANCE | A-007 | LOW | Vibration transmitters for predictive maintenance
PKG-20::L019 | PKG-20 |  | L019 | MAT | PKG-20 |  | Miscellaneous Process Switches - pressure and temperature switches for alarms (12 units) | 12 | EA | 1800 | 21600 | CAD | ALLOWANCE | A-016 | LOW | Various alarm and interlock switches
PKG-20::L020 | PKG-20 |  | L020 | MAT | PKG-20 |  | Instrument Cable - multi-conductor shielded cable supply (~8000 m) | 8000 | M | 12 | 96000 | CAD | ALLOWANCE | A-008 | LOW | Multi-pair shielded instrument cable
PKG-20::L021 | PKG-20 |  | L021 | MAT | PKG-20 |  | Junction Boxes - NEMA 4X stainless steel instrument junction boxes (25 units) | 25 | EA | 2800 | 70000 | CAD | ALLOWANCE | A-009 | LOW | SS junction boxes for marine environment
PKG-20::L022 | PKG-20 |  | L022 | MAT | PKG-20 |  | Instrument Tubing and Fittings - SS tubing compression fittings manifolds | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-010 | LOW | Stainless steel instrument tubing
PKG-20::L023 | PKG-20 |  | L023 | MAT | PKG-20 |  | Instrument Supports and Mounting - brackets stands pipe mounts weather protection | 1 | LS | 28000 | 28000 | CAD | ALLOWANCE | A-017 | LOW | Field mounting hardware
PKG-20::L024 | PKG-20 |  | L024 | MAT | PKG-20 |  | Instrument Conduit and Fittings - rigid conduit flex conduit fittings | 1 | LS | 42000 | 42000 | CAD | ALLOWANCE | A-018 | LOW | Conduit system for cable protection
PKG-20::L025 | PKG-20 |  | L025 | CD | PKG-20 |  | Instrument Installation - field mounting wiring termination (106 instruments) | 106 | EA | 850 | 90100 | CAD | ALLOWANCE | A-019 | LOW | Average installation cost per instrument
PKG-20::L026 | PKG-20 |  | L026 | CD | PKG-20 |  | Instrument Cable Installation - cable pulling termination (~8000 m in tray/conduit) | 8000 | M | 18 | 144000 | CAD | ALLOWANCE | A-008 | LOW | Cable installation in tray and conduit
PKG-20::L027 | PKG-20 |  | L027 | CD | PKG-20 |  | Junction Box Installation - mounting wiring terminal block installation (25 units) | 25 | EA | 1200 | 30000 | CAD | ALLOWANCE | A-009 | LOW | Junction box field installation
PKG-20::L028 | PKG-20 |  | L028 | CD | PKG-20 |  | Instrument Conduit Installation - conduit and support installation | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-018 | LOW | Field conduit installation
PKG-20::L029 | PKG-20 |  | L029 | CD | PKG-20 |  | Instrument Tubing Installation - tubing routing and connection | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-010 | LOW | Process tubing installation
PKG-20::L030 | PKG-20 |  | L030 | CD | PKG-20 |  | Instrument Calibration - field calibration and verification (106 instruments) | 106 | EA | 280 | 29680 | CAD | ALLOWANCE | A-020 | LOW | Field calibration labor and equipment
PKG-20::L031 | PKG-20 |  | L031 | CD | PKG-20 |  | Loop Testing - point-to-point loop verification and testing (106 loops) | 106 | EA | 350 | 37100 | CAD | ALLOWANCE | A-020 | LOW | Loop check with DCS team
PKG-20::L032 | PKG-20 |  | L032 | CI | PKG-20 |  | Construction Indirects - field supervision QA/QC scaffolding temporary works (factor-based) | 1 | LS | 79000 | 79000 | CAD | PARAMETRIC | D-009 | LOW | 18% of CD base ($440k × 0.18)
PKG-20::L033 | PKG-20 |  | L033 | PM | PKG-20 |  | EPCM / Project Management - PKG-20 allocation (factor-based) | 1 | LS | 78000 | 78000 | CAD | PARAMETRIC | D-009 | MED | 6% of (CD+CI+MAT) base
PKG-20::L034 | PKG-20 |  | L034 | P | PKG-20 |  | Procurement Services - instrument vendor qualification expediting (factor-based) | 1 | LS | 13000 | 13000 | CAD | PARAMETRIC | D-009 | MED | 2% of MAT ($592k × 0.02)
PKG-20::L035 | PKG-20 |  | L035 | COM | PKG-20 |  | Commissioning - instrument commissioning loop validation system integration testing | 1 | LS | 52000 | 52000 | CAD | PARAMETRIC | D-009 | LOW | 4% of (CD+CI+MAT) base - elevated for I&C
PKG-21::L-001 | PKG-21 | DEL-21.01 | L-001 | E | PKG-21 | DEL-21.01 | Building design drawings - MCC building and operator shelters | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-003 | LOW | Includes GAs; floor plans; elevations; sections; shelter drawings
PKG-21::L-002 | PKG-21 | DEL-21.02 | L-002 | E | PKG-21 | DEL-21.02 | Building technical specifications | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-004 | LOW | Modular building spec; envelope spec; door/window spec
PKG-21::L-003 | PKG-21 | DEL-21.03 | L-003 | E | PKG-21 | DEL-21.03 | Building design calculations - structural and foundation | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-005 | LOW | NBC 2020 structural; seismic; wind; foundation calcs
PKG-21::L-004 | PKG-21 | DEL-21.04 | L-004 | E | PKG-21 | DEL-21.04 | Building data sheets and schedules | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-006 | LOW | Building system data sheet; door/window schedules
PKG-21::L-005 | PKG-21 | DEL-21.06 | L-005 | E | PKG-21 | DEL-21.06 | Building shop drawing coordination and review | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-007 | LOW | Review of fabricator/supplier shop drawings
PKG-21::L-006 | PKG-21 |  | L-006 | PM | PKG-21 |  | Project management - building package | 1 | LS | 67000 | 67000 | CAD | PARAMETRIC | D-007 | LOW | 6% of (CD+CI+MAT) per fallback model
PKG-21::L-007 | PKG-21 |  | L-007 | P | PKG-21 |  | Procurement services - building materials | 1 | LS | 14000 | 14000 | CAD | PARAMETRIC | D-008 | LOW | 2% of MAT per fallback model
PKG-21::L-008 | PKG-21 |  | L-008 | MAT | PKG-21 |  | MCC building - pre-engineered metal building supply | 600 | m2 | 650 | 390000 | CAD | ALLOWANCE | A-001 | LOW | PEMB structure; wall panels; roof panels; framing; fasteners
PKG-21::L-009 | PKG-21 |  | L-009 | MAT | PKG-21 |  | MCC building - insulated metal panel cladding upgrade | 600 | m2 | 120 | 72000 | CAD | ALLOWANCE | A-008 | LOW | R-20 wall insulation; vapor barrier; flashing; trim
PKG-21::L-010 | PKG-21 |  | L-010 | MAT | PKG-21 |  | MCC building - standing seam roof system | 600 | m2 | 85 | 51000 | CAD | ALLOWANCE | A-009 | LOW | Standing seam metal roof; R-30 insulation; underlayment
PKG-21::L-011 | PKG-21 |  | L-011 | MAT | PKG-21 |  | MCC building - doors and hardware | 7 | EA | 4500 | 32000 | CAD | ALLOWANCE | A-010 | LOW | 6 personnel doors; 1 overhead door; hardware; frames
PKG-21::L-012 | PKG-21 |  | L-012 | MAT | PKG-21 |  | MCC building - windows and glazing | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-011 | LOW | Limited industrial glazing; frames; hardware
PKG-21::L-013 | PKG-21 |  | L-013 | MAT | PKG-21 |  | MCC building - foundation materials | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-012 | LOW | Concrete slab; pile caps; reinforcing; anchor bolts
PKG-21::L-014 | PKG-21 |  | L-014 | MAT | PKG-21 |  | Operator shelters - prefabricated units | 4 | EA | 45000 | 180000 | CAD | ALLOWANCE | A-002 | LOW | Insulated prefab shelters; 15 m2 each; includes heating provisions
PKG-21::L-015 | PKG-21 |  | L-015 | MAT | PKG-21 |  | Operator shelter - foundation materials | 4 | EA | 8000 | 32000 | CAD | ALLOWANCE | A-013 | LOW | Concrete pads/piles; anchor bolts
PKG-21::L-016 | PKG-21 |  | L-016 | MAT | PKG-21 |  | Protective coatings and corrosion protection | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-014 | LOW | Marine environment protection; galvanizing allowance
PKG-21::L-017 | PKG-21 |  | L-017 | CD | PKG-21 |  | MCC building - foundation installation | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-015 | LOW | Pile driving or spread footing installation; slab pour
PKG-21::L-018 | PKG-21 |  | L-018 | CD | PKG-21 |  | MCC building - PEMB erection | 600 | m2 | 180 | 108000 | CAD | ALLOWANCE | A-016 | LOW | Structural erection; crane; rigging; crew labor
PKG-21::L-019 | PKG-21 |  | L-019 | CD | PKG-21 |  | MCC building - envelope installation | 600 | m2 | 95 | 57000 | CAD | ALLOWANCE | A-017 | LOW | Cladding; roofing; flashing; sealants installation
PKG-21::L-020 | PKG-21 |  | L-020 | CD | PKG-21 |  | MCC building - door and window installation | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-018 | LOW | Door hanging; hardware; window installation; sealing
PKG-21::L-021 | PKG-21 |  | L-021 | CD | PKG-21 |  | Operator shelter - installation | 4 | EA | 12000 | 48000 | CAD | ALLOWANCE | A-019 | LOW | Shelter setting; anchor; connections
PKG-21::L-022 | PKG-21 |  | L-022 | CD | PKG-21 |  | Operator shelter - foundation installation | 4 | EA | 6000 | 24000 | CAD | ALLOWANCE | A-020 | LOW | Concrete work; anchor bolt setting
PKG-21::L-023 | PKG-21 |  | L-023 | CD | PKG-21 |  | Building finishing and punch list | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-021 | LOW | Touch-up; adjustments; minor corrections
PKG-21::L-024 | PKG-21 |  | L-024 | CI | PKG-21 |  | Construction indirects - building package | 1 | LS | 62000 | 62000 | CAD | PARAMETRIC | D-009 | LOW | 18% of CD per fallback model; supervision; temp facilities
PKG-21::L-025 | PKG-21 | DEL-21.05 | L-025 | COM | PKG-21 | DEL-21.05 | Building inspection and test records | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-022 | LOW | QA/QC inspections; envelope testing; code inspections
PKG-21::L-026 | PKG-21 |  | L-026 | COM | PKG-21 |  | Building commissioning support | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-023 | LOW | Commissioning coordination; punch list resolution
PKG-22::L-001 | PKG-22 | DEL-22.01 | L-001 | E | PKG-22 | DEL-22.01 | MEP engineering design - Building MEP Design Drawing Set | 1 | LS | 48000 | 48000 | CAD | ALLOWANCE | A-006 | LOW | HVAC layout; plumbing layout; interior electrical layout; fire suppression layout; 8-15 sheets estimated; 150-250 hours @ $140-175/hr blended
PKG-22::L-002 | PKG-22 | DEL-22.02 | L-002 | E | PKG-22 | DEL-22.02 | MEP engineering design - Building MEP Technical Specification | 1 | LS | 28000 | 28000 | CAD | ALLOWANCE | A-006 | LOW | HVAC specification; building plumbing specification; fire suppression specification; 3 spec sections; 80-120 hours
PKG-22::L-003 | PKG-22 | DEL-22.03 | L-003 | E | PKG-22 | DEL-22.03 | MEP engineering design - Building MEP Design Calculations | 1 | LS | 22000 | 22000 | CAD | ALLOWANCE | A-006 | LOW | HVAC load calculations; plumbing sizing; fire sprinkler hydraulics; 100-150 hours
PKG-22::L-004 | PKG-22 | DEL-22.04 | L-004 | E | PKG-22 | DEL-22.04 | MEP engineering design - Building MEP Data Sheet Package | 1 | LS | 10000 | 10000 | CAD | ALLOWANCE | A-006 | LOW | HVAC unit data sheet; fire suppression system data sheet; equipment parameters; 60-100 hours
PKG-22::L-005 | PKG-22 | DEL-22.06 | L-005 | E | PKG-22 | DEL-22.06 | MEP engineering design - Building MEP Shop Design Drawing Set review | 1 | LS | 16000 | 16000 | CAD | ALLOWANCE | A-006 + A-021 | LOW | Shop drawing review for HVAC equipment; sprinkler system; major plumbing equipment; 80-120 hours review effort
PKG-22::L-006 | PKG-22 | DEL-22.01 | L-006 | MAT | PKG-22 | DEL-22.01 | HVAC equipment and controls | 1 | LS | 295000 | 295000 | CAD | ALLOWANCE | A-001 + A-007 + A-014 | LOW | Packaged rooftop units or split systems (45-75 tons total cooling; 250-400 MBH heating); ductwork (200-350 LM); diffusers/grilles (40-60 units); insulation; controls; BAS integration; 300 m² MCC building
PKG-22::L-007 | PKG-22 | DEL-22.01 | L-007 | MAT | PKG-22 | DEL-22.01 | Plumbing fixtures and materials | 1 | LS | 90000 | 90000 | CAD | ALLOWANCE | A-002 + A-008 | LOW | Fixtures (8-12 total: WCs; lavatories; sinks; safety shower/eyewash); domestic water piping (80-120 LM copper/PEX); sanitary drainage (60-100 LM PVC/ABS); water heater (150-300L); backflow preventer; insulation
PKG-22::L-008 | PKG-22 | DEL-22.01 | L-008 | MAT | PKG-22 | DEL-22.01 | Fire suppression system materials | 1 | LS | 110000 | 110000 | CAD | ALLOWANCE | A-003 + A-009 + A-016 | LOW | Automatic wet-pipe sprinkler system per NFPA 13 Light Hazard; sprinkler heads (40-60 units); pipe DN25-DN100 (150-250 LM); alarm valve; trim; flow/tamper switches; fire alarm interface; test connection; connection to site fire water loop; 300 m² coverage
PKG-22::L-009 | PKG-22 | DEL-22.01 | L-009 | MAT | PKG-22 | DEL-22.01 | Interior electrical materials | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-004 + A-015 | LOW | LED lighting fixtures (30-50 units); receptacles (15-25 units); small power panels (2-3 units); emergency lighting (8-12 units); wiring and conduit; interior lighting controls; 12-18 kW connected load for building services
PKG-22::L-010 | PKG-22 | DEL-22.01 | L-010 | MAT | PKG-22 | DEL-22.01 | Interior finishes materials | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-005 | LOW | Flooring (sealed concrete or epoxy for 300 m²); wall finishes (painted drywall or metal panels; 150-200 m² wall area); ceilings (suspended acoustic tile or exposed for 50-80% coverage); trim and accessories; industrial grade finishes
PKG-22::L-011 | PKG-22 | DEL-22.01 | L-011 | CD | PKG-22 | DEL-22.01 | HVAC installation | 1 | LS | 195000 | 195000 | CAD | ALLOWANCE | A-001 + A-010 + A-011 + A-012 | LOW | Equipment placement and rigging; ductwork fabrication and installation; diffuser/grille installation; insulation; piping connections; control wiring; startup support; 30-50 hours/ton productivity; labor/equipment per A-010/A-011
PKG-22::L-012 | PKG-22 | DEL-22.01 | L-012 | CD | PKG-22 | DEL-22.01 | Plumbing installation | 1 | LS | 125000 | 125000 | CAD | ALLOWANCE | A-002 + A-010 + A-011 + A-012 | LOW | Fixture installation; domestic water piping (80-120 LM); sanitary drainage (60-100 LM); water heater installation; backflow preventer installation; pressure testing; 2-4 hours/fixture + 0.5-1.0 hours/m pipe productivity
PKG-22::L-013 | PKG-22 | DEL-22.01 | L-013 | CD | PKG-22 | DEL-22.01 | Fire suppression installation | 1 | LS | 115000 | 115000 | CAD | ALLOWANCE | A-003 + A-010 + A-011 + A-012 | LOW | Sprinkler pipe installation (150-250 LM); sprinkler head installation (40-60 heads); alarm valve and trim installation; flow/tamper switch installation; fire alarm interface; hydrostatic testing; main drain test; 0.8-1.2 hours/head + 0.4-0.6 hours/m pipe productivity
PKG-22::L-014 | PKG-22 | DEL-22.01 | L-014 | CD | PKG-22 | DEL-22.01 | Interior electrical installation | 1 | LS | 105000 | 105000 | CAD | ALLOWANCE | A-004 + A-010 + A-011 + A-012 | LOW | Lighting fixture installation (30-50 units); receptacle installation (15-25 units); panel installation (2-3 units); emergency lighting installation; conduit and wiring; testing; 0.3-0.5 hours/fixture productivity
PKG-22::L-015 | PKG-22 | DEL-22.01 | L-015 | CD | PKG-22 | DEL-22.01 | Interior finishes installation | 1 | LS | 92000 | 92000 | CAD | ALLOWANCE | A-005 + A-010 + A-011 | LOW | Flooring installation (300 m² sealed concrete or epoxy); wall finish installation (150-200 m² drywall or panels); ceiling installation (suspended tile or exposed finish); trim installation; surface preparation; cleanup
PKG-22::L-016 | PKG-22 |  | L-016 | CI | PKG-22 |  | Construction Indirects (factor-based) | 1 | LS | 114000 | 114000 | CAD | PARAMETRIC | D-009 (factor=0.18) | MEDIUM | CI = 0.18 × CD ($632k); includes site supervision; temporary facilities; HSE; QA/QC field inspection; construction management; small tools; per fallback typical model
PKG-22::L-017 | PKG-22 |  | L-017 | P | PKG-22 |  | Procurement Services (factor-based) | 1 | LS | 14000 | 14000 | CAD | PARAMETRIC | D-009 (factor=0.02) | MEDIUM | P = 0.02 × MAT ($675k); includes material sourcing; PO processing; vendor coordination; expediting; receiving inspection; material documentation; per fallback typical model
PKG-22::L-018 | PKG-22 |  | L-018 | PM | PKG-22 |  | EPCM/Project Management (factor-based) | 1 | LS | 85000 | 85000 | CAD | PARAMETRIC | D-009 (factor=0.06) | MEDIUM | PM = 0.06 × (CD + CI + MAT) ($1421k); includes project management; engineering management; schedule/cost control; contract administration; stakeholder coordination; per fallback typical model
PKG-22::L-019 | PKG-22 |  | L-019 | COM | PKG-22 |  | Commissioning (factor-based) | 1 | LS | 43000 | 43000 | CAD | PARAMETRIC | D-009 + A-013 (factor=0.03) | MEDIUM | COM = 0.03 × (CD + CI + MAT) ($1421k); includes HVAC TAB; plumbing pressure testing; fire sprinkler hydrostatic/flow testing per NFPA 13; electrical testing; functional performance testing; owner training; per fallback typical model
PKG-23::L-001 | PKG-23 | DEL-23.01 | L-001 | E | PKG-23 | DEL-23.01 | Fire protection engineering design - Fire Protection Design Drawing Set | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-012 | LOW | Fire water loop layout; hydrant locations; fire alarm system drawings; foam system layouts; typical 8-12 sheets
PKG-23::L-002 | PKG-23 | DEL-23.02 | L-002 | E | PKG-23 | DEL-23.02 | Fire protection engineering design - Fire Protection Technical Specification | 1 | LS | 40000 | 40000 | CAD | ALLOWANCE | A-012 | LOW | Fire water piping spec; fire hydrant spec; fire alarm spec; foam system spec; NFPA 30/24/72/11 compliance
PKG-23::L-003 | PKG-23 | DEL-23.03 | L-003 | E | PKG-23 | DEL-23.03 | Fire protection engineering design - Fire Protection Design Calculations | 1 | LS | 50000 | 50000 | CAD | ALLOWANCE | A-012 | LOW | Fire water demand calcs per NFPA 30; hydraulic calcs per NFPA 24; foam system sizing per NFPA 11/16
PKG-23::L-004 | PKG-23 | DEL-23.04 | L-004 | E | PKG-23 | DEL-23.04 | Fire protection engineering design - Fire Protection Data Sheet Package | 1 | LS | 30000 | 30000 | CAD | ALLOWANCE | A-012 | LOW | Fire hydrant data sheets (8-12); fire alarm panel data sheet; foam equipment data sheets
PKG-23::L-005 | PKG-23 | DEL-23.01 | L-005 | MAT | PKG-23 | DEL-23.01 | Fire water piping - underground ductile iron | 1 | LS | 165000 | 165000 | CAD | ALLOWANCE | A-001 + A-009 | LOW | Ductile iron pipe DN150-DN300 (500-800 LM) with cement-mortar lining; polyethylene wrap; fittings; valve boxes; per AWWA C151
PKG-23::L-006 | PKG-23 | DEL-23.01 | L-006 | MAT | PKG-23 | DEL-23.01 | Fire water piping - above-ground steel | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-001 + A-009 | LOW | Steel pipe Schedule 40 DN100-DN200 (200-400 LM); fittings; supports; fire protection paint; per ASTM A53
PKG-23::L-007 | PKG-23 | DEL-23.04 | L-007 | MAT | PKG-23 | DEL-23.04 | Fire hydrants and accessories | 1 | LS | 120000 | 120000 | CAD | ALLOWANCE | A-002 + A-009 | LOW | Dry-barrel fire hydrants (8-12 units) rated -40C; 2x2.5in + 1x4.5in outlets; valve boxes; FDC (2 units); hose bibs
PKG-23::L-008 | PKG-23 | DEL-23.01 | L-008 | MAT | PKG-23 | DEL-23.01 | Fire water valves and fittings | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-003 + A-009 | LOW | Gate valves OS&Y (12-18); PIV valves (4-6); check valves (2-4); valve markers; fittings per AWWA C509
PKG-23::L-009 | PKG-23 | DEL-23.04 | L-009 | MAT | PKG-23 | DEL-23.04 | Fire alarm control panel and equipment | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-004 + A-010 | LOW | Addressable FACP per ULC-S527; network interface for DCS integration; battery backup; annunciator panels
PKG-23::L-010 | PKG-23 | DEL-23.04 | L-010 | MAT | PKG-23 | DEL-23.04 | Fire detection devices | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-005 + A-010 | LOW | Heat detectors (40-60); flame detectors UV/IR (15-25); smoke detectors (10-20); manual pull stations (20-30); per ULC standards
PKG-23::L-011 | PKG-23 | DEL-23.01 | L-011 | MAT | PKG-23 | DEL-23.01 | Fire alarm notification and wiring | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-005 + A-010 | LOW | Horn/strobes (40-60 devices); fire alarm cable per ULC-S139; conduit; junction boxes; weatherproof enclosures
PKG-23::L-012 | PKG-23 | DEL-23.04 | L-012 | MAT | PKG-23 | DEL-23.04 | Foam concentrate storage and proportioning | 1 | LS | 185000 | 185000 | CAD | ALLOWANCE | A-006 + A-011 | LOW | Foam concentrate tank (2000-4000 gal); bladder tank proportioner or balanced pressure system; foam concentrate (AR-AFFF 3%)
PKG-23::L-013 | PKG-23 | DEL-23.04 | L-013 | MAT | PKG-23 | DEL-23.04 | Tank foam discharge systems | 1 | LS | 145000 | 145000 | CAD | ALLOWANCE | A-007 + A-011 | LOW | Foam chambers or foam makers for 3 x 15000 MT tanks; foam piping to tanks; control valves; per NFPA 11
PKG-23::L-014 | PKG-23 | DEL-23.04 | L-014 | MAT | PKG-23 | DEL-23.04 | Marine loading foam system | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-008 + A-011 | LOW | Foam monitors or nozzles for marine loading platform; foam piping; quick-disconnect fittings; control valves
PKG-23::L-015 | PKG-23 | DEL-23.01 | L-015 | CD | PKG-23 | DEL-23.01 | Fire water loop installation | 1 | LS | 300000 | 300000 | CAD | ALLOWANCE | A-013 + A-014 | LOW | Trench excavation (700-1200 LM); pipe laying and jointing; valve installation; thrust blocks; backfill; coordination with PKG-03
PKG-23::L-016 | PKG-23 | DEL-23.04 | L-016 | CD | PKG-23 | DEL-23.04 | Fire hydrant and FDC installation | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-015 | LOW | Hydrant installation (8-12 units); concrete pads; valve box installation; FDC installation; marking posts
PKG-23::L-017 | PKG-23 | DEL-23.01 | L-017 | CD | PKG-23 | DEL-23.01 | Fire alarm system installation | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-016 | LOW | FACP installation; detector mounting; device wiring; conduit installation; terminations; programming; coordination with PKG-19
PKG-23::L-018 | PKG-23 | DEL-23.04 | L-018 | CD | PKG-23 | DEL-23.04 | Foam system installation | 1 | LS | 150000 | 150000 | CAD | ALLOWANCE | A-017 | LOW | Foam tank installation; proportioner installation; foam piping to tanks and marine loading; foam chamber mounting; controls
PKG-23::L-019 | PKG-23 |  | L-019 | CI | PKG-23 |  | Construction Indirects (factor-based) | 1 | LS | 108000 | 108000 | CAD | PARAMETRIC | D-009 (factor=0.18) | MEDIUM | CI = 0.18 x CD ($600k); includes site supervision; temporary facilities; HSE; QA/QC field inspection; per fallback typical model
PKG-23::L-020 | PKG-23 |  | L-020 | P | PKG-23 |  | Procurement Services (factor-based) | 1 | LS | 21000 | 21000 | CAD | PARAMETRIC | D-009 (factor=0.02) | MEDIUM | P = 0.02 x MAT ($1065k); includes fire protection equipment sourcing; vendor coordination; expediting; per fallback typical model
PKG-23::L-021 | PKG-23 |  | L-021 | PM | PKG-23 |  | EPCM/Project Management (factor-based) | 1 | LS | 106000 | 106000 | CAD | PARAMETRIC | D-009 (factor=0.06) | MEDIUM | PM = 0.06 x (CD + CI + MAT) ($1773k); includes project management; engineering management; coordination; per fallback typical model
PKG-23::L-022 | PKG-23 | DEL-23.05 | L-022 | COM | PKG-23 | DEL-23.05 | Commissioning (factor-based) | 1 | LS | 53000 | 53000 | CAD | PARAMETRIC | D-009 (factor=0.03) | MEDIUM | COM = 0.03 x (CD + CI + MAT) ($1773k); includes hydrostatic testing; flow testing; fire alarm testing; foam system testing; per DEL-23.05 scope
PKG-24::L-001 | PKG-24 | DEL-24.01 | L-001 | E | PKG-24 | DEL-24.01 | Security systems engineering design - Design Drawing Set | 1 | LS | 48000 | 48000 | CAD | ALLOWANCE | A-001 | LOW | CCTV layout; camera coverage drawings; access control layout; system architecture diagram; typical mounting details; 600-800 hours @ $140-175/hr blended (senior designer + CAD technician)
PKG-24::L-002 | PKG-24 | DEL-24.02 | L-002 | E | PKG-24 | DEL-24.02 | Security systems engineering design - Technical Specification | 1 | LS | 32000 | 32000 | CAD | ALLOWANCE | A-001 | LOW | CCTV specification; access control specification; network infrastructure requirements; testing/commissioning requirements; 400-500 hours @ $140-175/hr blended
PKG-24::L-003 | PKG-24 | DEL-24.03 | L-003 | E | PKG-24 | DEL-24.03 | Security systems engineering - Data Sheet Package | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-001 | LOW | Equipment submittal review; compliance verification; datasheet compilation; 200-250 hours @ $140-175/hr blended
PKG-24::L-004 | PKG-24 | DEL-24.04 | L-004 | E | PKG-24 | DEL-24.04 | Security systems engineering - Installation & Test Records support | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-001 | LOW | Coverage verification; SAT witness; commissioning support; deficiency review; as-built markup review; 300-350 hours @ $140-175/hr blended
PKG-24::L-005 | PKG-24 | DEL-24.03 | L-005 | MAT | PKG-24 | DEL-24.03 | CCTV fixed cameras with mounts | 18 | EA | 3500 | 63000 | CAD | ALLOWANCE | A-002 | LOW | IP cameras 2-4MP resolution; outdoor IP66/IP67 rated; marine-grade housings; IR illumination; mounting brackets; typical unit cost $2500-4500 for industrial-grade outdoor cameras
PKG-24::L-006 | PKG-24 | DEL-24.03 | L-006 | MAT | PKG-24 | DEL-24.03 | CCTV PTZ cameras with mounts | 3 | EA | 12000 | 36000 | CAD | ALLOWANCE | A-003 | LOW | IP PTZ cameras 2-4MP; 30x optical zoom; outdoor IP66/IP67 rated; marine-grade; heavy-duty pan/tilt; mounting brackets; typical unit cost $9000-15000
PKG-24::L-007 | PKG-24 | DEL-24.03 | L-007 | MAT | PKG-24 | DEL-24.03 | Network Video Recorder (NVR) system | 2 | EA | 15000 | 30000 | CAD | ALLOWANCE | A-004 | LOW | NVR 32-64 channel; 30-90 day retention @ 4MP; RAID storage; redundant dual NVR configuration; rack-mount; typical unit cost $12000-18000 per NVR
PKG-24::L-008 | PKG-24 | DEL-24.03 | L-008 | MAT | PKG-24 | DEL-24.03 | Video Management System (VMS) software and licensing | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-005 | LOW | VMS software platform; 5-10 user licenses; ONVIF-compliant; alarm management; integration APIs; Terminal interface capability per DEC-05
PKG-24::L-009 | PKG-24 | DEL-24.03 | L-009 | MAT | PKG-24 | DEL-24.03 | Access control card readers | 12 | EA | 1200 | 14400 | CAD | ALLOWANCE | A-006 | LOW | Proximity or smart card readers (125kHz/13.56MHz); outdoor IP65 rated; IK08 vandal resistant; OSDP or Wiegand protocol; typical unit cost $800-1500
PKG-24::L-010 | PKG-24 | DEL-24.03 | L-010 | MAT | PKG-24 | DEL-24.03 | Access control controllers and panels | 2 | EA | 8000 | 16000 | CAD | ALLOWANCE | A-007 | LOW | Network-based access control panels; 8-16 doors per panel; TCP/IP communication; battery backup; fail-safe/fail-secure configurable; typical unit cost $6000-10000
PKG-24::L-011 | PKG-24 | DEL-24.03 | L-011 | MAT | PKG-24 | DEL-24.03 | Access control software and licensing | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | A-008 | LOW | Access control management software; 3-5 user licenses; cardholder management; audit trails; Terminal integration per DEC-05; reporting features
PKG-24::L-012 | PKG-24 | DEL-24.03 | L-012 | MAT | PKG-24 | DEL-24.03 | Door hardware - Electric strikes and magnetic locks | 12 | EA | 650 | 7800 | CAD | ALLOWANCE | A-009 | LOW | Electric strikes or mag locks for 12 controlled doors/gates; fail-safe/fail-secure per design; stainless steel; typical unit cost $450-850
PKG-24::L-013 | PKG-24 | DEL-24.03 | L-013 | MAT | PKG-24 | DEL-24.03 | Door hardware - REX devices and door position switches | 12 | EA | 180 | 2160 | CAD | ALLOWANCE | A-009 | LOW | Request-to-exit motion sensors or buttons; door position switches; 1 set per controlled door; typical unit cost $120-240 per set
PKG-24::L-014 | PKG-24 | DEL-24.03 | L-014 | MAT | PKG-24 | DEL-24.03 | Network switches (PoE) and fiber equipment | 4 | EA | 4500 | 18000 | CAD | ALLOWANCE | A-010 | LOW | Managed PoE+ switches (24-48 port); fiber SFP modules; patch panels; typical unit cost $3500-5500 per switch with accessories
PKG-24::L-015 | PKG-24 | DEL-24.03 | L-015 | MAT | PKG-24 | DEL-24.03 | UPS and power supplies | 3 | EA | 2800 | 8400 | CAD | ALLOWANCE | A-011 | LOW | UPS units for equipment rooms and critical controllers; 4-8 hour battery backup; rack-mount or standalone; typical unit cost $2000-3500
PKG-24::L-016 | PKG-24 | DEL-24.03 | L-016 | MAT | PKG-24 | DEL-24.03 | Cabling and conduit materials | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-012 | LOW | Cat6A cabling (2000-3000m); single-mode fiber (500-800m); outdoor-rated; conduit and fittings; cable trays; pull boxes; labels; typical bulk cabling materials for 21 cameras + 12 readers + network infrastructure
PKG-24::L-017 | PKG-24 | DEL-24.03 | L-017 | MAT | PKG-24 | DEL-24.03 | Camera poles and mounting structures | 8 | EA | 3200 | 25600 | CAD | ALLOWANCE | A-013 | LOW | Dedicated camera poles 4-8m height for areas without building/structure mounting; includes foundation; typical unit cost $2500-4000 per pole with foundation and installation
PKG-24::L-018 | PKG-24 | DEL-24.04 | L-018 | CD | PKG-24 | DEL-24.04 | CCTV equipment installation | 21 | EA | 850 | 17850 | CAD | ALLOWANCE | A-014 + A-020 | LOW | Fixed and PTZ camera installation; mounting; cable pulling/termination; aiming; configuration; typical labor 6-12 hours per camera @ $120-150/hr loaded labor rate
PKG-24::L-019 | PKG-24 | DEL-24.04 | L-019 | CD | PKG-24 | DEL-24.04 | Access control equipment installation | 12 | EA | 1100 | 13200 | CAD | ALLOWANCE | A-015 + A-020 | LOW | Card reader installation; controller installation; door hardware installation; cable pulling/termination; configuration; typical labor 8-14 hours per door @ $120-150/hr loaded labor rate
PKG-24::L-020 | PKG-24 | DEL-24.04 | L-020 | CD | PKG-24 | DEL-24.04 | Network and central equipment installation | 1 | LS | 42000 | 42000 | CAD | ALLOWANCE | A-016 + A-020 | LOW | NVR/VMS server installation and configuration; network switch installation and configuration; fiber terminations; rack installation; UPS installation; typical 250-350 hours @ $120-150/hr loaded labor rate
PKG-24::L-021 | PKG-24 | DEL-24.04 | L-021 | CD | PKG-24 | DEL-24.04 | Underground conduit installation | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-017 | LOW | Trenching or boring for underground conduit routing; conduit installation; pull boxes; backfill; coordinate with PKG-03; approximately 400-700 LM conduit runs; includes excavation/backfill labor
PKG-24::L-022 | PKG-24 | DEL-24.04 | L-022 | CD | PKG-24 | DEL-24.04 | Camera pole foundations and installation | 8 | EA | 1400 | 11200 | CAD | ALLOWANCE | A-018 | LOW | Concrete foundations for camera poles; pole erection; grounding; typical labor 10-16 hours per pole @ $120-150/hr loaded labor + concrete materials labor
PKG-24::L-023 | PKG-24 | DEL-24.04 | L-023 | CD | PKG-24 | DEL-24.04 | System testing and commissioning labor | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-019 + A-021 | LOW | Cable testing; camera functional testing; access control functional testing; coverage verification; integration testing; SAT support; commissioning; Terminal integration coordination per DEC-05; typical 400-550 hours @ $120-150/hr loaded labor rate
PKG-24::L-024 | PKG-24 |  | L-024 | CI | PKG-24 |  | Construction Indirects (factor-based) | 1 | LS | 44000 | 44000 | CAD | PARAMETRIC | D-009 (factor=0.18) | MEDIUM | CI = 0.18 × CD ($244k); includes field supervision; temporary facilities allocation; HSE; QA/QC field inspection; construction management; small tools; per fallback typical model
PKG-24::L-025 | PKG-24 |  | L-025 | P | PKG-24 |  | Procurement Services (factor-based) | 1 | LS | 7000 | 7000 | CAD | PARAMETRIC | D-009 (factor=0.02) | MEDIUM | P = 0.02 × MAT ($359k); includes equipment sourcing; vendor coordination; PO processing; expediting; receiving inspection; documentation management; per fallback typical model
PKG-24::L-026 | PKG-24 |  | L-026 | PM | PKG-24 |  | EPCM/Project Management (factor-based) | 1 | LS | 37000 | 37000 | CAD | PARAMETRIC | D-009 (factor=0.06) | MEDIUM | PM = 0.06 × (CD + CI + MAT) ($647k); includes project management allocation; engineering management; schedule/cost control; contract administration; Terminal coordination; per fallback typical model
PKG-24::L-027 | PKG-24 |  | L-027 | COM | PKG-24 |  | Commissioning Services (factor-based) | 1 | LS | 19000 | 19000 | CAD | PARAMETRIC | D-009 (factor=0.03) | MEDIUM | COM = 0.03 × (CD + CI + MAT) ($647k); includes commissioning planning; integrated system testing; performance verification; Terminal integration verification per DEC-05; deficiency closeout; training support (PKG-35); handover; per fallback typical model
PKG-25::2501-01 | PKG-25 | DEL-25.01 | 2501-01 | MAT | PKG-25 | DEL-25.01 | Fiber optic cabling system (single-mode and multi-mode; 800-1500 LM total; fiber counts 12-24; termination and splicing) | 1 | LS | 80000 | 80000 | CAD | ALLOWANCE | A-2501 | LOW | OS2 single-mode for backbone (300-600 LM); OM3/OM4 multi-mode for distribution (500-900 LM); includes cables + connectors + splicing; integrated materials + labor allowance
PKG-25::2501-02 | PKG-25 | DEL-25.01 | 2501-02 | CD | PKG-25 | DEL-25.01 | Fiber optic cable installation and testing (pulling; termination; splicing; OTDR testing) | 1 | LS | 40000 | 40000 | CAD | ALLOWANCE | A-2501 + A-2509 | LOW | Installation labor for fiber infrastructure; includes pathway coordination per DEL-25.01; testing per DEL-25.04
PKG-25::2502-01 | PKG-25 | DEL-25.01 | 2502-01 | MAT | PKG-25 | DEL-25.01 | Structured copper cabling system (Cat 6 or Cat 6A; 1500-2500 LM horizontal; 50-100 outlets) | 1 | LS | 50000 | 50000 | CAD | ALLOWANCE | A-2502 | LOW | Cat 6/6A UTP or F/UTP per DEL-25.02; includes horizontal cables + outlet jacks + backbone cables; integrated materials + labor allowance
PKG-25::2502-02 | PKG-25 | DEL-25.01 | 2502-02 | CD | PKG-25 | DEL-25.01 | Structured copper cable installation and testing (pulling; termination; certification testing) | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-2502 + A-2510 | LOW | Installation labor for copper structured cabling; termination at outlets and patch panels; certification per TIA-568; testing per DEL-25.04
PKG-25::2503-01 | PKG-25 | DEL-25.03 | 2503-01 | MAT | PKG-25 | DEL-25.03 | Network switches and active equipment (1 core switch + 3-7 access switches; 150-300 total ports) | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-2503 + A-2511 | LOW | Managed switches; 24-48 ports each; VLAN/QoS capable; fiber uplinks; PoE capability TBD (may add 20-40%); includes SFP transceivers
PKG-25::2504-01 | PKG-25 | DEL-25.01 | 2504-01 | MAT | PKG-25 | DEL-25.01 | Patch panels (fiber and copper; 8-15 panels total; 24-48 ports each; rack-mounted) | 1 | LS | 30000 | 30000 | CAD | ALLOWANCE | A-2504 + A-2512 | LOW | Fiber patch panels (LC or SC connectors per DEL-25.02); copper patch panels (Cat 6/6A); includes patch cords; 19-inch rack-mount per EIA-310-D
PKG-25::2505-01 | PKG-25 | DEL-25.01 | 2505-01 | MAT | PKG-25 | DEL-25.01 | Cable management and infrastructure (J-hooks; labels; grounding; firestopping) | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-2505 + A-2513 | MED | Cable support hardware; TIA-606 labeling; TIA-607 grounding/bonding; firestopping at penetrations; pathway coordination with PKG-17
PKG-25::2506-01 | PKG-25 | DEL-25.01 | 2506-01 | E | PKG-25 | DEL-25.01 | Engineering design (drawings; specifications; data sheets; test procedures; 600-800 hours) | 1 | LS | 75000 | 75000 | CAD | ALLOWANCE | A-2506 | MED | DEL-25.01 (300-400 hrs); DEL-25.02 (100-150 hrs); DEL-25.03 (100-150 hrs); DEL-25.04 (100-100 hrs); blended rate $125-150/hr
PKG-25::2507-01 | PKG-25 | DEL-25.01 | 2507-01 | CD | PKG-25 | DEL-25.01 | Network equipment installation and mounting (rack installation; cable dressing; equipment configuration) | 1 | LS | 40000 | 40000 | CAD | ALLOWANCE | A-2503 | LOW | Switch installation in racks; initial configuration; cable management; coordination with PKG-17 for power; PKG-22 for HVAC
PKG-25::2508-01 | PKG-25 | DEL-25.01 | 2508-01 | CD | PKG-25 | DEL-25.01 | Equipment room and TR infrastructure setup (rack setup; grounding; cable management) | 1 | LS | 30000 | 30000 | CAD | ALLOWANCE | A-2515 | LOW | Equipment room (ER) and telecommunications rooms (TRs) infrastructure; coordinate with PKG-21 layouts and PKG-22 HVAC
PKG-25::2509-01 | PKG-25 | DEL-25.01 | 2509-01 | CD | PKG-25 | DEL-25.01 | Fiber splicing and termination labor (field termination; splice closures; testing) | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-2509 | LOW | Specialized fiber splicing labor; connector termination; splice enclosures; coordinate with outdoor fiber runs
PKG-25::2510-01 | PKG-25 |  | 2510-01 | CI | PKG-25 |  | Construction indirects (field supervision; QA/QC; HSE; coordination) | 1 | LS | 28800 | 28800 | CAD | PARAMETRIC | D-2506 (18% of CD=$160k) | MED | Factor-based CI = 18% × CD; includes field superintendent; QA/QC; HSE; terminal coordination per A-2514
PKG-25::2511-01 | PKG-25 |  | 2511-01 | P | PKG-25 |  | Procurement services (vendor coordination; expediting; inspection) | 1 | LS | 6900 | 6900 | CAD | PARAMETRIC | D-2506 (2% of MAT=$345k) | MED | Factor-based P = 2% × MAT; vendor quote solicitation; equipment inspection; delivery coordination
PKG-25::2512-01 | PKG-25 |  | 2512-01 | PM | PKG-25 |  | Project management (EPCM; design coordination; document control) | 1 | LS | 32028 | 32028 | CAD | PARAMETRIC | D-2506 (6% of CD+CI+MAT=$533.8k) | MED | Factor-based PM = 6% × (CD+CI+MAT); EPCM allocation; interdisciplinary coordination; document management
PKG-25::2517-01 | PKG-25 | DEL-25.04 | 2517-01 | COM | PKG-25 | DEL-25.04 | Commissioning and integration testing (network testing; integration with PKG-19; performance verification) | 1 | LS | 16014 | 16014 | CAD | PARAMETRIC | D-2506 (3% of CD+CI+MAT=$533.8k) + A-2517 | MED | Factor-based COM = 3% × (CD+CI+MAT); fiber/copper testing per DEL-25.04; network commissioning; PKG-19 integration per A-2516
PKG-25::2518-01 | PKG-25 | DEL-25.01 | 2518-01 | MAT | PKG-25 | DEL-25.01 | Spare capacity allowance (spare fibers; spare ports; pathway capacity) | 1 | LS | 5000 | 5000 | CAD | ALLOWANCE | A-2518 | MED | Future expansion capacity per OBJ-8; embedded in cable/panel sizing; no separate equipment; 20-40% spare capacity in infrastructure
PKG-26::L2601 | PKG-26 | DEL-26.01 | L2601 | E | PKG-26 | DEL-26.01 | Coating Technical Specification - specification writing (tank internal/external structural steel marine field painting specs) | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-2601 | LOW | ~100 hours at $250/hr; includes performance requirements materials workmanship for 5 coating application types
PKG-26::L2602 | PKG-26 | DEL-26.02 | L2602 | E | PKG-26 | DEL-26.02 | Coating Procedures - procedure development (surface prep application inspection testing procedures) | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-2602 | LOW | ~80 hours at $250/hr; includes surface preparation procedures coating application procedures field painting procedures marine application procedures
PKG-26::L2603 | PKG-26 | DEL-26.03 | L2603 | E | PKG-26 | DEL-26.03 | Coating Data Sheet Package - compilation of manufacturer data sheets FDA/NSF certificates application guides SDS | 1 | LS | 10000 | 10000 | CAD | ALLOWANCE | A-2603 | LOW | ~40 hours at $250/hr for data sheet compilation and organization by application type
PKG-26::L2604 | PKG-26 | DEL-26.04 | L2604 | E | PKG-26 | DEL-26.04 | Coating Installation & Test Records - QA/QC documentation templates record preparation (surface prep DFT holiday detection adhesion records) | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-2604 | LOW | ~60 hours at $250/hr for documentation templates and record closeout preparation
PKG-26::L2605 | PKG-26 |  | L2605 | E | PKG-26 |  | Coating Engineering Coordination - interdisciplinary coordination with PKG-06 PKG-08 PKG-13 PKG-27 PKG-30 PKG-33 | 1 | LS | 22000 | 22000 | CAD | ALLOWANCE | A-2605 | LOW | ~90 hours at $245/hr for interface coordination; critical for shop/field split marine zones food-grade requirements
PKG-26::L2606 | PKG-26 |  | L2606 | MAT | PKG-26 |  | Tank Internal Coating System - food-grade epoxy lining FDA/NSF compliant (~11000 m² supply and application) | 11000 | m2 | 50 | 550000 | 550000 | CAD | ALLOWANCE | A-2606 | MED
PKG-26::L2607 | PKG-26 |  | L2607 | MAT | PKG-26 |  | Tank External Coating System - multi-coat atmospheric protection (~9000 m² supply and application) | 9000 | m2 | 20 | 180000 | 180000 | CAD | ALLOWANCE | A-2607 | MED
PKG-26::L2608 | PKG-26 |  | L2608 | MAT | PKG-26 |  | Structural Steel Field Painting - field painting over galvanized steel (~3750 m² derived from 150 tonnes) | 3750 | m2 | 15 | 56250 | 56250 | CAD | ALLOWANCE | A-2608 | LOW
PKG-26::L2609 | PKG-26 |  | L2609 | MAT | PKG-26 |  | Marine Coatings - high-performance marine coating systems for immersion splash atmospheric zones (~7650 m²) | 7650 | m2 | 35 | 267750 | 267750 | CAD | ALLOWANCE | A-2609 | LOW
PKG-26::L2610 | PKG-26 |  | L2610 | MAT | PKG-26 |  | Field Touch-Up Materials - touch-up coatings field weld coating misc field-installed components | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-2610 | LOW | Allowance for field touch-up scope (field welds connections handling damage touch-up); extent unknown until construction
PKG-26::L2611 | PKG-26 |  | L2611 | MAT | PKG-26 |  | Surface Preparation Abrasives - blasting media consumables cleaning materials surface profile verification | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-2611 | LOW | Allowance for abrasives consumables; depends on surface prep grade (SSPC-SP 6 SP-10 or SP-5) and accessibility
PKG-26::L2612 | PKG-26 |  | L2612 | MAT | PKG-26 |  | Coating Application Consumables - spray equipment consumables masking materials ventilation equipment PPE | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-2612 | LOW | Allowance for application consumables; includes spray tips filters masking materials confined space ventilation equipment
PKG-26::L2613 | PKG-26 |  | L2613 | MAT | PKG-26 |  | Testing and Inspection Equipment - DFT gages holiday detectors adhesion test kits environmental monitoring | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-2613 | LOW | Allowance for inspection and testing equipment and consumables
PKG-26::L2614 | PKG-26 |  | L2614 | CD | PKG-26 |  | Tank Internal Surface Preparation - abrasive blasting cleaning surface profile verification (~11000 m²) | 11000 | m2 | 8 | 88000 | 88000 | CAD | ALLOWANCE | A-2614 | LOW
PKG-26::L2615 | PKG-26 |  | L2615 | CD | PKG-26 |  | Tank Internal Coating Application - spray application environmental control DFT measurement holiday detection (~11000 m²) | 11000 | m2 | 12 | 132000 | 132000 | CAD | ALLOWANCE | A-2615 | LOW
PKG-26::L2616 | PKG-26 |  | L2616 | CD | PKG-26 |  | Tank External Surface Preparation - abrasive blasting cleaning surface profile verification (~9000 m²) | 9000 | m2 | 5 | 45000 | 45000 | CAD | ALLOWANCE | A-2616 | LOW
PKG-26::L2617 | PKG-26 |  | L2617 | CD | PKG-26 |  | Tank External Coating Application - spray application environmental monitoring DFT measurement (~9000 m²) | 9000 | m2 | 7 | 63000 | 63000 | CAD | ALLOWANCE | A-2617 | LOW
PKG-26::L2618 | PKG-26 |  | L2618 | CD | PKG-26 |  | Structural Steel Surface Preparation - touch-up surface prep for field welds connections handling damage (~3750 m²) | 3750 | m2 | 3 | 11250 | 11250 | CAD | ALLOWANCE | A-2618 | LOW
PKG-26::L2619 | PKG-26 |  | L2619 | CD | PKG-26 |  | Structural Steel Field Painting - field painting application DFT measurement (~3750 m²) | 3750 | m2 | 5 | 18750 | 18750 | CAD | ALLOWANCE | A-2619 | LOW
PKG-26::L2620 | PKG-26 |  | L2620 | CD | PKG-26 |  | Marine Structure Surface Preparation - abrasive blasting for marine structures immersion splash atmospheric zones (~7650 m²) | 7650 | m2 | 7 | 53550 | 53550 | CAD | ALLOWANCE | A-2620 | LOW
PKG-26::L2621 | PKG-26 |  | L2621 | CD | PKG-26 |  | Marine Coating Application - high-performance marine coating application DFT measurement holiday detection (~7650 m²) | 7650 | m2 | 10 | 76500 | 76500 | CAD | ALLOWANCE | A-2621 | LOW
PKG-26::L2622 | PKG-26 |  | L2622 | CD | PKG-26 |  | Field Touch-Up Labor - field weld coating touch-up handling damage repair misc field painting | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-2622 | LOW | Allowance for field touch-up labor; extent unknown until construction; includes travel mobilization to various field locations
PKG-26::L2623 | PKG-26 |  | L2623 | CD | PKG-26 |  | Coating Inspection and Testing - DFT measurement holiday detection adhesion testing surface cleanliness verification environmental monitoring | 1 | LS | 75000 | 75000 | CAD | ALLOWANCE | A-2623 | LOW | Allowance for QA/QC inspection and testing labor; continuous monitoring during application; verification testing for acceptance
PKG-26::L2624 | PKG-26 |  | L2624 | CD | PKG-26 |  | Confined Space Entry Support - ventilation air monitoring safety watch rescue equipment for tank internal coating | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-2624 | LOW | Allowance for confined space entry support during tank internal surface prep and coating; HSE-critical; coordinate with PKG-33
PKG-26::L2625 | PKG-26 |  | L2625 | CD | PKG-26 |  | Access Equipment and Scaffolding - scaffolding aerial lifts access platforms for external tank coating and structural steel | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-2625 | LOW | Allowance for access equipment rental and setup; tank external coating requires scaffolding or aerial lifts
PKG-26::L2626 | PKG-26 |  | L2626 | CI | PKG-26 |  | Construction Indirects - field supervision QA/QC HSE coating operations coordination (factor-based) | 1 | LS | 137133 | 137133 | CAD | PARAMETRIC | D-2608 | LOW | 18% of CD base ($761.85k × 0.18 = $137.1k); factor from fallback model per AGENT_ESTIMATING.md
PKG-26::L2627 | PKG-26 |  | L2627 | P | PKG-26 |  | Procurement Services - coating vendor coordination material expediting quality documentation review (factor-based) | 1 | LS | 27780 | 27780 | CAD | PARAMETRIC | D-2608 | MED | 2% of MAT base ($1388.7k × 0.02 = $27.8k); factor from fallback model per AGENT_ESTIMATING.md
PKG-26::L2628 | PKG-26 |  | L2628 | PM | PKG-26 |  | EPCM / Project Management - PKG-26 allocation coating engineering coordination (factor-based) | 1 | LS | 137280 | 137280 | CAD | PARAMETRIC | D-2608 | MED | 6% of (CD+CI+MAT) = 6% × ($761.85k + $137.1k + $1388.7k) = $137.3k; factor from fallback model per AGENT_ESTIMATING.md
PKG-26::L2629 | PKG-26 |  | L2629 | COM | PKG-26 |  | Commissioning and Acceptance Testing - final coating inspection DFT verification holiday detection food-grade acceptance adhesion testing documentation closeout | 1 | LS | 68640 | 68640 | CAD | PARAMETRIC | D-2608 | LOW | 3% of (CD+CI+MAT) = 3% × ($761.85k + $137.1k + $1388.7k) = $68.6k; factor from fallback model per AGENT_ESTIMATING.md; includes food-grade acceptance for tank internals
PKG-27::L001 | PKG-27 | DEL-27.01 | L001 | E | PKG-27 | DEL-27.01 | Design Basis Documents - Civil discipline | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-001 | LOW | Design basis memorandum for civil/structural scope (site grading; foundations; structures)
PKG-27::L002 | PKG-27 | DEL-27.01 | L002 | E | PKG-27 | DEL-27.01 | Design Basis Documents - Mechanical discipline | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-002 | LOW | Design basis for process mechanical scope (tanks; piping; loading systems)
PKG-27::L003 | PKG-27 | DEL-27.01 | L003 | E | PKG-27 | DEL-27.01 | Design Basis Documents - Electrical discipline | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-003 | LOW | Design basis for electrical scope (power distribution; lighting; MCC)
PKG-27::L004 | PKG-27 | DEL-27.01 | L004 | E | PKG-27 | DEL-27.01 | Design Basis Documents - I&C discipline | 1 | LS | 38000 | 38000 | CAD | ALLOWANCE | A-004 | LOW | Design basis for instrumentation and controls scope (control systems; field instruments)
PKG-27::L005 | PKG-27 | DEL-27.01 | L005 | E | PKG-27 | DEL-27.01 | Design Basis Documents - Marine discipline | 1 | LS | 42000 | 42000 | CAD | ALLOWANCE | A-005 | LOW | Design basis for marine structures and loading arm scope
PKG-27::L006 | PKG-27 | DEL-27.02 | L006 | E | PKG-27 | DEL-27.02 | HAZOP Study - Facilitation and coordination | 40 | hr | 250 | 10000 | CAD | PARAMETRIC | A-006 | MED | HAZOP facilitator (5 days × 8 hr) for multi-discipline review sessions
PKG-27::L007 | PKG-27 | DEL-27.02 | L007 | E | PKG-27 | DEL-27.02 | HAZOP Study - Engineering participation (multi-discipline) | 200 | hr | 175 | 35000 | CAD | PARAMETRIC | A-007 | MED | Senior engineers representing civil/mechanical/electrical/I&C/process (5 disciplines × 40 hr)
PKG-27::L008 | PKG-27 | DEL-27.02 | L008 | E | PKG-27 | DEL-27.02 | HAZOP Study - Report preparation and documentation | 80 | hr | 165 | 13200 | CAD | PARAMETRIC | A-008 | MED | HAZOP report writing; action item tracking; distribution (2 weeks effort)
PKG-27::L009 | PKG-27 | DEL-27.02 | L009 | E | PKG-27 | DEL-27.02 | HAZOP Study - Client/Employer participation support | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | A-009 | LOW | Client attendance allowance (materials; logistics; coordination; assumed 5 attendees for 5 days)
PKG-27::L010 | PKG-27 | DEL-27.03 | L010 | E | PKG-27 | DEL-27.03 | Phase 2 Expansion Documentation - Concept design | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-010 | LOW | Phase 2 general arrangement drawing; interface identification; expansion planning memo
PKG-27::L011 | PKG-27 | DEL-27.03 | L011 | E | PKG-27 | DEL-27.03 | Phase 2 Expansion Documentation - Feasibility engineering | 1 | LS | 48000 | 48000 | CAD | ALLOWANCE | A-011 | LOW | Capacity analysis; staging assessment; cost order-of-magnitude estimate for Phase 2 scope
PKG-27::L012 | PKG-27 | DEL-27.04 | L012 | E | PKG-27 | DEL-27.04 | Design Submission Package - 30% Design | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-012 | LOW | 30% design submission: compilation; coordination; review; QA/QC; formatting; distribution (all disciplines)
PKG-27::L013 | PKG-27 | DEL-27.04 | L013 | E | PKG-27 | DEL-27.04 | Design Submission Package - 60% Design | 1 | LS | 110000 | 110000 | CAD | ALLOWANCE | A-013 | LOW | 60% design submission: compilation; coordination; review; QA/QC; formatting; distribution (all disciplines)
PKG-27::L014 | PKG-27 | DEL-27.04 | L014 | E | PKG-27 | DEL-27.04 | Design Submission Package - 90% Design | 1 | LS | 125000 | 125000 | CAD | ALLOWANCE | A-014 | LOW | 90% design submission: compilation; coordination; review; QA/QC; formatting; distribution (all disciplines)
PKG-27::L015 | PKG-27 | DEL-27.04 | L015 | E | PKG-27 | DEL-27.04 | Design Submission Package - IFC (Issued for Construction) | 1 | LS | 145000 | 145000 | CAD | ALLOWANCE | A-015 | LOW | IFC submission: final coordination; review; QA/QC; formatting; distribution; record management (all disciplines)
PKG-27::L016 | PKG-27 | DEL-27.05 | L016 | E | PKG-27 | DEL-27.05 | Cathodic Protection Design Basis | 1 | LS | 28000 | 28000 | CAD | ALLOWANCE | A-016 | LOW | CP specialist design basis development for marine structures and buried/submerged piping
PKG-27::L017 | PKG-27 | DEL-27.05 | L017 | E | PKG-27 | DEL-27.05 | Cathodic Protection Design Calculations | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-017 | LOW | CP anode layout calcs; current demand calcs; interference studies; design drawings (marine piles; buried pipe; tank bottoms)
PKG-27::L018 | PKG-27 | DEL-27.05 | L018 | E | PKG-27 | DEL-27.05 | Cathodic Protection OEM Coordination | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | A-018 | LOW | Rectifier selection coordination; impressed current system configuration; vendor data review
PKG-27::L019 | PKG-27 |  | L019 | PM | PKG-27 |  | Project Management - Design coordination and oversight | 1 | LS | 85000 | 85000 | CAD | PARAMETRIC | D-001 | MED | PM oversight of design package coordination across all disciplines (~6% of engineering base per fallback model)
PKG-27::L020 | PKG-27 |  | L020 | PM | PKG-27 |  | Project Management - Design review and approval coordination | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-019 | LOW | Internal design review facilitation; approval coordination; submission tracking; client interface management
PKG-27::L021 | PKG-27 |  | L021 | P | PKG-27 |  | Procurement support - HAZOP materials and logistics | 1 | LS | 2000 | 2000 | CAD | ALLOWANCE | A-020 | LOW | HAZOP session materials procurement; venue booking if external; catering coordination
PKG-27::L022 | PKG-27 |  | L022 | CD | PKG-27 |  | Construction support - Design representatives on site (FAT/SAT attendance) | 120 | hr | 145 | 17400 | CAD | PARAMETRIC | A-021 | MED | Design authority attendance at Factory/Site Acceptance Tests (estimated 15 days across project)
PKG-27::L023 | PKG-27 |  | L023 | CI | PKG-27 |  | Construction indirects - Design coordination during construction | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-022 | LOW | Field engineering coordination; RFI response support; design clarification during construction
PKG-27::L024 | PKG-27 |  | L024 | COM | PKG-27 |  | Commissioning support - Design verification during commissioning | 80 | hr | 165 | 13200 | CAD | PARAMETRIC | A-023 | MED | Engineering support during commissioning activities (design verification; troubleshooting; performance validation)
PKG-28::L001 | PKG-28 | DEL-28.01 | L001 | E | PKG-28 | DEL-28.01 | Independent Design Verification Reports - IDV services across all disciplines and submission stages (30/60/90/IFC) | 1 | LS | 350000 | 350000 | CAD | ALLOWANCE | A-001 | LOW | Allowance for IDV services without vendor quotes; assumes 8 disciplines x 4 stages at $10-12k per review
PKG-28::L002 | PKG-28 | DEL-28.02 | L002 | E | PKG-28 | DEL-28.02 | VFPA IP Review Responses - technical response preparation and documentation | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-003 | LOW | Allowance for IP review technical responses; assumes 4-6 major submission cycles at $15-20k each
PKG-28::L003 | PKG-28 | DEL-28.02 | L003 | PM | PKG-28 | DEL-28.02 | VFPA IP Review Coordination - authority coordination scheduling meetings | 1 | LS | 42300 | 42300 | CAD | ALLOWANCE | A-004 | LOW | Allowance for IP coordination effort; interface with VFPA reviewers and schedule management
PKG-28::L004 | PKG-28 | DEL-28.03 | L004 | PM | PKG-28 | DEL-28.03 | Design Coordination - inter-discipline coordination activities and meetings | 1 | LS | 80000 | 80000 | CAD | ALLOWANCE | A-002 | LOW | Allowance for coordination effort; assumes 18-24 months active design at ~$4k/month
PKG-28::L005 | PKG-28 | DEL-28.03 | L005 | PM | PKG-28 | DEL-28.03 | Clash Detection & Resolution - BIM coordination and clash reports | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-005 | LOW | Allowance for clash detection services; model coordination and resolution tracking
PKG-28::L006 | PKG-28 | DEL-28.03 | L006 | PM | PKG-28 | DEL-28.03 | RFI Management - RFI log maintenance response coordination tracking | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-006 | LOW | Allowance for RFI management; assumes 200-400 RFIs over design duration at ~$75-125 each for tracking/coordination
PKG-28::L007 | PKG-28 |  | L007 | CI | PKG-28 |  | QA/QC Engineering Review Allocation - quality oversight of design verification process | 1 | LS | 55100 | 55100 | CAD | PARAMETRIC | D-006 | MED | 18% of notional engineering review allocation ($306k); QA/QC oversight of IDV and coordination processes
PKG-28::L008 | PKG-28 |  | L008 | PM | PKG-28 |  | EPCM / Project Management - PKG-28 allocation (factor-based) | 1 | LS | 26700 | 26700 | CAD | PARAMETRIC | D-006 | MED | 6% of Engineering base ($445k); project management overhead allocation
PKG-28::L009 | PKG-28 |  | L009 | P | PKG-28 |  | Procurement Services - third-party engineering coordination (factor-based) | 1 | LS | 8900 | 8900 | CAD | PARAMETRIC | D-006 | MED | 2% of third-party engineering services ($445k); procurement coordination for IDV contracts
PKG-28::L010 | PKG-28 | DEL-28.01 | L010 | E | PKG-28 | DEL-28.01 | IDV Report Documentation and Records - final compilation and archival | 1 | LS | 0 | 0 | CAD | ALLOWANCE | A-007 | MED | Included in L001 IDV services allowance; no separate line item required
PKG-29::L-001 | PKG-29 | DEL-29.01 | L-001 | E | PKG-29 | DEL-29.01 | Test procedure development - Hydrostatic test procedures | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-014 | LOW | Hydrostatic test procedures for tanks (3) and piping systems; pressure/duration/acceptance criteria per ASME B31.3
PKG-29::L-002 | PKG-29 | DEL-29.01 | L-002 | E | PKG-29 | DEL-29.01 | Test procedure development - Electrical test procedures | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-015 | LOW | Electrical test procedures for switchgear; MCCs; motors; cables; protective relays; grounding per CSA/IEEE standards
PKG-29::L-003 | PKG-29 | DEL-29.01 | L-003 | E | PKG-29 | DEL-29.01 | Test procedure development - I&C test procedures | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-016 | LOW | I&C test procedures for instrument calibration; loop checks; control valve stroking; DCS FAT/SAT per ISA standards
PKG-29::L-004 | PKG-29 | DEL-29.02 | L-004 | E | PKG-29 | DEL-29.02 | Inspection and test plan development | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-017 | LOW | ITP development with hold/witness points matrix; inspection matrix; coordination with Employer QA requirements
PKG-29::L-005 | PKG-29 | DEL-29.06 | L-005 | E | PKG-29 | DEL-29.06 | Tank hydrotest water management plan | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-018 | LOW | Fill/hold/drain plan for 3 x 15000 MT tanks; treatment approach; sampling/testing plan; discharge/hauling plan per environmental permits
PKG-29::L-006 | PKG-29 |  | L-006 | E | PKG-29 |  | FAT procedure and protocol development | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-011 | LOW | FAT procedures and checklists for major equipment; acceptance criteria; witness point coordination
PKG-29::L-007 | PKG-29 |  | L-007 | E | PKG-29 |  | SAT procedure and protocol development | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-013 | LOW | SAT procedures and checklists for site acceptance; integration testing protocols; punch list format
PKG-29::L-008 | PKG-29 | DEL-29.03 | L-008 | MAT | PKG-29 | DEL-29.03 | Test equipment rental - Hydrostatic testing | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-019 | LOW | Hydrostatic test pumps; pressure gauges/recorders; chart recorders; blinds and isolation equipment; 8-12 week rental
PKG-29::L-009 | PKG-29 | DEL-29.03 | L-009 | MAT | PKG-29 | DEL-29.03 | Test equipment rental - Electrical and I&C testing | 1 | LS | 38000 | 38000 | CAD | ALLOWANCE | A-020 | LOW | Meggers; hi-pot testers; relay test sets; loop calibrators; HART communicators; multimeters; 8-12 week rental
PKG-29::L-010 | PKG-29 | DEL-29.07 | L-010 | MAT | PKG-29 | DEL-29.07 | Hydrotest water treatment chemicals and consumables | 1 | LS | 50000 | 50000 | CAD | ALLOWANCE | A-021 | LOW | Biocide; oxygen scavenger; corrosion inhibitor; pH adjustment chemicals; sampling supplies for 45000 m3 total volume
PKG-29::L-011 | PKG-29 | DEL-29.03 | L-011 | CD | PKG-29 | DEL-29.03 | Tank hydrostatic testing execution | 1 | LS | 180000 | 180000 | CAD | ALLOWANCE | A-001 | LOW | Water fill (45000 m3); hold period (24-48 hrs each); inspection; leak repair; drain; 3 tanks sequential or overlapped
PKG-29::L-012 | PKG-29 | DEL-29.07 | L-012 | CD | PKG-29 | DEL-29.07 | Hydrotest water treatment and testing | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-002 | LOW | Water treatment during fill/hold; sampling and lab testing; treatment adjustment; discharge water quality testing
PKG-29::L-013 | PKG-29 | DEL-29.08 | L-013 | CD | PKG-29 | DEL-29.08 | Hydrotest water disposal (haul-off portion) | 1 | LS | 120000 | 120000 | CAD | ALLOWANCE | A-003 | LOW | Vacuum truck haul-off for 50% of hydrotest water (~22500 m3); assume $10-12/m3 disposal; treatment facility fees
PKG-29::L-014 | PKG-29 | DEL-29.03 | L-014 | CD | PKG-29 | DEL-29.03 | Piping hydrostatic testing execution | 1 | LS | 120000 | 120000 | CAD | ALLOWANCE | A-004 + A-005 | LOW | 15-25 piping test packages; fill/pressurize/hold/drain; leak repair; punch list closeout; all disciplines
PKG-29::L-015 | PKG-29 | DEL-29.03 | L-015 | CD | PKG-29 | DEL-29.03 | Electrical testing execution | 1 | LS | 140000 | 140000 | CAD | ALLOWANCE | A-006 + A-007 | LOW | Switchgear testing; MCC testing (4 units); motor testing (25-35); cable meggering; relay testing; grounding verification
PKG-29::L-016 | PKG-29 | DEL-29.03 | L-016 | CD | PKG-29 | DEL-29.03 | I&C testing execution | 1 | LS | 167000 | 167000 | CAD | ALLOWANCE | A-008 + A-009 | LOW | Instrument calibration (200-300 loops); loop checks; control valve stroking (50-75); DCS point-to-point; alarm testing
PKG-29::L-017 | PKG-29 | DEL-29.04 | L-017 | CD | PKG-29 | DEL-29.04 | FAT attendance and execution | 1 | LS | 125000 | 125000 | CAD | ALLOWANCE | A-010 + A-011 | LOW | 8-12 major equipment FATs; 2-4 days each; travel/accommodation; engineering time; punch list management
PKG-29::L-018 | PKG-29 | DEL-29.05 | L-018 | CD | PKG-29 | DEL-29.05 | SAT execution | 1 | LS | 140000 | 140000 | CAD | ALLOWANCE | A-012 + A-013 | LOW | 15-25 major equipment SATs; on-site acceptance testing; punch list development and closeout; handover support
PKG-29::L-019 | PKG-29 |  | L-019 | CI | PKG-29 |  | Construction Indirects (factor-based) | 1 | LS | 146000 | 146000 | CAD | PARAMETRIC | D-009 (factor=0.18) | MEDIUM | CI = 0.18 x CD ($810k); includes site supervision; temporary facilities; HSE; QA/QC field inspection; per fallback typical model
PKG-29::L-020 | PKG-29 |  | L-020 | P | PKG-29 |  | Procurement Services (factor-based) | 1 | LS | 3000 | 3000 | CAD | PARAMETRIC | D-009 (factor=0.02) | MEDIUM | P = 0.02 x MAT ($143k); includes test equipment sourcing; vendor coordination; expediting; per fallback typical model
PKG-29::L-021 | PKG-29 |  | L-021 | PM | PKG-29 |  | EPCM/Project Management (factor-based) | 1 | LS | 66000 | 66000 | CAD | PARAMETRIC | D-009 (factor=0.06) | MEDIUM | PM = 0.06 x (CD + CI + MAT) ($1099k); includes testing coordination; schedule management; per fallback typical model
PKG-29::L-022 | PKG-29 |  | L-022 | COM | PKG-29 |  | Commissioning support (factor-based) | 1 | LS | 33000 | 33000 | CAD | PARAMETRIC | D-009 (factor=0.03) | MEDIUM | COM = 0.03 x (CD + CI + MAT) ($1099k); pre-commissioning support; handover to PKG-30 Commissioning
PKG-30::L-001 | PKG-30 | DEL-30.01 | L-001 | E | PKG-30 | DEL-30.01 | Commissioning Procedures Development - Pre-commissioning | 10 | EA | 12000 | 120000 | CAD | ALLOWANCE | A-003 | LOW | 10 pre-commissioning procedures @ 40 hrs ea @ $150/hr blended rate
PKG-30::L-002 | PKG-30 | DEL-30.01 | L-002 | E | PKG-30 | DEL-30.01 | Commissioning Procedures Development - System Commissioning | 15 | EA | 12000 | 180000 | CAD | ALLOWANCE | A-003 | LOW | 15 system commissioning procedures @ 40 hrs ea @ $150/hr blended rate
PKG-30::L-003 | PKG-30 | DEL-30.01 | L-003 | E | PKG-30 | DEL-30.01 | Commissioning Procedures Development - Start-up | 5 | EA | 10000 | 50000 | CAD | ALLOWANCE | A-003 | LOW | 5 start-up procedures @ 40 hrs ea @ $125/hr blended rate
PKG-30::L-004 | PKG-30 | DEL-30.02 | L-004 | E | PKG-30 | DEL-30.02 | Commissioning Plan Document Development | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-004 | LOW | Commissioning plan document and schedule development; ~240 hrs @ $145/hr blended rate
PKG-30::L-005 | PKG-30 |  | L-005 | PM | PKG-30 |  | Project Management - Commissioning Phase | 30 | WK | 7000 | 210000 | CAD | PARAMETRIC | D-010 | MEDIUM | PM allocation @ 6% of (CD+CI+MAT); 30 weeks commissioning duration
PKG-30::L-006 | PKG-30 |  | L-006 | P | PKG-30 |  | Procurement Services - Test Equipment & Consumables | 1 | LS | 52000 | 52000 | CAD | PARAMETRIC | D-011 | MEDIUM | Procurement allocation @ 2% of (MAT+vendor equipment); test equipment procurement coordination
PKG-30::L-007 | PKG-30 | DEL-30.03 | L-007 | MAT | PKG-30 | DEL-30.03 | Commissioning Consumables - Flushing & Cleaning | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-022 | LOW | Flushing fluids, cleaning chemicals, disposal for piping and tank systems
PKG-30::L-008 | PKG-30 | DEL-30.03 | L-008 | MAT | PKG-30 | DEL-30.03 | Hydrotest Water Treatment & Disposal | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-012 | LOW | Tank hydrotest water treatment and discharge; ~45,000 m³ total volume
PKG-30::L-009 | PKG-30 | DEL-30.03 | L-009 | MAT | PKG-30 | DEL-30.03 | Nitrogen Purging & Drying Consumables | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-022 | LOW | Nitrogen supply for purging and drying of piping systems
PKG-30::L-010 | PKG-30 | DEL-30.04 | L-010 | MAT | PKG-30 | DEL-30.04 | Commissioning Test Equipment Rental | 6 | MO | 30000 | 180000 | CAD | ALLOWANCE | A-022 | LOW | Multimeters, megohmmeters, vibration analyzers, loop calibrators, power quality analyzers; 6-month rental
PKG-30::L-011 | PKG-30 | DEL-30.04 | L-011 | MAT | PKG-30 | DEL-30.04 | Metering System Proving Equipment Rental | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-018 | LOW | Specialized custody transfer meter proving equipment rental; prover and master meters
PKG-30::L-012 | PKG-30 |  | L-012 | MAT | PKG-30 |  | Miscellaneous Commissioning Supplies | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-022 | LOW | General commissioning supplies, tools, safety equipment, temporary instrumentation
PKG-30::L-013 | PKG-30 | DEL-30.02 | L-013 | CD | PKG-30 | DEL-30.02 | Commissioning Manager | 30 | WK | 5400 | 162000 | CAD | RATE_TABLE | A-020 | MEDIUM | 1 FTE × 30 weeks × 40 hrs/wk × $135/hr fully burdened
PKG-30::L-014 | PKG-30 | DEL-30.04 | L-014 | CD | PKG-30 | DEL-30.04 | Mechanical Commissioning Lead | 24 | WK | 4600 | 110400 | CAD | RATE_TABLE | A-020 | MEDIUM | 1 FTE × 24 weeks × 40 hrs/wk × $115/hr fully burdened
PKG-30::L-015 | PKG-30 | DEL-30.04 | L-015 | CD | PKG-30 | DEL-30.04 | Electrical Commissioning Lead | 20 | WK | 4600 | 92000 | CAD | RATE_TABLE | A-020 | MEDIUM | 1 FTE × 20 weeks × 40 hrs/wk × $115/hr fully burdened
PKG-30::L-016 | PKG-30 | DEL-30.04 | L-016 | CD | PKG-30 | DEL-30.04 | I&C Commissioning Lead | 22 | WK | 4600 | 101200 | CAD | RATE_TABLE | A-020 | MEDIUM | 1 FTE × 22 weeks × 40 hrs/wk × $115/hr fully burdened
PKG-30::L-017 | PKG-30 | DEL-30.03 | L-017 | CD | PKG-30 | DEL-30.03 | Field Commissioning Technicians - Pre-commissioning | 8 | WK | 27200 | 217600 | CAD | RATE_TABLE | A-020 | MEDIUM | 8 FTE avg × 8 weeks × 40 hrs/wk × $85/hr; flushing, cleaning, hydrotesting activities
PKG-30::L-018 | PKG-30 | DEL-30.04 | L-018 | CD | PKG-30 | DEL-30.04 | Field Commissioning Technicians - Mechanical Systems | 10 | WK | 34000 | 340000 | CAD | RATE_TABLE | A-020 | MEDIUM | 10 FTE avg × 10 weeks × 40 hrs/wk × $85/hr; pumps, valves, tanks commissioning
PKG-30::L-019 | PKG-30 | DEL-30.04 | L-019 | CD | PKG-30 | DEL-30.04 | Field Commissioning Technicians - Electrical Systems | 8 | WK | 27200 | 217600 | CAD | RATE_TABLE | A-020 | MEDIUM | 8 FTE avg × 8 weeks × 40 hrs/wk × $85/hr; power distribution, motors, lighting commissioning
PKG-30::L-020 | PKG-30 | DEL-30.04 | L-020 | CD | PKG-30 | DEL-30.04 | Field Commissioning Technicians - I&C Systems | 10 | WK | 34000 | 340000 | CAD | RATE_TABLE | A-020 | MEDIUM | 10 FTE avg × 10 weeks × 40 hrs/wk × $85/hr; loop checking, SCADA/PLC, instrumentation commissioning
PKG-30::L-021 | PKG-30 | DEL-30.05 | L-021 | CD | PKG-30 | DEL-30.05 | Field Commissioning Technicians - Integrated Systems Testing | 6 | WK | 40800 | 244800 | CAD | RATE_TABLE | A-020 | MEDIUM | 12 FTE peak × 6 weeks × 40 hrs/wk × $85/hr; integrated systems and end-to-end testing
PKG-30::L-022 | PKG-30 | DEL-30.06 | L-022 | CD | PKG-30 | DEL-30.06 | Field Commissioning Technicians - Start-up & Performance Testing | 4 | WK | 27200 | 108800 | CAD | RATE_TABLE | A-020 | MEDIUM | 8 FTE avg × 4 weeks × 40 hrs/wk × $85/hr; start-up support and performance verification
PKG-30::L-023 | PKG-30 | DEL-30.04 | L-023 | CD | PKG-30 | DEL-30.04 | Vendor Commissioning Support - Storage Tanks | 2 | WK | 16000 | 32000 | CAD | ALLOWANCE | A-005 | LOW | Tank level gauging system vendor commissioning support; 2 weeks × 1 tech × $8k/wk
PKG-30::L-024 | PKG-30 | DEL-30.04 | L-024 | CD | PKG-30 | DEL-30.04 | Vendor Commissioning Support - Metering Systems | 3 | WK | 25000 | 75000 | CAD | ALLOWANCE | A-018 | LOW | Custody transfer meter proving specialist; 3 weeks × 1 specialist × $12.5k/wk (includes equipment)
PKG-30::L-025 | PKG-30 | DEL-30.04 | L-025 | CD | PKG-30 | DEL-30.04 | Vendor Commissioning Support - Marine Loading Arms | 2 | WK | 18000 | 36000 | CAD | ALLOWANCE | A-005 | LOW | Marine loading arm OEM commissioning support; 2 weeks × 1 tech × $9k/wk
PKG-30::L-026 | PKG-30 | DEL-30.04 | L-026 | CD | PKG-30 | DEL-30.04 | Vendor Commissioning Support - Control Systems | 2 | WK | 16000 | 32000 | CAD | ALLOWANCE | A-005 | LOW | SCADA/PLC vendor FAT and SAT support; 2 weeks × 1 tech × $8k/wk
PKG-30::L-027 | PKG-30 | DEL-30.04 | L-027 | CD | PKG-30 | DEL-30.04 | Vendor Commissioning Support - Other Specialized Equipment | 2 | WK | 10000 | 20000 | CAD | ALLOWANCE | A-005 | LOW | Fire protection, security systems, other specialty vendor support; 2 weeks total
PKG-30::L-028 | PKG-30 | DEL-30.04 | L-028 | CD | PKG-30 | DEL-30.04 | QA/QC Inspector - Commissioning Phase | 30 | WK | 3400 | 102000 | CAD | RATE_TABLE | A-020 | MEDIUM | 1 FTE × 30 weeks × 40 hrs/wk × $85/hr (QC inspector rate); commissioning verification
PKG-30::L-029 | PKG-30 | DEL-30.05 | L-029 | CD | PKG-30 | DEL-30.05 | Railcar Unloading System Commissioning | 32 | EA | 18000 | 576000 | CAD | ALLOWANCE | A-014 | LOW | 32 railcar stations commissioning; mechanical, electrical, I&C per station; ~120 hrs/station @ $150/hr blended
PKG-30::L-030 | PKG-30 | DEL-30.04 | L-030 | CD | PKG-30 | DEL-30.04 | Storage Tank System Commissioning | 3 | EA | 65000 | 195000 | CAD | ALLOWANCE | A-013 | LOW | 3×15,000 MT tanks commissioning; level gauging, temp monitoring, mixing; ~400 hrs/tank @ $160/hr blended
PKG-30::L-031 | PKG-30 | DEL-30.08 | L-031 | CD | PKG-30 | DEL-30.08 | Cathodic Protection Commissioning | 1 | LS | 28000 | 28000 | CAD | ALLOWANCE | A-023 | LOW | CP system commissioning; rectifier commissioning, baseline potentials, acceptance testing
PKG-30::L-032 | PKG-30 | DEL-30.07 | L-032 | CD | PKG-30 | DEL-30.07 | Defect Rectification Allowance | 1 | LS | 75000 | 75000 | CAD | ALLOWANCE | A-024 | LOW | Allowance for construction defects discovered during commissioning requiring rectification
PKG-30::L-033 | PKG-30 |  | L-033 | CI | PKG-30 |  | Field Supervision - Commissioning Phase | 30 | WK | 6500 | 195000 | CAD | PARAMETRIC | D-015 | MEDIUM | Field supervision allocation; 1 supervisor × 30 weeks × $6.5k/wk
PKG-30::L-034 | PKG-30 |  | L-034 | CI | PKG-30 |  | HSE Coordination - Commissioning Phase | 15 | WK | 5000 | 75000 | CAD | PARAMETRIC | D-015 | MEDIUM | HSE coordinator allocation; 0.5 FTE × 30 weeks × $5k/wk blended
PKG-30::L-035 | PKG-30 |  | L-035 | CI | PKG-30 |  | QA/QC Oversight - Commissioning Phase | 1 | LS | 48000 | 48000 | CAD | PARAMETRIC | D-015 | MEDIUM | QA/QC management allocation for commissioning phase
PKG-30::L-036 | PKG-30 |  | L-036 | CI | PKG-30 |  | Temporary Facilities - Commissioning Phase | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-025 | LOW | Temporary commissioning offices, storage, welfare facilities; 7 months duration
PKG-30::L-037 | PKG-30 |  | L-037 | CI | PKG-30 |  | Site Overhead - Commissioning Phase | 1 | LS | 102000 | 102000 | CAD | PARAMETRIC | D-015 | MEDIUM | Site overhead allocation during commissioning phase; utilities, communications, misc
PKG-30::L-038 | PKG-30 | DEL-30.05 | L-038 | COM | PKG-30 | DEL-30.05 | Integrated Systems Test Planning & Coordination | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-016 | LOW | IST test protocol development, coordination, execution support
PKG-30::L-039 | PKG-30 | DEL-30.06 | L-039 | COM | PKG-30 | DEL-30.06 | Performance Test Planning & Execution | 1 | LS | 55000 | 55000 | CAD | ALLOWANCE | A-017 | LOW | Performance test protocol development, test execution, data analysis, reporting
PKG-30::L-040 | PKG-30 | DEL-30.05 | L-040 | COM | PKG-30 | DEL-30.05 | Integrated Systems Test - Railcar to Tank Scenario | 1 | LS | 38000 | 38000 | CAD | ALLOWANCE | A-016 | LOW | End-to-end test: railcar unloading → transfer → storage tank; includes setup, execution, reporting
PKG-30::L-041 | PKG-30 | DEL-30.05 | L-041 | COM | PKG-30 | DEL-30.05 | Integrated Systems Test - Tank to Ship Scenario | 1 | LS | 42000 | 42000 | CAD | ALLOWANCE | A-016 | LOW | End-to-end test: storage tank → transfer → metering → marine loading; includes setup, execution, reporting
PKG-30::L-042 | PKG-30 | DEL-30.05 | L-042 | COM | PKG-30 | DEL-30.05 | Integrated Systems Test - Direct Rail to Ship Scenario | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-016 | LOW | End-to-end test: railcar → transfer → metering → marine loading (operational flexibility verification - OBJ-4)
PKG-30::L-043 | PKG-30 | DEL-30.05 | L-043 | COM | PKG-30 | DEL-30.05 | Control System Integration Testing | 1 | LS | 41000 | 41000 | CAD | ALLOWANCE | A-016 | LOW | SCADA/PLC integration, interlocks, alarms, emergency shutdown verification
PKG-31::L001 | PKG-31 | DEL-31.01 | L001 | E | PKG-31 | DEL-31.01 | Record Drawing Set - Drafting & Coordination | 275 | sheets | 165 | 45375 | CAD | PARAMETRIC | A-001; D-006 | MED | Estimated 275 total drawings at 12 hrs/sheet avg; $165/hr blended eng rate
PKG-31::L002 | PKG-31 | DEL-31.02 | L002 | E | PKG-31 | DEL-31.02 | As-Built Drawing Set - Field Markup Incorporation | 275 | sheets | 110 | 30250 | CAD | PARAMETRIC | A-001; D-006 | MED | As-built updates at +8 hrs/sheet; includes field verification & QA
PKG-31::L003 | PKG-31 | DEL-31.03 | L003 | E | PKG-31 | DEL-31.03 | Operation Manuals - System Level | 12 | systems | 13200 | 158400 | CAD | PARAMETRIC | A-002; D-007 | MED | 12 operational systems at 80 hrs/system; includes procedures and diagrams
PKG-31::L004 | PKG-31 | DEL-31.04 | L004 | E | PKG-31 | DEL-31.04 | Maintenance Manuals - Equipment Level | 90 | equipment | 2640 | 237600 | CAD | PARAMETRIC | A-003; D-007 | MED | 90 major equipment items at 16 hrs/equipment; compilation from vendor docs
PKG-31::L005 | PKG-31 | DEL-31.05 | L005 | PM | PKG-31 | DEL-31.05 | Vendor Documentation - Compilation & Organization | 90 | vendors | 1320 | 118800 | CAD | PARAMETRIC | A-003; D-008 | MED | Collection organization and indexing of vendor manuals certificates warranties
PKG-31::L006 | PKG-31 | DEL-31.06 | L006 | PM | PKG-31 | DEL-31.06 | Asset Hierarchy - Database Development | 1 | LS | 15840 | 15840 | CAD | PARAMETRIC | D-008 | MED | 120 hours at $132/hr PM rate; database structure and population
PKG-31::L007 | PKG-31 | DEL-31.07 | L007 | PM | PKG-31 | DEL-31.07 | Health & Safety File - Compilation | 1 | LS | 5280 | 5280 | CAD | PARAMETRIC | D-008 | MED | 40 hours at $132/hr PM rate; H&S documentation compilation
PKG-31::L008 | PKG-31 | DEL-31.08 | L008 | PM | PKG-31 | DEL-31.08 | Warranties Register - Development | 1 | LS | 5280 | 5280 | CAD | PARAMETRIC | D-008 | MED | 40 hours at $132/hr PM rate; register development and maintenance
PKG-31::L009 | PKG-31 | DEL-31.09 | L009 | PM | PKG-31 | DEL-31.09 | Warranty Certificates - Collection & Verification | 1 | LS | 7920 | 7920 | CAD | PARAMETRIC | D-008 | MED | 60 hours at $132/hr PM rate; certificate collection and verification
PKG-31::L010 | PKG-31 | DEL-31.10 | L010 | PM | PKG-31 | DEL-31.10 | Building Warranty Certificates - Coordination | 1 | LS | 3960 | 3960 | CAD | PARAMETRIC | D-008 | LOW | 30 hours at $132/hr PM rate; building-specific warranty coordination
PKG-31::L011 | PKG-31 | DEL-31.11 | L011 | PM | PKG-31 | DEL-31.11 | Building MEP Warranty Certificates - Coordination | 1 | LS | 3960 | 3960 | CAD | PARAMETRIC | D-008 | LOW | 30 hours at $132/hr PM rate; MEP-specific warranty coordination
PKG-31::L012 | PKG-31 |  | L012 | MAT | PKG-31 |  | Drawing Printing & Binding - Record Set | 3 | sets | 3850 | 11550 | CAD | ALLOWANCE | A-004 | LOW | 3 full sets at ~275 sheets/set; large format printing binding indexing
PKG-31::L013 | PKG-31 |  | L013 | MAT | PKG-31 |  | Drawing Printing & Binding - As-Built Set | 3 | sets | 4125 | 12375 | CAD | ALLOWANCE | A-004 | LOW | 3 full as-built sets; higher quality paper and binding
PKG-31::L014 | PKG-31 |  | L014 | MAT | PKG-31 |  | Manual Printing & Binding - Operations | 4 | sets | 1100 | 4400 | CAD | ALLOWANCE | A-005 | LOW | 4 bound operation manual sets
PKG-31::L015 | PKG-31 |  | L015 | MAT | PKG-31 |  | Manual Printing & Binding - Maintenance | 4 | sets | 2200 | 8800 | CAD | ALLOWANCE | A-005 | LOW | 4 bound maintenance manual sets
PKG-31::L016 | PKG-31 |  | L016 | MAT | PKG-31 |  | Document Management Software/Database | 1 | LS | 22000 | 22000 | CAD | ALLOWANCE | A-006 | LOW | Asset hierarchy database software/setup; allowance for CMMS-ready format
PKG-31::L017 | PKG-31 |  | L017 | PM | PKG-31 |  | Document Control & QA - Throughout Project | 1 | LS | 52800 | 52800 | CAD | PARAMETRIC | D-009 | MED | 400 hours at $132/hr PM rate; ongoing doc control QA review distribution
PKG-31::L018 | PKG-31 |  | L018 | PM | PKG-31 |  | Final Submittal Preparation & Delivery | 1 | LS | 10560 | 10560 | CAD | PARAMETRIC | D-009 | MED | 80 hours at $132/hr PM rate; final assembly indexing submittal to Employer
PKG-32::3201 | PKG-32 | DEL-32.01 | 3201 | E | PKG-32 | DEL-32.01 | Permit Application Engineering (Preparation & Submission) | 1 | LS | 75000 | 75000 | CAD | ALLOWANCE | A-3201 | LOW | Engineering hours for permit identification, application preparation, supporting documentation, internal review, Employer review, authority submission. Assumes 600 hrs @ $125/hr for 5-8 major permit applications (VFPA PER, DFO, TC, building, construction, environmental, fire). Range: $50k-$100k.
PKG-32::3202 | PKG-32 | DEL-32.03-32.06 | 3202 | E | PKG-32 | DEL-32.03-32.06 | Regulatory/Environmental Consultant Support | 1 | LS | 60000 | 60000 | CAD | ALLOWANCE | A-3207 | LOW | External consultant support for permit applications and compliance monitoring. Typical scope: environmental assessments, permit prep support, regulatory liaison, compliance monitoring. Assumes 300 hrs @ $200/hr. Covers ~50% of regulatory work. Range: $40k-$100k.
PKG-32::3203 | PKG-32 | DEL-32.02 | 3203 | MAT | PKG-32 | DEL-32.02 | Permit Application Fees (Contractor-Responsible) | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-3208 | LOW | Permit fees for Contractor-responsible permits: building permit ($5k-$15k), construction permits ($2k-$5k), environmental permits ($1k-$5k), fire approval ($1k-$3k), other fees ($1k-$5k). Excludes Employer-responsible permits. Range: $10k-$50k.
PKG-32::3204 | PKG-32 |  | 3204 | CD | PKG-32 |  | Construction Directs (None - Administrative Package) | 1 | LS | 0 | 0 | CAD | ALLOWANCE | D-3210 | MED | PKG-32 is administrative/document-based with no physical construction or field installation work. All work is engineering, PM, and QA/QC.
PKG-32::3205 | PKG-32 | DEL-32.03 | 3205 | CI | PKG-32 | DEL-32.03 | VFPA PER Compliance Monitoring & Documentation | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-3203 | LOW | QA/QC hours for VFPA PER compliance monitoring and documentation. Typical VFPA PER: 10-30 conditions. Assumes 200 hrs @ $125/hr. Covers condition tracking, monitoring reports, VFPA submittals, closeout. Range: $15k-$40k.
PKG-32::3206 | PKG-32 | DEL-32.04 | 3206 | CI | PKG-32 | DEL-32.04 | DFO Compliance Monitoring & Documentation | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-3204 | LOW | QA/QC hours for DFO Fisheries Act authorization compliance. Typical DFO authorization: 5-15 conditions (marine environmental protection focus). Assumes 160 hrs @ $125/hr. Covers marine work windows, environmental monitoring, DFO reporting. Range: $10k-$30k.
PKG-32::3207 | PKG-32 | DEL-32.05 | 3207 | CI | PKG-32 | DEL-32.05 | Transport Canada Compliance Monitoring & Documentation | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | A-3205 | LOW | QA/QC hours for Transport Canada compliance (rail, marine interface). Typical TC approvals: 3-10 conditions. Assumes 120 hrs @ $125/hr. Covers rail/marine safety compliance, inspection coordination, reporting. Range: $8k-$25k.
PKG-32::3208 | PKG-32 | DEL-32.06 | 3208 | CI | PKG-32 | DEL-32.06 | Code Compliance Inspection Coordination & Documentation | 1 | LS | 30000 | 30000 | CAD | ALLOWANCE | A-3206 | LOW | QA/QC hours for code inspection coordination (building, structural, fire, electrical, mechanical). Typical: 15-30 inspections. Assumes 240 hrs @ $125/hr. Covers inspection scheduling, attendance, deficiency tracking, re-inspections, certificate of occupancy. Range: $20k-$45k.
PKG-32::3209 | PKG-32 |  | 3209 | P | PKG-32 |  | Procurement Services (Consultant Engagement & Fee Processing) | 1 | LS | 1700 | 1700 | CAD | PARAMETRIC | A-3211; D-3209 | MED | Procurement services for consultant RFP/contracting and permit fee payment processing. Parametric allocation: P = 2% × MAT ($85k) = $1.7k. Typical range: 1%-3% of MAT.
PKG-32::3210 | PKG-32 | DEL-32.02 | 3210 | PM | PKG-32 | DEL-32.02 | Permit Receipt & Tracking | 1 | LS | 5000 | 5000 | CAD | ALLOWANCE | A-3202 | LOW | PM hours for permit receipt, condition review, register update, distribution, compliance tracking initiation. Embedded in PM parametric allocation. Assumes 150 hrs total over project lifecycle. Component allocation: $5k.
PKG-32::3211 | PKG-32 | DEL-32.07 | 3211 | PM | PKG-32 | DEL-32.07 | Correspondence Register Setup & Maintenance | 1 | LS | 2000 | 2000 | CAD | ALLOWANCE | A-3209 | LOW | PM hours for correspondence register template setup, entry logging, status updates, reporting, closeout. Embedded in PM parametric allocation. Assumes 60 hrs. Component allocation: $2k.
PKG-32::3212 | PKG-32 | DEL-32.08 | 3212 | PM | PKG-32 | DEL-32.08 | Correspondence Filing & Closeout Package | 1 | LS | 1000 | 1000 | CAD | ALLOWANCE | A-3210 | LOW | PM hours for correspondence filing, archive organization, closeout package assembly. Embedded in PM parametric allocation. Assumes 50 hrs. Component allocation: $1k.
PKG-32::3213 | PKG-32 |  | 3213 | PM | PKG-32 |  | Project Management (EPCM Allocation) | 1 | LS | 7000 | 7000 | CAD | PARAMETRIC | A-3212; D-3209 | MED | EPCM/PM allocation for overall PKG-32 coordination and management. Parametric allocation: PM = 6% × (E + MAT + CD + CI base) = 6% × $250k = $15k total. Breakdown: $5k (A-3202) + $2k (A-3209) + $1k (A-3210) + $7k (this line) = $15k. Typical range: 4%-10%.
PKG-32::3214 | PKG-32 |  | 3214 | COM | PKG-32 |  | Commissioning & Regulatory Closeout | 1 | LS | 7000 | 7000 | CAD | PARAMETRIC | A-3213; D-3209 | MED | Commissioning/closeout allocation for regulatory compliance closeout, certificate of occupancy, final permit submissions. Parametric allocation: COM = 3% × (E + MAT + CD + CI base) = 3% × $250k = $7.5k, rounded to $7k. Typical range: 1%-5%.
PKG-33::L-001 | PKG-33 | DEL-33.01 | L-001 | E | PKG-33 | DEL-33.01 | Occupational Health & Safety Plan - Engineering | 1 | LS | 84000 | 84000 | CAD | ALLOWANCE | A-001 | LOW | OHS Plan preparation; 70% of $120k allowance allocated to engineering effort
PKG-33::L-002 | PKG-33 | DEL-33.02 | L-002 | E | PKG-33 | DEL-33.02 | Risk Assessments - Task-Based JHAs | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | A-002 | LOW | Risk assessment and job hazard analysis development for 30-50 construction activities
PKG-33::L-003 | PKG-33 | DEL-33.03 | L-003 | E | PKG-33 | DEL-33.03 | Method Statements - Safe Work Procedures | 1 | LS | 110000 | 110000 | CAD | ALLOWANCE | A-003 | LOW-MED | Safe work method statements for 25-40 high-risk activities
PKG-33::L-004 | PKG-33 | DEL-33.08 | L-004 | E | PKG-33 | DEL-33.08 | Waterway Pollution Control Method Statement | 1 | LS | 65000 | 65000 | CAD | ALLOWANCE | A-008 | MED | Marine pollution control procedures and spill prevention measures for ship loading operations
PKG-33::L-005 | PKG-33 | DEL-33.07 | L-005 | E | PKG-33 | DEL-33.07 | Emergency Response Plan - Engineering | 1 | LS | 45000 | 45000 | CAD | ALLOWANCE | A-007 | MED | Emergency Response Plan engineering content; 60% of $75k allowance allocated to engineering
PKG-33::L-006 | PKG-33 | DEL-33.01 | L-006 | PM | PKG-33 | DEL-33.01 | Occupational Health & Safety Plan - Coordination | 1 | LS | 36000 | 36000 | CAD | ALLOWANCE | A-001 | LOW | OHS Plan coordination; 30% of $120k allowance allocated to PM effort
PKG-33::L-007 | PKG-33 | DEL-33.07 | L-007 | PM | PKG-33 | DEL-33.07 | Emergency Response Plan - Coordination | 1 | LS | 30000 | 30000 | CAD | ALLOWANCE | A-007 | MED | Emergency Response Plan coordination with site and local emergency services; 40% of $75k allowance
PKG-33::L-008 | PKG-33 |  | L-008 | PM | PKG-33 |  | HSE Coordination & Management Allocation | 1 | LS | 32700 | 32700 | CAD | PARAMETRIC | D-006 (Fallback Model) | MED | Project management allocation for HSE coordination; 6% of engineering base ($545k)
PKG-33::L-009 | PKG-33 |  | L-009 | P | PKG-33 |  | Procurement Services - HSE Consultants | 1 | LS | 10900 | 10900 | CAD | PARAMETRIC | D-006 (Fallback Model) | MED | Procurement services for third-party HSE/environmental consultants; 2% of HSE services ($545k)
PKG-33::L-010 | PKG-33 | DEL-33.04 | L-010 | CI | PKG-33 | DEL-33.04 | CEMP Compliance Monitoring - Construction | 1 | LS | 105000 | 105000 | CAD | ALLOWANCE | A-004 | LOW | CEMP compliance monitoring and records during construction phase; 75% of $140k allowance
PKG-33::L-011 | PKG-33 | DEL-33.05 | L-011 | CI | PKG-33 | DEL-33.05 | SPPP Compliance Monitoring - Construction | 1 | LS | 63750 | 63750 | CAD | ALLOWANCE | A-005 | LOW | SPPP compliance monitoring and BMP inspections during construction; 75% of $85k allowance
PKG-33::L-012 | PKG-33 | DEL-33.06 | L-012 | CI | PKG-33 | DEL-33.06 | Waste Management Records - Construction | 1 | LS | 44000 | 44000 | CAD | ALLOWANCE | A-006 | MED | Waste tracking and manifesting during construction phase; 80% of $55k allowance
PKG-33::L-013 | PKG-33 |  | L-013 | CI | PKG-33 |  | Construction Indirects - HSE Oversight Allocation | 1 | LS | 93100 | 93100 | CAD | PARAMETRIC | D-006 (Fallback Model) | MED | CI allocation for HSE oversight and QA/QC; 18% of notional construction base ($517k)
PKG-33::L-014 | PKG-33 | DEL-33.04 | L-014 | COM | PKG-33 | DEL-33.04 | CEMP Compliance Monitoring - Commissioning | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-004 | LOW | CEMP compliance monitoring during commissioning phase; 25% of $140k allowance
PKG-33::L-015 | PKG-33 | DEL-33.05 | L-015 | COM | PKG-33 | DEL-33.05 | SPPP Compliance Monitoring - Commissioning | 1 | LS | 21250 | 21250 | CAD | ALLOWANCE | A-005 | LOW | SPPP compliance during commissioning/startup; 25% of $85k allowance
PKG-33::L-016 | PKG-33 | DEL-33.06 | L-016 | COM | PKG-33 | DEL-33.06 | Waste Management Records - Commissioning | 1 | LS | 11000 | 11000 | CAD | ALLOWANCE | A-006 | MED | Waste management during commissioning/startup; 20% of $55k allowance
PKG-34::L001 | PKG-34 | DEL-34.01 | L001 | PM | PKG-34 | DEL-34.01 | Coordination Meeting Records - Weekly Terminal coordination meetings over 24-30 month construction | 1 | LS | 75000 | 75000 | CAD | ALLOWANCE | A-003 | LOW | Allowance for ~100-130 weekly meetings at $600-750/meeting (admin staff prep review distribution filing)
PKG-34::L002 | PKG-34 | DEL-34.02 | L002 | PM | PKG-34 | DEL-34.02 | Interface Agreements - FSPL-TI interface agreement preparation and negotiation | 1 | LS | 30000 | 30000 | CAD | ALLOWANCE | A-002 | LOW | Allowance for major interface agreement with Terminal operations; includes negotiations documentation coordination
PKG-34::L003 | PKG-34 | DEL-34.02 | L003 | PM | PKG-34 | DEL-34.02 | Interface Agreements - Metro Vancouver utilities interface agreement | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | A-002 | LOW | Allowance for utility interface agreement including sewer water coordination
PKG-34::L004 | PKG-34 | DEL-34.02 | L004 | PM | PKG-34 | DEL-34.02 | Interface Agreements - Other utilities and rail interface agreements | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | A-002 | LOW | Allowance for remaining interface agreements (BC Hydro FortisBC rail authority telecommunications)
PKG-34::L005 | PKG-34 | DEL-34.03 | L005 | PM | PKG-34 | DEL-34.03 | Marine Coordination Records - Notices to mariners and port/marine authority coordination | 1 | LS | 50000 | 50000 | CAD | ALLOWANCE | A-004 | LOW | Allowance for marine coordination over 8-12 month marine works period; includes NTM preparation VFPA coordination vessel scheduling
PKG-34::L006 | PKG-34 | DEL-34.04 | L006 | PM | PKG-34 | DEL-34.04 | Security Compliance Records - CBSA/TC security compliance documentation | 1 | LS | 40000 | 40000 | CAD | ALLOWANCE | A-005 | LOW | Allowance for security compliance over 24-30 month construction in port security zone; includes TWIC/MSIC coordination background checks access management
PKG-34::L007 | PKG-34 | DEL-34.05 | L007 | E | PKG-34 | DEL-34.05 | Trenchless Crossing Monitoring Reports - Settlement and condition monitoring for HDD crossings | 1 | LS | 75000 | 75000 | CAD | ALLOWANCE | A-001 | LOW | Allowance for 2-4 trenchless crossings; survey instrumentation monitoring and reporting over installation period
PKG-34::L008 | PKG-34 | DEL-34.05 | L008 | PM | PKG-34 | DEL-34.05 | Trenchless Crossing Monitoring Coordination - Coordination and stakeholder reporting | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | A-001 | LOW | Allowance for coordination with utility owners railway stakeholder reporting
PKG-34::L009 | PKG-34 |  | L009 | E | PKG-34 |  | Engineering Oversight Allocation - technical oversight for monitoring and interface activities | 1 | LS | 20000 | 20000 | CAD | PARAMETRIC | D-006 | MED | Additional engineering review and oversight allocation for technical coordination activities
PKG-34::L010 | PKG-34 |  | L010 | PM | PKG-34 |  | EPCM / Project Management - PKG-34 allocation (factor-based) | 1 | LS | 20000 | 20000 | CAD | PARAMETRIC | D-006 | MED | EPCM project management overhead allocation for coordination package
PKG-34::L011 | PKG-34 |  | L011 | CI | PKG-34 |  | QA/QC Coordination Oversight - quality oversight of coordination and interface activities | 1 | LS | 36000 | 36000 | CAD | PARAMETRIC | D-006 | MED | 18% of notional coordination base ($200k); QA/QC oversight of interface management and records
PKG-34::L012 | PKG-34 |  | L012 | P | PKG-34 |  | Procurement Services - third-party monitoring coordination (factor-based) | 1 | LS | 6000 | 6000 | CAD | PARAMETRIC | D-006 | MED | 2% of third-party monitoring services; procurement coordination for monitoring contracts
PKG-35::L-001 | PKG-35 | DEL-35.01 | L-001 | E | PKG-35 | DEL-35.01 | Training materials development - technical writing and presentations | 1 | LS | 285000 | 285000 | CAD | ALLOWANCE | A-003 | LOW | 5 major training categories; manuals and presentations
PKG-35::L-002 | PKG-35 | DEL-35.02 | L-002 | COM | PKG-35 | DEL-35.02 | OEM training delivery - major equipment systems | 1 | LS | 195000 | 195000 | CAD | ALLOWANCE | A-001 | LOW | 8 major systems requiring OEM training
PKG-35::L-003 | PKG-35 | DEL-35.02 | L-003 | COM | PKG-35 | DEL-35.02 | Contractor training delivery - operations and maintenance | 1 | LS | 100000 | 100000 | CAD | ALLOWANCE | A-001 | LOW | Operations maintenance and safety training programs
PKG-35::L-004 | PKG-35 | DEL-35.02 | L-004 | COM | PKG-35 | DEL-35.02 | Competency assessments and certification | 1 | LS | 100000 | 100000 | CAD | ALLOWANCE | A-001 | LOW | Written tests and practical demonstrations
PKG-35::L-005 | PKG-35 | DEL-35.02 | L-005 | PM | PKG-35 | DEL-35.02 | Training records management and administration | 1 | LS | 47000 | 47000 | CAD | ALLOWANCE | A-009 | MED | Training records system and administration
PKG-35::L-006 | PKG-35 | DEL-35.03 | L-006 | PM | PKG-35 | DEL-35.03 | Handover documentation and coordination | 1 | LS | 85000 | 85000 | CAD | ALLOWANCE | A-004 | MED | Taking Over certificates and handover checklists
PKG-35::L-007 | PKG-35 | DEL-35.04 | L-007 | CD | PKG-35 | DEL-35.04 | Site reinstatement - temporary facilities removal and site restoration | 1 | LS | 350000 | 350000 | CAD | ALLOWANCE | A-002 | LOW | Temp facilities removal cleanup and ground restoration
PKG-35::L-008 | PKG-35 | DEL-35.05 | L-008 | PM | PKG-35 | DEL-35.05 | Defects liability support - 12 month warranty period | 1 | LS | 165000 | 165000 | CAD | ALLOWANCE | A-005 | LOW | Defects management site visits and rectification support
PKG-35::L-009 | PKG-35 | DEL-35.04 | L-009 | CI | PKG-35 | DEL-35.04 | Construction indirects - QA/QC and site clearance supervision | 1 | LS | 134000 | 134000 | CAD | PARAMETRIC | D-006 | MED | 18% of CD plus 25% of COM QA allocation
PKG-35::L-010 | PKG-35 |  | L-010 | P | PKG-35 |  | Procurement services - third-party training procurement | 1 | LS | 17000 | 17000 | CAD | PARAMETRIC | D-006 | MED | 2% of third-party training services

## BOE_Reference
BOE reference tables (from Project_BOE.md) |  |  |  |  | Home
Executive summary metrics |  |  | Counts
Metric | Value |  | Packages | 36
**Total Estimate** | **$117.1M CAD** |  | Deliverables | 202
Base Estimate | $92,416,406 CAD |  | Line items | 867
Contingency | ~$24.7M CAD (~26.7% blended)
Currency | CAD (Canadian dollars)
Pricing Date | January 2026
Estimate Class | Class 5 (Order of Magnitude)
Overall Confidence | LOW
Accuracy Range | -30% / +50%
Package coverage summary
Category | Packages | Base Cost | % of Total
Site & Civil | PKG-00 to PKG-04 | $12.5M | 13.5%
Structural | PKG-05 to PKG-09 | $13.7M | 14.8%
Mechanical | PKG-10 to PKG-16 | $36.0M | 39.0%
Electrical & I&C | PKG-17 to PKG-20 | $8.4M | 9.1%
Buildings & Protection | PKG-21 to PKG-26 | $9.3M | 10.1%
Project Execution | PKG-27 to PKG-35 | $12.5M | 13.5%
**TOTAL** | **36 Packages** | **$92.4M** | **100%**
CBS summary
CBS | Description | Amount (CAD) | % of Total
MAT | Materials | $41,045,785 | 44.4%
CD | Construction Directs | $26,933,520 | 29.1%
E | Engineering | $8,640,165 | 9.4%
PM | Project Management | $5,821,748 | 6.3%
CI | Construction Indirects | $5,816,043 | 6.3%
COM | Commissioning | $3,004,199 | 3.3%
P | Procurement | $921,946 | 1.0%
FRT | Freight | $233,000 | 0.3%
**BASE TOTAL** |  | **$92,416,406** | **100%**
Pricing method distribution
Method | Line Items | % of Items | Remarks
ALLOWANCE | 689 | 79.5% | Lump-sum placeholders without vendor validation
PARAMETRIC | 154 | 17.8% | Factor-based calculations (indirects, PM, etc.)
RATE_TABLE | 11 | 1.3% | Limited rate table pricing
QUOTE | 0 | 0% | No vendor quotes available
**TOTAL** | **867** | **100%**
Contingency by CBS (as stated in BOE)
CBS | Base (CAD) | Contingency Rate | Contingency (CAD)
E | $8,640,165 | 15% | $1,296,000
PM | $5,821,748 | 15% | $873,000
P | $921,946 | 15% | $138,000
MAT | $41,045,785 | 20% | $8,209,000
FRT | $233,000 | 20% | $47,000
CD | $26,933,520 | 25% | $6,733,000
CI | $5,816,043 | 25% | $1,454,000
COM | $3,004,199 | 30% | $901,000
**TOTAL** | **$92,416,406** | **~26.7%** | **~$24.7M**

## Inputs
Model Inputs / Lookups | [7 empty] | Home
Contingency scaling factor | 1 | (1.00 = use BOE bucket rates as-is)
Contingency rates by CBS (from BOE §7.2) |  |  | Package category mapping (from BOE §2.3) |  | Package descriptions (from BOE §12)
CBS | Rate |  | Package | PackageCategory | Package | Description | Confidence
E | 15% |  | PKG-00 | Site & Civil | PKG-00 | Site Establishment | LOW
PM | 15% |  | PKG-01 | Site & Civil | PKG-01 | Demolition & Removals | LOW
P | 15% |  | PKG-02 | Site & Civil | PKG-02 | Earthworks & Ground Improvement | LOW
MAT | 20% |  | PKG-03 | Site & Civil | PKG-03 | Underground Utilities & Drainage | LOW
FRT | 20% |  | PKG-04 | Site & Civil | PKG-04 | Pavement & Surfacing | LOW
CD | 25% |  | PKG-05 | Structural | PKG-05 | Concrete Structures | LOW
CI | 25% |  | PKG-06 | Structural | PKG-06 | Structural Steelwork | LOW
COM | 30% |  | PKG-07 | Structural | PKG-07 | Rail Works | LOW
|  |  | PKG-08 | Structural | PKG-08 | Marine Structures | LOW
|  |  | PKG-09 | Structural | PKG-09 | Marine Outfitting | LOW
|  |  | PKG-10 | Mechanical | PKG-10 | Railcar Unloading System | LOW
|  |  | PKG-11 | Mechanical | PKG-11 | Marine Loading System | LOW
|  |  | PKG-12 | Mechanical | PKG-12 | Product Transfer & Metering | LOW
|  |  | PKG-13 | Mechanical | PKG-13 | Storage Tanks | LOW
|  |  | PKG-14 | Mechanical | PKG-14 | Process Piping | LOW
|  |  | PKG-15 | Mechanical | PKG-15 | Pumps & Rotating Equipment | LOW-MED
|  |  | PKG-16 | Mechanical | PKG-16 | Valves & Specialty Equipment | LOW
|  |  | PKG-17 | Electrical & I&C | PKG-17 | Electrical Power Distribution | LOW
|  |  | PKG-18 | Electrical & I&C | PKG-18 | Lighting | LOW
|  |  | PKG-19 | Electrical & I&C | PKG-19 | Control Systems | LOW
|  |  | PKG-20 | Electrical & I&C | PKG-20 | Field Instrumentation | LOW
|  |  | PKG-21 | Buildings & Protection | PKG-21 | Buildings (MCC/Shelters) | LOW
|  |  | PKG-22 | Buildings & Protection | PKG-22 | Building Interior & MEP | LOW
|  |  | PKG-23 | Buildings & Protection | PKG-23 | Fire Protection | LOW
|  |  | PKG-24 | Buildings & Protection | PKG-24 | Security Systems | LOW
|  |  | PKG-25 | Buildings & Protection | PKG-25 | Communications & IT | LOW
|  |  | PKG-26 | Buildings & Protection | PKG-26 | Protective Coatings & Painting | LOW-MED
|  |  | PKG-27 | Project Execution | PKG-27 | Insulation | LOW
|  |  | PKG-28 | Project Execution | PKG-28 | Design Verification | LOW
|  |  | PKG-29 | Project Execution | PKG-29 | Testing | LOW
|  |  | PKG-30 | Project Execution | PKG-30 | Commissioning | LOW-MED
|  |  | PKG-31 | Project Execution | PKG-31 | Documentation | LOW
|  |  | PKG-32 | Project Execution | PKG-32 | Regulatory & Permits | LOW
|  |  | PKG-33 | Project Execution | PKG-33 | HSE Management | LOW
|  |  | PKG-34 | Project Execution | PKG-34 | Coordination & Interfaces | LOW
|  |  | PKG-35 | Project Execution | PKG-35 | Training & Handover | LOW