## Dashboard
Estimating Dashboard
Project: | Town of Penhold -- Public Services Building (PSB)
Currency / Base Year: | CAD / 2024 | As of: | 2026-02-18
Filters (optional) |  |  |  |  | Chart Drivers (auto)
Package | All | Method | All | * | Method | Amount
Deliverable | All | Confidence | All | * | RATE_TABLE | 6216696
|  |  |  | * | ALLOWANCE | 692150
|  |  |  | * | PARAMETRIC | 292400
Project Total (excl. subtotals) |  | Selected Scope Total |  |  | QUOTE | 18600
7219846 |  | 7219846 |  |  | Total | 7219846
[5 empty] | Confidence | Amount
[5 empty] | HIGH | 30770
Allowance Share |  | Low-Confidence Share |  |  | MED | 6028056
9.587% |  | 15.82% |  |  | MEDIUM | 18600
[5 empty] | LOW | 1142420
[5 empty] | Total | 7219846
Priced Lines (scope) |  | Deliverables (line count) in scope |  |  | Package | Subtotal
266 |  | 266 |  |  | PKG-001 | 464450
[5 empty] | PKG-002 | 4239304
[5 empty] | PKG-003 | 1657342
[5 empty] | PKG-004 | 464750
[5 empty] | PKG-005 | 394000
[5 empty] | Total | 7219846
Risk Heatmap (count)
[5 empty] | Likelihood \ Impact | LOW | MEDIUM | HIGH
[5 empty] | LOW | 8 | 0 | 1
[5 empty] | MEDIUM | 0 | 13 | 1
[5 empty] | HIGH | 0 | 1 | 6
Data sheets:
Detail Lines
WBS Summary
CBS Summary
WBS×CBS Matrix
BOE Index
Coverage
Assumptions
Risks
BOE Collection

## Detail_Lines
LineUID | FromDeliverableID | FromPackageID | LineID | CBS | WBS_PackageID | WBS_DeliverableID | Description | Qty | Unit | UnitRate | Amount | Currency | Method | SourceRef | Confidence | Notes | SourceSnapshot
DEL-01-01::L-001 | DEL-01-01 | PKG-001 | L-001 | MGMT | PKG-001 | DEL-01-01 | Project Manager — PM oversight across full 18-month construction phase (~7 hr/wk) | 120 | hr | 175 | 21000 | CAD | RATE_TABLE | Rate: Professional_Staff_Rates.csv row R-02 ($175/hr); Hours: Level_of_Effort.csv row DEL-01-01/R-02 (120 hr); Duration basis: Assumed_Project_Parameters.csv PP-01 (18 months) | MED | PM oversight across full 18-month construction phase; ~7 hr/wk | EST_DEL-01-01_2026-02-18_1200
DEL-01-01::L-002 | DEL-01-01 | PKG-001 | L-002 | MGMT | PKG-001 | DEL-01-01 | Design Manager — Design phase leadership 4 months + periodic review during construction | 80 | hr | 165 | 13200 | CAD | RATE_TABLE | Rate: Professional_Staff_Rates.csv row R-03 ($165/hr); Hours: Level_of_Effort.csv row DEL-01-01/R-03 (80 hr); Duration basis: Assumed_Project_Parameters.csv PP-02 (4 months design) | MED | Design phase leadership 4 months; periodic review during construction | EST_DEL-01-01_2026-02-18_1200
DEL-01-01::L-003 | DEL-01-01 | PKG-001 | L-003 | DESIGN | PKG-001 | DEL-01-01 | Architect (Project) — Design review and QA/QC review cycles | 40 | hr | 145 | 5800 | CAD | RATE_TABLE | Rate: Professional_Staff_Rates.csv row R-04 ($145/hr); Hours: Level_of_Effort.csv row DEL-01-01/R-04 (40 hr) | MED | Design review; QA/QC review cycles — management function not discipline design production | EST_DEL-01-01_2026-02-18_1200
DEL-01-01::L-004 | DEL-01-01 | PKG-001 | L-004 | ADMIN | PKG-001 | DEL-01-01 | Administrative / Document Control — Document management full project duration (~3.5 hr/wk) | 60 | hr | 80 | 4800 | CAD | RATE_TABLE | Rate: Professional_Staff_Rates.csv row R-24 ($80/hr); Hours: Level_of_Effort.csv row DEL-01-01/R-24 (60 hr); Duration basis: Assumed_Project_Parameters.csv PP-01 (18 months) | MED | Document management full project duration; ~3.5 hr/wk | EST_DEL-01-01_2026-02-18_1200
DEL-01-02::L-001 | DEL-01-02 | PKG-001 | L-001 | MGMT.PROJ_CONTROLS | PKG-001 | DEL-01-02 | Scheduler — schedule development (40h) + monthly updates (2h/mo x 18mo = 36h) + closeout | 80 | hr | 130 | 10400 | CAD | RATE_TABLE | Professional_Staff_Rates.csv row R-17; Level_of_Effort.csv row DEL-01-02 R-17 | MED | Rate: R-17 Scheduler $130/hr; Hours: LOE basis (PARAMETRIC) see DEC-EST-001 | EST_DEL-01-02_2026-02-18_2100
DEL-01-02::L-002 | DEL-01-02 | PKG-001 | L-002 | MGMT.PROJ_CONTROLS | PKG-001 | DEL-01-02 | Project Manager — schedule review + reporting oversight | 20 | hr | 175 | 3500 | CAD | RATE_TABLE | Professional_Staff_Rates.csv row R-02; Level_of_Effort.csv row DEL-01-02 R-02 | MED | Rate: R-02 PM $175/hr; Hours: LOE basis (PARAMETRIC) see DEC-EST-001 | EST_DEL-01-02_2026-02-18_2100
DEL-01-02::L-003 | DEL-01-02 | PKG-001 | L-003 | MGMT.PROJ_CONTROLS | PKG-001 | DEL-01-02 | Scheduling software / tools — project scheduling license (18-month project) | 1 | LS | 3500 | 3500 | CAD | ALLOWANCE | Parametric allowance — P6/MS Project license for 18-month project | LOW | Previously TBD; resolved as parametric allowance per ORCHESTRATOR TBD resolution pass; see DEC-EST-005 | EST_DEL-01-02_2026-02-18_2100
DEL-01-03::L-0103-001 | DEL-01-03 | PKG-001 | L-0103-001 | CBS-LABOUR-SAFETY | PKG-001 | DEL-01-03 | Safety Officer - H&S plan development and site safety management | 60 | hr | 110 | 6600 | CAD | RATE_TABLE | Professional_Staff_Rates.csv (R-20) + Level_of_Effort.csv (DEL-01-03 R-20) | MED | 20h plan development + ~2.5h/wk x 16wk active site safety; rate $110/hr per rate table | EST_DEL-01-03_2026-02-18_2100
DEL-01-03::L-0103-002 | DEL-01-03 | PKG-001 | L-0103-002 | CBS-LABOUR-ADMIN | PKG-001 | DEL-01-03 | Administrative / Document Control - Safety documentation filing | 8 | hr | 80 | 640 | CAD | RATE_TABLE | Professional_Staff_Rates.csv (R-24) + Level_of_Effort.csv (DEL-01-03 R-24) | MED | Safety doc filing support; rate $80/hr per rate table | EST_DEL-01-03_2026-02-18_2100
DEL-01-03::L-0103-003 | DEL-01-03 | PKG-001 | L-0103-003 | CBS-TRAINING | PKG-001 | DEL-01-03 | Training costs - site orientation and safety training materials for 18-month project | 1 | LS | 4500 | 4500 | CAD | ALLOWANCE | Parametric allowance — site orientation + safety training for 30-40 workers over 18-month project | LOW | Previously TBD; resolved as parametric allowance per ORCHESTRATOR TBD resolution pass; covers WHMIS/first aid/confined space training sessions + materials | EST_DEL-01-03_2026-02-18_2100
DEL-01-03::L-0103-004 | DEL-01-03 | PKG-001 | L-0103-004 | CBS-SUPPLIES | PKG-001 | DEL-01-03 | PPE and signage supplies - hard hats + vests + glasses + first aid kits + site signage | 1 | LS | 3500 | 3500 | CAD | ALLOWANCE | Parametric allowance — PPE and site safety signage for 18-month construction project | LOW | Previously TBD; resolved as parametric allowance per ORCHESTRATOR TBD resolution pass; covers standard PPE inventory + site safety signage package | EST_DEL-01-03_2026-02-18_2100
DEL-01-04::L-01 | DEL-01-04 | PKG-001 | L-01 | 01-MGMT | PKG-001 | DEL-01-04 | Project Manager -- permit applications; inspection coordination; AHJ liaison | 40 | hr | 175 | 7000 | CAD | RATE_TABLE | Level_of_Effort.csv row DEL-01-04/R-02 + Professional_Staff_Rates.csv R-02 | MED | 40h per Level_of_Effort.csv; $175/hr per Professional_Staff_Rates.csv | EST_DEL-01-04_2026-02-18_1400
DEL-01-04::L-02 | DEL-01-04 | PKG-001 | L-02 | 01-MGMT | PKG-001 | DEL-01-04 | Administrative / Document Control -- permit documentation; inspection records | 12 | hr | 80 | 960 | CAD | RATE_TABLE | Level_of_Effort.csv row DEL-01-04/R-24 + Professional_Staff_Rates.csv R-24 | MED | 12h per Level_of_Effort.csv; $80/hr per Professional_Staff_Rates.csv | EST_DEL-01-04_2026-02-18_1400
DEL-01-04::L-03 | DEL-01-04 | PKG-001 | L-03 | 01-FEES | PKG-001 | DEL-01-04 | Building permit -- Town of Penhold (0.75% of estimated construction value) | 1 | LS | 65250 | 65250 | CAD | ALLOWANCE | Fees_Permits_Insurance.csv FP-06 + Assumed_Project_Parameters.csv PP-24 | LOW | 0.75% recommended rate x $8700000 PP-24; Penhold fee schedule TBD; ALLOWANCE method per FALLBACK_POLICY | EST_DEL-01-04_2026-02-18_1400
DEL-01-04::L-04 | DEL-01-04 | PKG-001 | L-04 | 01-FEES | PKG-001 | DEL-01-04 | Development permit -- Town of Penhold | 1 | LS | 1200 | 1200 | CAD | ALLOWANCE | Fees_Permits_Insurance.csv FP-07 | LOW | Recommended rate $1200; Penhold fee schedule TBD | EST_DEL-01-04_2026-02-18_1400
DEL-01-04::L-05 | DEL-01-04 | PKG-001 | L-05 | 01-FEES | PKG-001 | DEL-01-04 | Electrical permit -- Alberta Safety Codes | 1 | LS | 2500 | 2500 | CAD | ALLOWANCE | Fees_Permits_Insurance.csv FP-08 | MED | Recommended rate $2500; based on electrical scope | EST_DEL-01-04_2026-02-18_1400
DEL-01-04::L-06 | DEL-01-04 | PKG-001 | L-06 | 01-FEES | PKG-001 | DEL-01-04 | Plumbing permit -- Alberta Safety Codes | 1 | LS | 2000 | 2000 | CAD | ALLOWANCE | Fees_Permits_Insurance.csv FP-09 | MED | Recommended rate $2000; based on fixture count | EST_DEL-01-04_2026-02-18_1400
DEL-01-04::L-07 | DEL-01-04 | PKG-001 | L-07 | 01-FEES | PKG-001 | DEL-01-04 | Gas permit -- Alberta Safety Codes | 1 | LS | 1000 | 1000 | CAD | ALLOWANCE | Fees_Permits_Insurance.csv FP-10 | MED | Recommended rate $1000; based on appliance count | EST_DEL-01-04_2026-02-18_1400
DEL-01-05::L-01 | DEL-01-05 | PKG-001 | L-01 | PM | PKG-001 | DEL-01-05 | Project Manager — meetings (biweekly x 2h x 18mo = 72h) + change control admin (18h) | 90 | hr | 175 | 15750 | CAD | RATE_TABLE | Professional_Staff_Rates.csv (R-02) + Level_of_Effort.csv (DEL-01-05 R-02 90h) | MED | SOW-0011 meetings + SOW-0012 change control; PP-01 18-month duration basis | EST_DEL-01-05_2026-02-18_0000
DEL-01-05::L-02 | DEL-01-05 | PKG-001 | L-02 | ADMIN | PKG-001 | DEL-01-05 | Administrative / Document Control — minutes + RFI log + submittal tracking + change order documentation | 50 | hr | 80 | 4000 | CAD | RATE_TABLE | Professional_Staff_Rates.csv (R-24) + Level_of_Effort.csv (DEL-01-05 R-24 50h) | MED | SOW-0011 meeting minutes + SOW-0012 documentation management; PP-01 18-month duration basis | EST_DEL-01-05_2026-02-18_0000
DEL-01-06::L-0106-001 | DEL-01-06 | PKG-001 | L-0106-001 | 01-CMGT | PKG-001 | DEL-01-06 | Site Superintendent -- full-time on-site supervision (40h/wk x 18mo construction duration at 80% utilization) | 1440 | hr | 135 | 194400 | CAD | RATE_TABLE | Professional_Staff_Rates.csv row R-16 + Level_of_Effort.csv row DEL-01-06/R-16 | MED | 1440 hrs from Level_of_Effort.csv (PARAMETRIC basis: 40h/wk x 18mo x 4.33wk/mo trimmed to 80% utilization); $135/hr from Professional_Staff_Rates.csv R-16; 18-month duration from Assumed_Project_Parameters.csv PP-01 | EST_DEL-01-06_2026-02-18_2100
DEL-01-06::L-0106-002 | DEL-01-06 | PKG-001 | L-0106-002 | 01-CMGT | PKG-001 | DEL-01-06 | Construction Manager -- periodic site visits and logistics oversight (~3.5h/wk) | 60 | hr | 155 | 9300 | CAD | RATE_TABLE | Professional_Staff_Rates.csv row R-15 + Level_of_Effort.csv row DEL-01-06/R-15 | MED | 60 hrs from Level_of_Effort.csv (PARAMETRIC basis: ~3.5h/wk); $155/hr from Professional_Staff_Rates.csv R-15 | EST_DEL-01-06_2026-02-18_2100
DEL-01-06::L-0106-003 | DEL-01-06 | PKG-001 | L-0106-003 | 01-SITE | PKG-001 | DEL-01-06 | Temporary facilities and fencing -- site office trailer + temp power + fencing panels + portable washrooms for 18-month construction duration | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | Parametric allowance — site office trailer ($1500/mo x 18) + temp power hookup ($5000) + temp power consumption ($500/mo x 18) + fencing panels ($500/mo x 18) + portable washrooms ($300/mo x 18) + misc $5000 | LOW | Previously TBD; resolved as parametric allowance per ORCHESTRATOR TBD resolution pass | EST_DEL-01-06_2026-02-18_2100
DEL-01-06::L-0106-004 | DEL-01-06 | PKG-001 | L-0106-004 | 01-SITE | PKG-001 | DEL-01-06 | Site cleaning -- ongoing construction cleanup + final pre-occupancy clean for 24000 sf total building area | 1 | LS | 25000 | 25000 | CAD | ALLOWANCE | Parametric allowance — ongoing cleanup ($800/mo x 18mo = $14400) + final pre-occupancy clean ($10000 for 24000 sf at $0.40/sf) | LOW | Previously TBD; resolved as parametric allowance per ORCHESTRATOR TBD resolution pass | EST_DEL-01-06_2026-02-18_2100
DEL-01-07::L-0107-01 | DEL-01-07 | PKG-001 | L-0107-01 | CBS-0107-CX | PKG-001 | DEL-01-07 | Commissioning Lead -- Cx plan development (20h) + functional testing coordination (40h) + training delivery (20h) + as-built coordination (20h) + warranty admin (20h) | 120 | hr | 140 | 16800 | CAD | RATE_TABLE | Professional_Staff_Rates.csv row R-21 (HourlyRate_CAD=140); Level_of_Effort.csv row DEL-01-07/R-21 (EstimatedHours=120) | MED | Overall Cx coordination only; system-specific commissioning labor is in PKG-002 discipline deliverables | EST_DEL-01-07_2026-02-18_1830
DEL-01-07::L-0107-02 | DEL-01-07 | PKG-001 | L-0107-02 | CBS-0107-MGT | PKG-001 | DEL-01-07 | Project Manager -- Cx oversight and closeout coordination and warranty management | 30 | hr | 175 | 5250 | CAD | RATE_TABLE | Professional_Staff_Rates.csv row R-02 (HourlyRate_CAD=175); Level_of_Effort.csv row DEL-01-07/R-02 (EstimatedHours=30) | MED | PM oversight of commissioning and closeout process | EST_DEL-01-07_2026-02-18_1830
DEL-01-07::L-0107-03 | DEL-01-07 | PKG-001 | L-0107-03 | CBS-0107-ADM | PKG-001 | DEL-01-07 | Administrative / Document Control -- As-built documentation assembly and O&M manual compilation and warranty log maintenance | 20 | hr | 80 | 1600 | CAD | RATE_TABLE | Professional_Staff_Rates.csv row R-24 (HourlyRate_CAD=80); Level_of_Effort.csv row DEL-01-07/R-24 (EstimatedHours=20) | MED | Document assembly and formatting; binder preparation (2 hard copies + digital) | EST_DEL-01-07_2026-02-18_1830
DEL-02-01::L-001 | DEL-02-01 | PKG-002 | L-001 | 3300 | PKG-002 | DEL-02-01 | Interior hollow metal doors — single (office/admin/shared areas; estimated 18 openings) | 18 | each | 1800 | 32400 | CAD | RATE_TABLE | Building_Envelope_Rates.csv BE-11 | MED | 18 single doors per ASM-004 | EST_DEL-02-01_2026-02-18_2100
DEL-02-01::L-002 | DEL-02-01 | PKG-002 | L-002 | 3300 | PKG-002 | DEL-02-01 | Interior hollow metal doors — double (meeting room main entry; 1 pair) | 1 | each | 3400 | 3400 | CAD | RATE_TABLE | Building_Envelope_Rates.csv BE-12 | MED | One double-door pair | EST_DEL-02-01_2026-02-18_2100
DEL-02-01::L-003 | DEL-02-01 | PKG-002 | L-003 | 3300 | PKG-002 | DEL-02-01 | Door hardware sets — commercial (all interior openings; 19 sets) | 19 | each | 600 | 11400 | CAD | RATE_TABLE | Building_Envelope_Rates.csv BE-13 | MED | 19 openings per ASM-004 | EST_DEL-02-01_2026-02-18_2100
DEL-02-01::L-004 | DEL-02-01 | PKG-002 | L-004 | 3200 | PKG-002 | DEL-02-01 | Interior partition walls — metal stud and gypsum board (~325 m2) | 325 | m2 | 93 | 30225 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv IA-01/IA-02/IA-04 blended (70/20/10) | MED | Previously TBD; resolved via PS-27 | EST_DEL-02-01_2026-02-18_2100
DEL-02-01::L-005 | DEL-02-01 | PKG-002 | L-005 | 3400 | PKG-002 | DEL-02-01 | Sealed concrete floor finish — densifier + sealer (~483 m2) | 483 | m2 | 35 | 16905 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv IA-08 | MED | Previously TBD; resolved via PS-27 | EST_DEL-02-01_2026-02-18_2100
DEL-02-01::L-006 | DEL-02-01 | PKG-002 | L-006 | 3400 | PKG-002 | DEL-02-01 | Ceiling system — suspended acoustical ceiling tile (~483 m2) | 483 | m2 | 68 | 32844 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv IA-05 | MED | Previously TBD; resolved via PS-27 | EST_DEL-02-01_2026-02-18_2100
DEL-02-01::L-007 | DEL-02-01 | PKG-002 | L-007 | 3500 | PKG-002 | DEL-02-01 | Accessibility features — barrier-free washrooms and accessible routes | 1 | LS | 9490 | 9490 | CAD | RATE_TABLE | IA-15/16/17/18 composite | MED | Previously TBD; resolved via PS-27 | EST_DEL-02-01_2026-02-18_2100
DEL-02-01::L-008 | DEL-02-01 | PKG-002 | L-008 | 3600 | PKG-002 | DEL-02-01 | Code-required signage — exit + room ID + fire safety | 1 | LS | 11520 | 11520 | CAD | RATE_TABLE | IA-19/20/21 composite | MED | Previously TBD; resolved via PS-27 | EST_DEL-02-01_2026-02-18_2100
DEL-02-01::L-009 | DEL-02-01 | PKG-002 | L-009 | 3400 | PKG-002 | DEL-02-01 | Interior paint — wall finishes (~650 m2) | 650 | m2 | 14.05 | 9133 | CAD | RATE_TABLE | IA-12/IA-13 blended (85/15) | MED | Previously TBD; resolved via PS-27 | EST_DEL-02-01_2026-02-18_2100
DEL-02-01::L-010 | DEL-02-01 | PKG-002 | L-010 | 3100 | PKG-002 | DEL-02-01 | Architectural design fees — 7% of DEL-02-01 construction cost | 1 | LS | 11012 | 11012 | CAD | RATE_TABLE | Professional_Design_Fees.csv DF-01 (7% of $157317) | MED | Previously TBD; now computable | EST_DEL-02-01_2026-02-18_2100
DEL-02-02::L-001 | DEL-02-02 | PKG-002 | L-001 | 03-CONCRETE | PKG-002 | DEL-02-02 | Sealed concrete floor finish -- 4 fire apparatus bays (780 m2 total; 4 bays x 2100 sf = 8400 sf) | 780 | m2 | 35 | 27300 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-08; Assumed_Project_Parameters.csv / PP-11 (4 bays) and PP-05 (bay area ~2100 sf each from Datasheet) | MED | Bay area midpoint 2100 sf per Addendum 03 s1.21 (2000-2200 sf range). Densifier + sealer per IA-08 description. See ASM-001. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-002 | DEL-02-02 | PKG-002 | L-002 | 09-FINISHES | PKG-002 | DEL-02-02 | Exposed structure paint -- 4 fire apparatus bay ceilings (780 m2) | 780 | m2 | 22 | 17160 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-07; Assumed_Project_Parameters.csv / PP-11 | MED | Spray-apply latex to exposed deck/joists in bay area. Same 780 m2 as bay floor area. See ASM-001. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-003 | DEL-02-02 | PKG-002 | L-003 | 10-SPECIALTIES | PKG-002 | DEL-02-02 | Bunker gear lockers -- heavy-duty ventilated (40 units) | 40 | each | 2200 | 88000 | CAD | RATE_TABLE | Equipment_Pricing.csv / EQ-06; Assumed_Project_Parameters.csv / PP-15 | MED | Quantity confirmed at 40 per Addendum 03 s1.13 and PP-15. Rate $2200 is midpoint of $1800-$2500 range. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-004 | DEL-02-02 | PKG-002 | L-004 | 11-EQUIPMENT | PKG-002 | DEL-02-02 | Breathing air compressor system -- fire service complete (1 system) | 1 | LS | 55000 | 55000 | CAD | RATE_TABLE | Equipment_Pricing.csv / EQ-08; Mechanical_System_Rates.csv / MS-08 | LOW | Both sources consistent ($45k-$65k range). Includes compressor + dryer + storage + fill panels + distribution piping within SCBA room. Resolves CON-M-01 per cost ownership rules. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-005 | DEL-02-02 | PKG-002 | L-005 | 23-MECH | PKG-002 | DEL-02-02 | Compressed air distribution piping -- from compressor room to 4 apparatus bays (ceiling drops) | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | Decision_Log.md / DEC-EST-003; Equipment_Pricing.csv / EQ-08 Notes | LOW | No direct rate table entry for piping distribution. Allowance based on 4 bays x typical 15-25m piping runs + ceiling drop assemblies + valves. FALLBACK_POLICY=ALLOW_ALLOWANCE applied. See ASM-003. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-006 | DEL-02-02 | PKG-002 | L-006 | 22-PLUMBING | PKG-002 | DEL-02-02 | Bay sump assemblies -- oil/water separator type (4 fire bays) | 4 | each | 4500 | 18000 | CAD | RATE_TABLE | Mechanical_System_Rates.csv / MS-10; Equipment_Pricing.csv / EQ-10; Assumed_Project_Parameters.csv / PP-18 | MED | 4 fire apparatus bays. Rate $4500 per MS-10/EQ-10. Includes floor drain + trap + separator + sanitary connection. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-007 | DEL-02-02 | PKG-002 | L-007 | 09-FINISHES | PKG-002 | DEL-02-02 | Decon area -- wet area partitions (steel stud + cement board; 50 m2) | 50 | m2 | 132 | 6600 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-04 | MED | Interior partition walls for decon room and shower/WR areas. Moisture-resistant GWB + cement board. See ASM-002. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-008 | DEL-02-02 | PKG-002 | L-008 | 09-FINISHES | PKG-002 | DEL-02-02 | Decon area -- ceramic tile flooring (decon room + shower/WR; 26.5 m2) | 26.5 | m2 | 118 | 3127 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-10 | MED | Commercial grade ceramic tile for wet areas. Decon room 16.3 m2 + 2x shower/WR 10.2 m2. See ASM-002. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-009 | DEL-02-02 | PKG-002 | L-009 | 09-FINISHES | PKG-002 | DEL-02-02 | Decon area -- ceramic tile walls in shower zones (20 m2) | 20 | m2 | 118 | 2360 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-10 | MED | Shower/WR wall tile to ceiling height. See ASM-002. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-010 | DEL-02-02 | PKG-002 | L-010 | 09-FINISHES | PKG-002 | DEL-02-02 | Decon area -- epoxy/semi-gloss paint on remaining walls (30 m2) | 30 | m2 | 20 | 600 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-13 | MED | Washable finish for cleaning-intensive decon areas. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-011 | DEL-02-02 | PKG-002 | L-011 | 10-SPECIALTIES | PKG-002 | DEL-02-02 | Decon area -- washroom accessories (2 washroom/shower rooms) | 2 | each | 800 | 1600 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-24 | MED | Dispensers + mirrors + shelves per shower/WR unit. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-012 | DEL-02-02 | PKG-002 | L-012 | 10-SPECIALTIES | PKG-002 | DEL-02-02 | Decon area -- toilet partitions (2 stalls) | 2 | each | 1500 | 3000 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-25 | MED | Phenolic or solid plastic; floor-mounted overhead-braced. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-013 | DEL-02-02 | PKG-002 | L-013 | 09-FINISHES | PKG-002 | DEL-02-02 | Bunker gear locker room -- non-rated partitions (30 m2) | 30 | m2 | 82 | 2460 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-02 | MED | Steel stud + 1-layer GWB both sides. Room area ~42 m2 (450 sf midpoint). See ASM-004. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-014 | DEL-02-02 | PKG-002 | L-014 | 03-CONCRETE | PKG-002 | DEL-02-02 | Bunker gear locker room -- sealed concrete floor (41.8 m2) | 41.8 | m2 | 35 | 1463 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-08 | MED | Densifier + sealer. See ASM-004. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-015 | DEL-02-02 | PKG-002 | L-015 | 09-FINISHES | PKG-002 | DEL-02-02 | Bunker gear locker room -- suspended ACT ceiling (41.8 m2) | 41.8 | m2 | 68 | 2842 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-05 | MED | 600x600 lay-in mineral fibre with seismic clips. See ASM-004. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-016 | DEL-02-02 | PKG-002 | L-016 | 09-FINISHES | PKG-002 | DEL-02-02 | Bunker gear locker room -- paint walls (60 m2) | 60 | m2 | 13 | 780 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-12 | MED | 2 coats latex on drywall. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-017 | DEL-02-02 | PKG-002 | L-017 | 09-FINISHES | PKG-002 | DEL-02-02 | Fire gear storage room -- non-rated partitions (20 m2) | 20 | m2 | 82 | 1640 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-02 | MED | Room area ~25.5 m2 (275 sf midpoint). See ASM-005. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-018 | DEL-02-02 | PKG-002 | L-018 | 03-CONCRETE | PKG-002 | DEL-02-02 | Fire gear storage room -- sealed concrete floor (25.5 m2) | 25.5 | m2 | 35 | 893 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-08 | MED | See ASM-005. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-019 | DEL-02-02 | PKG-002 | L-019 | 09-FINISHES | PKG-002 | DEL-02-02 | Fire gear storage room -- suspended ACT ceiling (25.5 m2) | 25.5 | m2 | 68 | 1734 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-05 | MED | See ASM-005. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-020 | DEL-02-02 | PKG-002 | L-020 | 09-FINISHES | PKG-002 | DEL-02-02 | Fire gear storage room -- paint walls (40 m2) | 40 | m2 | 13 | 520 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-12 | MED | See ASM-005. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-021 | DEL-02-02 | PKG-002 | L-021 | 09-FINISHES | PKG-002 | DEL-02-02 | Fire gear storage room -- hollow metal door + hardware (1 opening) | 1 | each | 2400 | 2400 | CAD | RATE_TABLE | Building_Envelope_Rates.csv / BE-11 ($1800) + BE-13 ($600) | MED | Single HM door + frame + lever handle/closer/hinges set. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-022 | DEL-02-02 | PKG-002 | L-022 | 09-FINISHES | PKG-002 | DEL-02-02 | SCBA/cascade room -- non-rated partitions (18 m2) | 18 | m2 | 82 | 1476 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-02 | MED | Room area ~16.3 m2 (175 sf midpoint). See ASM-006. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-023 | DEL-02-02 | PKG-002 | L-023 | 03-CONCRETE | PKG-002 | DEL-02-02 | SCBA/cascade room -- sealed concrete floor (16.3 m2) | 16.3 | m2 | 35 | 571 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-08 | MED | See ASM-006. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-024 | DEL-02-02 | PKG-002 | L-024 | 09-FINISHES | PKG-002 | DEL-02-02 | SCBA/cascade room -- exposed ceiling paint (16.3 m2) | 16.3 | m2 | 22 | 359 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-07 | MED | Exposed structure for equipment access. See ASM-006. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-025 | DEL-02-02 | PKG-002 | L-025 | 09-FINISHES | PKG-002 | DEL-02-02 | SCBA/cascade room -- paint walls (36 m2) | 36 | m2 | 13 | 468 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-12 | MED | See ASM-006. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-026 | DEL-02-02 | PKG-002 | L-026 | 09-FINISHES | PKG-002 | DEL-02-02 | SCBA/cascade room -- hollow metal door + hardware (1 opening) | 1 | each | 2400 | 2400 | CAD | RATE_TABLE | Building_Envelope_Rates.csv / BE-11 ($1800) + BE-13 ($600) | MED | Single HM door + frame + hardware set. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-027 | DEL-02-02 | PKG-002 | L-027 | 09-FINISHES | PKG-002 | DEL-02-02 | Compressor room -- fire-rated partitions 1-hr (16 m2) | 16 | m2 | 112 | 1792 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-01 | MED | Fire-rated due to compressor equipment. Room area ~11.6 m2 (125 sf midpoint). See ASM-007. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-028 | DEL-02-02 | PKG-002 | L-028 | 03-CONCRETE | PKG-002 | DEL-02-02 | Compressor room -- sealed concrete floor (11.6 m2) | 11.6 | m2 | 35 | 406 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-08 | MED | See ASM-007. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-029 | DEL-02-02 | PKG-002 | L-029 | 09-FINISHES | PKG-002 | DEL-02-02 | Compressor room -- exposed ceiling paint (11.6 m2) | 11.6 | m2 | 22 | 255 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-07 | MED | Exposed for equipment access. See ASM-007. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-030 | DEL-02-02 | PKG-002 | L-030 | 09-FINISHES | PKG-002 | DEL-02-02 | Compressor room -- paint walls (32 m2) | 32 | m2 | 13 | 416 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-12 | MED | See ASM-007. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-031 | DEL-02-02 | PKG-002 | L-031 | 09-FINISHES | PKG-002 | DEL-02-02 | Compressor room -- hollow metal door + hardware (1 opening) | 1 | each | 2400 | 2400 | CAD | RATE_TABLE | Building_Envelope_Rates.csv / BE-11 ($1800) + BE-13 ($600) | MED | Single HM door + frame + hardware set. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-032 | DEL-02-02 | PKG-002 | L-032 | 09-FINISHES | PKG-002 | DEL-02-02 | Medical/EMS storage room -- non-rated partitions (10 m2) | 10 | m2 | 82 | 820 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-02 | MED | Room area ~5.6 m2 (60 sf midpoint). See ASM-008. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-033 | DEL-02-02 | PKG-002 | L-033 | 03-CONCRETE | PKG-002 | DEL-02-02 | Medical/EMS storage room -- sealed concrete floor (5.6 m2) | 5.6 | m2 | 35 | 196 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-08 | MED | See ASM-008. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-034 | DEL-02-02 | PKG-002 | L-034 | 09-FINISHES | PKG-002 | DEL-02-02 | Medical/EMS storage room -- suspended ACT ceiling (5.6 m2) | 5.6 | m2 | 68 | 381 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-05 | MED | See ASM-008. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-035 | DEL-02-02 | PKG-002 | L-035 | 09-FINISHES | PKG-002 | DEL-02-02 | Medical/EMS storage room -- paint walls (20 m2) | 20 | m2 | 13 | 260 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv / IA-12 | MED | See ASM-008. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-036 | DEL-02-02 | PKG-002 | L-036 | 09-FINISHES | PKG-002 | DEL-02-02 | Medical/EMS storage room -- hollow metal door + hardware (1 opening) | 1 | each | 2400 | 2400 | CAD | RATE_TABLE | Building_Envelope_Rates.csv / BE-11 ($1800) + BE-13 ($600) | MED | Single HM door + frame + hardware set. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-037 | DEL-02-02 | PKG-002 | L-037 | 09-FINISHES | PKG-002 | DEL-02-02 | Decon area -- hollow metal door + hardware (2 openings) | 2 | each | 2400 | 4800 | CAD | RATE_TABLE | Building_Envelope_Rates.csv / BE-11 ($1800) + BE-13 ($600) | MED | Decon room entry + shower/WR access. 2 openings. | EST_DEL-02-02_2026-02-18_1036
DEL-02-02::L-038 | DEL-02-02 | PKG-002 | L-038 | 09-FINISHES | PKG-002 | DEL-02-02 | Bunker gear locker room -- hollow metal door + hardware (1 opening) | 1 | each | 2400 | 2400 | CAD | RATE_TABLE | Building_Envelope_Rates.csv / BE-11 ($1800) + BE-13 ($600) | MED | Main entry to locker room. | EST_DEL-02-02_2026-02-18_1036
DEL-02-03::L-001 | DEL-02-03 | PKG-002 | L-001 | 21.03.01 | PKG-002 | DEL-02-03 | Sealed concrete floor finish — PW shop bays (densifier + sealer; grind + polish) | 780 | m2 | 35 | 27300 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-08 | MED | 4 bays x 2100 sf/bay = 8400 sf = 780 m2; rate from IA-08 RecommendedRate $35/m2 | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-002 | DEL-02-03 | PKG-002 | L-002 | 21.03.01 | PKG-002 | DEL-02-03 | Sealed concrete floor finish — workshop area | 74 | m2 | 35 | 2590 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-08 | MED | 800 sf workshop = 74 m2; same finish as bays | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-003 | DEL-02-03 | PKG-002 | L-003 | 21.03.01 | PKG-002 | DEL-02-03 | Sealed concrete floor finish — warehouse/storage area | 56 | m2 | 35 | 1960 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-08 | MED | 600 sf storage = 56 m2; same finish as bays | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-004 | DEL-02-03 | PKG-002 | L-004 | 21.03.02 | PKG-002 | DEL-02-03 | Exposed structure paint — PW shop bay ceilings | 780 | m2 | 22 | 17160 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-07 | MED | Spray-apply latex to exposed structure in 4 bays | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-005 | DEL-02-03 | PKG-002 | L-005 | 21.03.02 | PKG-002 | DEL-02-03 | Exposed structure paint — workshop ceiling | 74 | m2 | 22 | 1628 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-07 | MED | Workshop area ceiling | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-006 | DEL-02-03 | PKG-002 | L-006 | 21.03.02 | PKG-002 | DEL-02-03 | Compressed air piping — hard-plumbed through bays | 1 | LS | 15000 | 15000 | CAD | ALLOWANCE | Assumptions_Log.md#ASM-008 | LOW | Functional Program Rows 27-28 require hard-plumbed air lines; no rate table item; allowance used per FALLBACK_POLICY | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-007 | DEL-02-03 | PKG-002 | L-007 | 21.03.02 | PKG-002 | DEL-02-03 | Shop bay interior wall paint (epoxy/semi-gloss; washable) | 320 | m2 | 20 | 6400 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-13 | MED | Bay perimeter walls within PW zone; estimated 320 m2 total wall area across 4 bays | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-008 | DEL-02-03 | PKG-002 | L-008 | 21.03.03 | PKG-002 | DEL-02-03 | Workshop workbench and welding area fit-up | 1 | LS | 22000 | 22000 | CAD | ALLOWANCE | Equipment_Pricing.csv#EQ-13 | LOW | Workshop equipment allowance: bench grinder; drill press; workbench; storage; per PW functional needs | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-009 | DEL-02-03 | PKG-002 | L-009 | 21.03.03 | PKG-002 | DEL-02-03 | Warehouse/parts storage shelving and racking | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | Assumptions_Log.md#ASM-009 | LOW | Industrial shelving/racking for parts storage; no rate table item; allowance per FALLBACK_POLICY | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-010 | DEL-02-03 | PKG-002 | L-010 | 21.03.04 | PKG-002 | DEL-02-03 | PW lockers — heavy-duty full-height (40 units) | 40 | each | 1000 | 40000 | CAD | RATE_TABLE | Equipment_Pricing.csv#EQ-07 | MED | 40 standard heavy-duty personnel lockers per functional program; RecommendedPrice $1000/each | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-011 | DEL-02-03 | PKG-002 | L-011 | 21.03.04 | PKG-002 | DEL-02-03 | PPE/locker room — ceramic tile flooring (shower/wet areas) | 56 | m2 | 118 | 6608 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-10 | MED | Shower and change area wet zones; ~600 sf = 56 m2; rate from IA-10 | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-012 | DEL-02-03 | PKG-002 | L-012 | 21.03.04 | PKG-002 | DEL-02-03 | PPE/locker room — sealed concrete flooring (dry areas) | 55 | m2 | 35 | 1925 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-08 | MED | Dry locker area; ~600 sf = 55 m2 | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-013 | DEL-02-03 | PKG-002 | L-013 | 21.03.04 | PKG-002 | DEL-02-03 | PPE/locker room — moisture-resistant partitions | 65 | m2 | 132 | 8580 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-04 | MED | Shower stall partitions and wet area walls; ~65 m2 estimated | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-014 | DEL-02-03 | PKG-002 | L-014 | 21.03.04 | PKG-002 | DEL-02-03 | PPE/locker room — suspended gypsum ceiling (washroom/shower) | 111 | m2 | 102 | 11322 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-06 | MED | Full locker room area 1200 sf = 111 m2; moisture-rated ceiling | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-015 | DEL-02-03 | PKG-002 | L-015 | 21.03.04 | PKG-002 | DEL-02-03 | PPE/locker room — epoxy wall paint | 180 | m2 | 20 | 3600 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-13 | MED | All locker room walls; estimated 180 m2 | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-016 | DEL-02-03 | PKG-002 | L-016 | 21.03.04 | PKG-002 | DEL-02-03 | PPE/locker room — washroom accessories package (2 washrooms) | 2 | each | 800 | 1600 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-24 | MED | Dispensers + mirrors + shelves per washroom | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-017 | DEL-02-03 | PKG-002 | L-017 | 21.03.04 | PKG-002 | DEL-02-03 | PPE/locker room — toilet partitions (4 stalls) | 4 | each | 1500 | 6000 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-25 | MED | Phenolic partitions; 2 per washroom x 2 washrooms | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-018 | DEL-02-03 | PKG-002 | L-018 | 21.03.04 | PKG-002 | DEL-02-03 | PPE/locker room — grab bars + accessible fittings (2 washrooms) | 2 | each | 1100 | 2200 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-17 | MED | Stainless steel grab bars per accessible washroom | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-019 | DEL-02-03 | PKG-002 | L-019 | 21.03.04 | PKG-002 | DEL-02-03 | PPE/locker room — vanity countertops | 3 | lm | 575 | 1725 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-22 | MED | Solid surface countertops; ~3 lm total across 2 washroom vanities | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-020 | DEL-02-03 | PKG-002 | L-020 | 21.03.04 | PKG-002 | DEL-02-03 | PPE/first aid room — fit-up | 1 | LS | 3500 | 3500 | CAD | ALLOWANCE | Assumptions_Log.md#ASM-010 | LOW | First aid equipment; PPE storage; food washing area; 100-150 sf room; no rate table item | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-021 | DEL-02-03 | PKG-002 | L-021 | 21.03.05 | PKG-002 | DEL-02-03 | Shop office — sealed concrete floor | 19 | m2 | 35 | 665 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-08 | MED | 200 sf = 19 m2; sealed concrete per OSR direction | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-022 | DEL-02-03 | PKG-002 | L-022 | 21.03.05 | PKG-002 | DEL-02-03 | Shop office — suspended acoustic tile ceiling | 19 | m2 | 68 | 1292 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-05 | MED | Standard T-bar ACT for office area | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-023 | DEL-02-03 | PKG-002 | L-023 | 21.03.05 | PKG-002 | DEL-02-03 | Shop office — wall paint (standard latex) | 50 | m2 | 13 | 650 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-12 | MED | Office perimeter walls; ~50 m2 estimated | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-024 | DEL-02-03 | PKG-002 | L-024 | 21.03.05 | PKG-002 | DEL-02-03 | Shop washroom — ceramic tile floor | 9 | m2 | 118 | 1062 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-10 | MED | 100 sf = 9 m2; washroom floor | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-025 | DEL-02-03 | PKG-002 | L-025 | 21.03.05 | PKG-002 | DEL-02-03 | Shop washroom — moisture-resistant partitions | 18 | m2 | 132 | 2376 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-04 | MED | Washroom walls; ~18 m2 | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-026 | DEL-02-03 | PKG-002 | L-026 | 21.03.05 | PKG-002 | DEL-02-03 | Shop washroom — suspended gypsum ceiling | 9 | m2 | 102 | 918 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-06 | MED | Moisture-rated ceiling | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-027 | DEL-02-03 | PKG-002 | L-027 | 21.03.05 | PKG-002 | DEL-02-03 | Shop washroom — epoxy wall paint | 18 | m2 | 20 | 360 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-13 | MED | Epoxy paint for wet area | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-028 | DEL-02-03 | PKG-002 | L-028 | 21.03.05 | PKG-002 | DEL-02-03 | Shop washroom — accessories package | 1 | each | 800 | 800 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-24 | MED | Dispensers + mirrors + shelves | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-029 | DEL-02-03 | PKG-002 | L-029 | 21.03.05 | PKG-002 | DEL-02-03 | Shop washroom — grab bars + accessible fittings | 1 | each | 1100 | 1100 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-17 | MED | Accessible washroom per ABC | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-030 | DEL-02-03 | PKG-002 | L-030 | 21.03.05 | PKG-002 | DEL-02-03 | Shop washroom — toilet partition | 1 | each | 1500 | 1500 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-25 | MED | Single stall partition | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-031 | DEL-02-03 | PKG-002 | L-031 | 21.03.05 | PKG-002 | DEL-02-03 | Shop washroom — vanity countertop | 1 | lm | 575 | 575 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv#IA-22 | MED | Solid surface; 1 lm | EST_DEL-02-03_2026-02-18_1100
DEL-02-03::L-032 | DEL-02-03 | PKG-002 | L-032 | 21.03.04 | PKG-002 | DEL-02-03 | PPE/locker room — shower fixtures and plumbing rough-in (2 standalone showers) | 1 | LS | 8000 | 8000 | CAD | ALLOWANCE | Assumptions_Log.md#ASM-011 | LOW | 2 standalone showers per functional program; includes shower valves + drains + waterproofing; no specific rate table item for showers | EST_DEL-02-03_2026-02-18_1100
DEL-02-04::L-001 | DEL-02-04 | PKG-002 | L-001 | 03-CONCRETE | PKG-002 | DEL-02-04 | Screw piles - installed (galvanized; 6-8m depth; Penhold soils) | 48 | each | 3000 | 144000 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv > SC-14; qty per ASM-07 | MED | Assumed 48 piles at ~3.5m spacing around perimeter + interior column lines; DB to confirm during design | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-002 | DEL-02-04 | PKG-002 | L-002 | 03-CONCRETE | PKG-002 | DEL-02-04 | Pile caps / grade beams - concrete 32 MPa (supplied and placed) | 38 | m3 | 385 | 14630 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv > SC-02; qty per ASM-08 | MED | Pile cap concrete volume: 48 caps x ~0.4m3 avg + grade beams ~19m3 | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-003 | DEL-02-04 | PKG-002 | L-003 | 03-CONCRETE | PKG-002 | DEL-02-04 | Foundation formwork - pile caps and grade beams | 180 | m2 | 65 | 11700 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv > SC-05; qty per ASM-09 | MED | Formwork for pile caps and grade beams combined | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-004 | DEL-02-04 | PKG-002 | L-004 | 03-CONCRETE | PKG-002 | DEL-02-04 | Foundation wall formwork (frost wall / stem wall at perimeter) | 165 | m2 | 75 | 12375 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv > SC-06; qty per ASM-10 | MED | Perimeter frost wall 165 lm x ~1.0m height avg both sides | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-005 | DEL-02-04 | PKG-002 | L-005 | 03-CONCRETE | PKG-002 | DEL-02-04 | Reinforcing steel - foundations (cut/bent/placed) | 4800 | kg | 3.25 | 15600 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv > SC-07; qty per ASM-11 | MED | ~100 kg/pile cap avg + grade beam rebar | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-006 | DEL-02-04 | PKG-002 | L-006 | 03-CONCRETE | PKG-002 | DEL-02-04 | Concrete slab-on-grade - 200mm reinforced (bay areas) | 1115 | m2 | 108 | 120420 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv > SC-04; qty per PP-05 / ASM-03 | MED | Heavy-duty slab for 8 apparatus/shop bays; ~12000 sf = 1115 m2 | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-007 | DEL-02-04 | PKG-002 | L-007 | 03-CONCRETE | PKG-002 | DEL-02-04 | Concrete slab-on-grade - 150mm with W/W mesh (office/shared areas) | 557 | m2 | 85 | 47345 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv > SC-03; qty per PP-05 / ASM-04 | MED | Standard slab for office and shared spaces; ~6000 sf = 557 m2 | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-008 | DEL-02-04 | PKG-002 | L-008 | 03-CONCRETE | PKG-002 | DEL-02-04 | Anchor bolts - set in concrete (column base plates) | 96 | each | 45 | 4320 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv > SC-15; qty per ASM-12 | MED | 2 bolts per pile cap x 48 piles (conservative; some caps may have 4) | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-009 | DEL-02-04 | PKG-002 | L-009 | 05-STEEL | PKG-002 | DEL-02-04 | Structural steel - primary framing (W-shapes and HSS; fabricated and erected) | 42000 | kg | 6.5 | 273000 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv > SC-08; qty per ASM-13 | MED | ~25 kg/m2 of footprint x 1672 m2 = ~42000 kg primary steel | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-010 | DEL-02-04 | PKG-002 | L-010 | 05-STEEL | PKG-002 | DEL-02-04 | Open-web steel joists (roof framing; supplied and erected) | 1672 | m2 | 52 | 86944 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv > SC-10; qty = building footprint area | MED | Clear-span OWSJ for roof over full footprint | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-011 | DEL-02-04 | PKG-002 | L-011 | 05-STEEL | PKG-002 | DEL-02-04 | Metal roof deck (supplied and installed) | 1672 | m2 | 42 | 70224 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv > SC-11; qty = building footprint area | MED | 22 ga or 20 ga deck over full footprint | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-012 | DEL-02-04 | PKG-002 | L-012 | 05-STEEL | PKG-002 | DEL-02-04 | Structural steel - miscellaneous (stairs/handrails/platforms) | 3500 | kg | 9 | 31500 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv > SC-09; qty per ASM-14 | MED | Stairs; mezzanine platforms if any; handrails; embed plates; lintels | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-013 | DEL-02-04 | PKG-002 | L-013 | 07-ENVELOPE | PKG-002 | DEL-02-04 | Insulated metal wall panels (R-20; factory-assembled) | 730 | m2 | 185 | 135050 | CAD | RATE_TABLE | Building_Envelope_Rates.csv > BE-01; qty per ASM-15 | MED | Upper wall cladding above masonry base; net of glazing and OH door openings | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-014 | DEL-02-04 | PKG-002 | L-014 | 07-ENVELOPE | PKG-002 | DEL-02-04 | Concrete masonry unit - 200mm reinforced grouted (base course) | 200 | m2 | 175 | 35000 | CAD | RATE_TABLE | Building_Envelope_Rates.csv > BE-03; qty per ASM-16 | MED | Impact-resistant base course ~1.2m high around perimeter (165 lm x 1.2m) | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-015 | DEL-02-04 | PKG-002 | L-015 | 07-ENVELOPE | PKG-002 | DEL-02-04 | Insulated metal roof panels (R-30; factory-assembled; solar-ready) | 1672 | m2 | 210 | 351120 | CAD | RATE_TABLE | Building_Envelope_Rates.csv > BE-04; qty = building footprint area | MED | Standing seam or through-fastened; includes vapour barrier; structural capacity for future solar loading | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-016 | DEL-02-04 | PKG-002 | L-016 | 07-ENVELOPE | PKG-002 | DEL-02-04 | Air/vapour barrier (self-adhered membrane - walls) | 730 | m2 | 18 | 13140 | CAD | RATE_TABLE | Building_Envelope_Rates.csv > BE-08; qty = net wall panel area | MED | Continuous air barrier at wall panels; lapped and sealed at penetrations | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-017 | DEL-02-04 | PKG-002 | L-017 | 07-ENVELOPE | PKG-002 | DEL-02-04 | Metal flashing and trim (pre-finished; all locations) | 380 | lm | 32 | 12160 | CAD | RATE_TABLE | Building_Envelope_Rates.csv > BE-15; qty per ASM-17 | MED | Corners; drip edges; window heads/sills; parapet cap; base flashing | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-018 | DEL-02-04 | PKG-002 | L-018 | 07-ENVELOPE | PKG-002 | DEL-02-04 | Perimeter sealant (all openings and joints) | 520 | lm | 16 | 8320 | CAD | RATE_TABLE | Building_Envelope_Rates.csv > BE-14; qty per ASM-18 | MED | All window/door/penetration perimeters; panel joints | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-019 | DEL-02-04 | PKG-002 | L-019 | 08-OPENINGS | PKG-002 | DEL-02-04 | Overhead doors (16x16 ft; motorized; insulated; car-wash grade; with windows) | 8 | each | 20000 | 160000 | CAD | RATE_TABLE | Equipment_Pricing.csv > EQ-01; qty per PP-13 | MED | 4 fire apparatus bays + 4 PW shop bays; car-wash grade hardware | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-020 | DEL-02-04 | PKG-002 | L-020 | 08-OPENINGS | PKG-002 | DEL-02-04 | Commercial glazing (double-pane; thermally broken aluminum frame) | 54 | m2 | 650 | 35100 | CAD | RATE_TABLE | Building_Envelope_Rates.csv > BE-09; qty per ASM-19 | MED | ~5% of gross wall area for windows; fixed and operable mix | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-021 | DEL-02-04 | PKG-002 | L-021 | 08-OPENINGS | PKG-002 | DEL-02-04 | Storefront entrance (double door; aluminum frame; glazed) | 2 | each | 8000 | 16000 | CAD | RATE_TABLE | Building_Envelope_Rates.csv > BE-10; qty per ASM-20 | MED | Main public entry + secondary entry; standard operators (no auto-operator) | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-022 | DEL-02-04 | PKG-002 | L-022 | 08-OPENINGS | PKG-002 | DEL-02-04 | Hollow metal door and frame - single (commercial) | 12 | each | 1800 | 21600 | CAD | RATE_TABLE | Building_Envelope_Rates.csv > BE-11; qty per ASM-21 | MED | Person doors at bays and service exits; count per code egress requirements (ASM) | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-023 | DEL-02-04 | PKG-002 | L-023 | 08-OPENINGS | PKG-002 | DEL-02-04 | Hollow metal door and frame - double (commercial) | 2 | each | 3400 | 6800 | CAD | RATE_TABLE | Building_Envelope_Rates.csv > BE-12; qty per ASM-22 | MED | Double doors at main corridor/bay transitions | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-024 | DEL-02-04 | PKG-002 | L-024 | 08-OPENINGS | PKG-002 | DEL-02-04 | Door hardware set (commercial; per opening) | 16 | each | 600 | 9600 | CAD | RATE_TABLE | Building_Envelope_Rates.csv > BE-13; qty = 12 single + 2 double + 2 storefront | MED | Lever handle + closer + hinges + weatherstrip; keyed | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-025 | DEL-02-04 | PKG-002 | L-025 | 09-FLOORING | PKG-002 | DEL-02-04 | Sealed concrete floor (densifier + sealer) - bay areas | 1115 | m2 | 35 | 39025 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv > IA-08; qty per ASM-03 | MED | Densifier + sealer applied to 200mm reinforced bay slab | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-026 | DEL-02-04 | PKG-002 | L-026 | 09-FLOORING | PKG-002 | DEL-02-04 | Sealed concrete floor (densifier + sealer) - office/shared areas | 557 | m2 | 35 | 19495 | CAD | RATE_TABLE | Interior_Architectural_Rates.csv > IA-08; qty per ASM-04 | MED | Sealed concrete acceptable/desired per Addendum 03 and SOW-0217 | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-027 | DEL-02-04 | PKG-002 | L-027 | 31-EARTHWORK | PKG-002 | DEL-02-04 | Sump rough-in blockouts in structural slab (8 locations) | 8 | each | 750 | 6000 | CAD | RATE_TABLE | Assumptions_Log.md > ASM-23; informed by MS-10 reference | LOW | Formwork + blockout + sleeve for sump opening embedded in 200mm slab; assembly/plumbing by DEL-02-05 | EST_DEL-02-04_2026-02-18_1130
DEL-02-04::L-028 | DEL-02-04 | PKG-002 | L-028 | 50-DESIGN | PKG-002 | DEL-02-04 | Structural engineering design fees (2.5% of structural construction cost) | 1 | LS | 20801 | 20801 | CAD | RATE_TABLE | Professional_Design_Fees.csv > DF-03; base per DEC-02 | MED | 2.5% of CBS 03-CONCRETE + 05-STEEL subtotal ($832058); concept through shop drawing review | EST_DEL-02-04_2026-02-18_1130
DEL-02-05::L-01 | DEL-02-05 | PKG-002 | L-01 | 23-HVAC | PKG-002 | DEL-02-05 | HVAC system - institutional/shared areas (complete; RTUs/AHUs; ductwork; controls; diffusers) | 5200 | sf | 32 | 166400 | CAD | RATE_TABLE | Mechanical_System_Rates.csv MS-01 (RecommendedRate $32/sf); PP-05 area zone split per ASM-01 | MED | Heated and cooled office/admin/kitchen/locker areas | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-02 | DEL-02-05 | PKG-002 | L-02 | 23-HVAC | PKG-002 | DEL-02-05 | HVAC system - apparatus bays (heated only; radiant or unit heaters) | 6400 | sf | 21 | 134400 | CAD | RATE_TABLE | Mechanical_System_Rates.csv MS-02 (RecommendedRate $21/sf); PP-05 area zone split per ASM-01 | MED | Simpler distribution; no cooling; 4 fire apparatus bays | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-03 | DEL-02-05 | PKG-002 | L-03 | 23-HVAC | PKG-002 | DEL-02-05 | HVAC system - PW shop bays (heated only; radiant or unit heaters) | 6400 | sf | 21 | 134400 | CAD | RATE_TABLE | Mechanical_System_Rates.csv MS-02 (RecommendedRate $21/sf); PP-05 area zone split per ASM-01 | MED | Simpler distribution; no cooling; 4 PW shop bays | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-04 | DEL-02-05 | PKG-002 | L-04 | 23-PLMB | PKG-002 | DEL-02-05 | Plumbing system - institutional/shared areas (complete; fixtures; piping; water heater; drain/vent) | 5200 | sf | 14 | 72800 | CAD | RATE_TABLE | Mechanical_System_Rates.csv MS-03 (RecommendedRate $14/sf); PP-05 area zone split per ASM-01 | MED | Washrooms; kitchen; showers; laundry rough-in | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-05 | DEL-02-05 | PKG-002 | L-05 | 23-PLMB | PKG-002 | DEL-02-05 | Plumbing system - apparatus/shop bays (minimal fixtures; hose bibs) | 12800 | sf | 6 | 76800 | CAD | RATE_TABLE | Mechanical_System_Rates.csv MS-04 (RecommendedRate $6/sf); combined bay area 6400+6400 | MED | Bay sumps priced separately; this covers hose bibs and basic piping | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-06 | DEL-02-05 | PKG-002 | L-06 | 23-EXHS | PKG-002 | DEL-02-05 | Vehicle exhaust extraction system - apparatus bays (source-capture; per bay) | 4 | each | 25000 | 100000 | CAD | RATE_TABLE | Mechanical_System_Rates.csv MS-06 (RecommendedRate $25000/bay); PP-11 qty=4 | MED | Hose reel + overhead track + fan + duct to exterior; 2 apparatus per bay | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-07 | DEL-02-05 | PKG-002 | L-07 | 23-EXHS | PKG-002 | DEL-02-05 | Shop bay ventilation system - PW bays (supply + exhaust; per bay) | 4 | each | 11000 | 44000 | CAD | RATE_TABLE | Mechanical_System_Rates.csv MS-07 (RecommendedRate $11000/bay); PP-12 qty=4 | MED | Combined supply + exhaust; occasional idling and welding ventilation | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-08 | DEL-02-05 | PKG-002 | L-08 | 23-EQUP | PKG-002 | DEL-02-05 | Water fill station (2-inch; installed; with backflow preventer) | 2 | each | 3500 | 7000 | CAD | RATE_TABLE | Mechanical_System_Rates.csv MS-09 (RecommendedRate $3500/each); PP-17 qty=2 | MED | 1 fire apparatus bay + 1 PW bay; per SOW-0223 | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-09 | DEL-02-05 | PKG-002 | L-09 | 23-EQUP | PKG-002 | DEL-02-05 | Bay sump assembly (oil/water separator type; installed with plumbing connection) | 8 | each | 4500 | 36000 | CAD | RATE_TABLE | Mechanical_System_Rates.csv MS-10 (RecommendedRate $4500/each); PP-18 qty=8 | MED | 4 fire bays + 4 PW bays; assembly + plumbing connection; slab rough-in excluded (DEL-02-04) | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-10 | DEL-02-05 | PKG-002 | L-10 | 23-EQUP | PKG-002 | DEL-02-05 | Domestic hot water heater (commercial; gas-fired; 75-100 gal) | 1 | each | 6000 | 6000 | CAD | RATE_TABLE | Mechanical_System_Rates.csv MS-11 (RecommendedRate $6000/each) | MED | Institutional duty; serves washrooms/showers/kitchen | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-11 | DEL-02-05 | PKG-002 | L-11 | 23-CTRL | PKG-002 | DEL-02-05 | Building automation system (BAS; DDC controls; sensors; programming) | 18000 | sf | 4 | 72000 | CAD | RATE_TABLE | Mechanical_System_Rates.csv MS-12 (RecommendedRate $4/sf); PP-05 full building area | MED | DDC controls; sensors; programming; commissioning | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-12 | DEL-02-05 | PKG-002 | L-12 | 23-FPRT | PKG-002 | DEL-02-05 | Fire protection - wet sprinkler system (institutional; if required by AHJ) | 18000 | sf | 6 | 108000 | CAD | RATE_TABLE | Mechanical_System_Rates.csv MS-05 (RecommendedRate $6/sf); PP-05 full building area | LOW | Conditional on AHJ requirement; may not be required for this occupancy classification | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-13 | DEL-02-05 | PKG-002 | L-13 | 23-PLMB | PKG-002 | DEL-02-05 | Kitchen/laundry plumbing rough-in (stubs to fixture locations) | 1 | LS | 8000 | 8000 | CAD | RATE_TABLE | Construction_Labour_Rates.csv T-05 ($82/hr x ~100 hrs); ASM-05 | MED | Rough-in stubs only; appliance connection by DEL-05-06 if elected | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-14 | DEL-02-05 | PKG-002 | L-14 | 23-PLMB | PKG-002 | DEL-02-05 | Base building mechanical rough-in to wash bay location | 1 | LS | 6000 | 6000 | CAD | RATE_TABLE | Construction_Labour_Rates.csv T-05 ($82/hr x ~73 hrs); ASM-06 | MED | Hot/cold water + drain stub to wash bay location; dedicated equipment by DEL-05-01 | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-15 | DEL-02-05 | PKG-002 | L-15 | 23-MECH-DESIGN | PKG-002 | DEL-02-05 | Mechanical engineering design fees (HVAC + plumbing + fire protection) | 1 | LS | 24295 | 24295 | CAD | RATE_TABLE | Professional_Design_Fees.csv DF-04 (2.5% of mechanical construction cost); DEC-03 | MED | 2.5% of L-01 through L-14 subtotal ($971800); applied to this deliverable per brief cost ownership | EST_DEL-02-05_2026-02-18_1400
DEL-02-05::L-16 | DEL-02-05 | PKG-002 | L-16 | 23-COMM | PKG-002 | DEL-02-05 | System-specific commissioning labour (mechanical balancing; TAB; functional testing) | 1 | LS | 18000 | 18000 | CAD | RATE_TABLE | Construction_Labour_Rates.csv T-05/T-06 blended ($80/hr x ~225 hrs); ASM-07 | MED | Testing air balancing and hydronic balancing; functional performance testing; per brief cost ownership | EST_DEL-02-05_2026-02-18_1400
DEL-02-06::L-0601 | DEL-02-06 | PKG-002 | L-0601 | 26-00 | PKG-002 | DEL-02-06 | Electrical power distribution - institutional/office/shared areas (service entrance to panels to branch circuits to receptacles) | 5200 | sf | 21 | 109200 | CAD | RATE_TABLE | Electrical_System_Rates.csv:ES-01 + Assumed_Project_Parameters.csv:PP-05 + ASM-001 | MED | Institutional areas = 18000 sf total - 12800 sf bay area per ASM-001 | EST_DEL-02-06_2026-02-18_1500
DEL-02-06::L-0602 | DEL-02-06 | PKG-002 | L-0602 | 26-00 | PKG-002 | DEL-02-06 | Electrical power distribution - apparatus/shop bay areas (heavier circuits; welding receptacles; 3-phase) | 12800 | sf | 14 | 179200 | CAD | RATE_TABLE | Electrical_System_Rates.csv:ES-02 + Assumed_Project_Parameters.csv:PP-05 + ASM-001 | MED | Bay areas = 8 bays x ~1600 sf per ASM-001; includes compressed air electrical feed per cost ownership rules | EST_DEL-02-06_2026-02-18_1500
DEL-02-06::L-0603 | DEL-02-06 | PKG-002 | L-0603 | 26-50 | PKG-002 | DEL-02-06 | LED lighting system - institutional/office/shared areas (IES-compliant; fixtures; controls; dimming) | 5200 | sf | 10 | 52000 | CAD | RATE_TABLE | Electrical_System_Rates.csv:ES-03 + ASM-001 | MED | IES-compliant per SOW-0228 | EST_DEL-02-06_2026-02-18_1500
DEL-02-06::L-0604 | DEL-02-06 | PKG-002 | L-0604 | 26-50 | PKG-002 | DEL-02-06 | LED lighting - apparatus/shop bays (high-bay LED; instant-on for emergency response) | 12800 | sf | 6 | 76800 | CAD | RATE_TABLE | Electrical_System_Rates.csv:ES-04 + ASM-001 | MED | High-bay fixtures per SOW-0228 | EST_DEL-02-06_2026-02-18_1500
DEL-02-06::L-0605 | DEL-02-06 | PKG-002 | L-0605 | 27-00 | PKG-002 | DEL-02-06 | IT/telecom data drops (Cat 6A cable; termination; patch panel port; tested) | 45 | each | 850 | 38250 | CAD | RATE_TABLE | Electrical_System_Rates.csv:ES-06 + Assumed_Project_Parameters.csv:PP-27 | MED | 45 drops per PP-27; includes 15 meeting room EM workstations per SOW-0208 | EST_DEL-02-06_2026-02-18_1500
DEL-02-06::L-0606 | DEL-02-06 | PKG-002 | L-0606 | 27-00 | PKG-002 | DEL-02-06 | IT backbone infrastructure (fibre + MDF/IDF rooms; racks; UPS) | 1 | LS | 32000 | 32000 | CAD | RATE_TABLE | Electrical_System_Rates.csv:ES-07 | MED | Main + intermediate distribution frames; provides infrastructure that access control connects to | EST_DEL-02-06_2026-02-18_1500
DEL-02-06::L-0607 | DEL-02-06 | PKG-002 | L-0607 | 27-50 | PKG-002 | DEL-02-06 | PA/paging system - building-wide (amplifier; speakers; zone control; microphone stations) | 1 | LS | 20000 | 20000 | CAD | RATE_TABLE | Electrical_System_Rates.csv:ES-09 | MED | Simple PA per SOW-0226; rate cross-referenced with Equipment_Pricing.csv:EQ-12 | EST_DEL-02-06_2026-02-18_1500
DEL-02-06::L-0608 | DEL-02-06 | PKG-002 | L-0608 | 27-00 | PKG-002 | DEL-02-06 | Apparatus bay display systems (55-inch commercial display + mount + power + data; 4 bays) | 4 | each | 2500 | 10000 | CAD | RATE_TABLE | Electrical_System_Rates.csv:ES-10 + Equipment_Pricing.csv:EQ-11 | MED | Emergency info display per SOW-0225; 4 fire apparatus bays | EST_DEL-02-06_2026-02-18_1500
DEL-02-06::L-0609 | DEL-02-06 | PKG-002 | L-0609 | 26-50 | PKG-002 | DEL-02-06 | Emergency lighting system (battery units; exit signs; egress lighting; per code) | 18000 | sf | 2.5 | 45000 | CAD | RATE_TABLE | Electrical_System_Rates.csv:ES-11 | MED | Full building area per PP-05; per SOW-0228 code requirement | EST_DEL-02-06_2026-02-18_1500
DEL-02-06::L-0610 | DEL-02-06 | PKG-002 | L-0610 | 26-10 | PKG-002 | DEL-02-06 | Solar-ready electrical provisions (conduit run; reserved panel space; labelled disconnect; no PV panels) | 1 | LS | 12000 | 12000 | CAD | RATE_TABLE | Electrical_System_Rates.csv:ES-13 | MED | Solar-capable roof per SOW-0221; electrical provisions only | EST_DEL-02-06_2026-02-18_1500
DEL-02-06::L-0611 | DEL-02-06 | PKG-002 | L-0611 | 26-00 | PKG-002 | DEL-02-06 | Electrical service entrance (600A; 347/600V 3-phase; switchboard; metering) | 1 | LS | 45000 | 45000 | CAD | RATE_TABLE | Electrical_System_Rates.csv:ES-14 | MED | Service entrance up to generator transfer point per cost ownership rules; excludes ATS/generator (DEL-02-07) | EST_DEL-02-06_2026-02-18_1500
DEL-02-06::L-0612 | DEL-02-06 | PKG-002 | L-0612 | 26-80 | PKG-002 | DEL-02-06 | System-specific commissioning labor - electrical/lighting/IT/PA testing and verification | 100 | hr | 80 | 8000 | CAD | RATE_TABLE | Construction_Labour_Rates.csv:T-07 + ASM-002 | MED | 100 hours estimated per ASM-002; T-07 Electrician fully-burdened rate; does not include DEL-01-07 general commissioning coordination | EST_DEL-02-06_2026-02-18_1500
DEL-02-06::L-0613 | DEL-02-06 | PKG-002 | L-0613 | 26-90 | PKG-002 | DEL-02-06 | Electrical engineering design fees (power + lighting + IT/telecom + fire alarm design) | 1 | LS | 15486 | 15486 | CAD | RATE_TABLE | Professional_Design_Fees.csv:DF-05 | MED | 2.5% of electrical construction subtotal ($619450); per DF-05 recommended percentage | EST_DEL-02-06_2026-02-18_1500
DEL-02-07::L-0207-010 | DEL-02-07 | PKG-002 | L-0207-010 | 26-EMRG-GEN | PKG-002 | DEL-02-07 | Diesel generator system (100-150 kW complete: genset + ATS + fuel tank 72-hr + concrete pad + exhaust system + sound attenuation + commissioning) | 1 | LS | 150000 | 150000 | CAD | ALLOWANCE | Equipment_Pricing.csv / EQ-04 (RecommendedPrice=$150000; Range=$120k-$180k) | LOW | No vendor quote; ALLOWANCE fallback from parametric source. EQ-05 ATS ($12k) noted as included in EQ-04 system price. Requires vendor quote replacement. | EST_DEL-02-07_2026-02-18_1600
DEL-02-07::L-0207-020 | DEL-02-07 | PKG-002 | L-0207-020 | 26-EMRG-DIST | PKG-002 | DEL-02-07 | Emergency power distribution from generator to essential loads (sub-panel + wiring + breakers for kitchen + meeting/command room + 2 bathrooms + emergency lighting) | 1 | LS | 18000 | 18000 | CAD | ALLOWANCE | Decision_Log.md / DEC-EST-003; Assumptions_Log.md / ASM-005 | LOW | Estimated as ~12% of generator system cost. No quote available. Covers dedicated sub-panel and branch circuits to essential loads only. Normal building distribution is DEL-02-06. | EST_DEL-02-07_2026-02-18_1600
DEL-02-07::L-0207-030 | DEL-02-07 | PKG-002 | L-0207-030 | 26-EMRG-DOOR | PKG-002 | DEL-02-07 | Overhead door backup power mechanism integration (8 bay doors — battery backup motor or UPS for door openers) | 1 | LS | 16000 | 16000 | CAD | ALLOWANCE | Decision_Log.md / DEC-EST-004; Assumptions_Log.md / ASM-006 | LOW | 8 doors x $2000/door assumed. Could be battery backup units or generator-fed circuits per door. Mechanism type TBD pending design. Cost ownership confirmed: DEL-02-07 owns backup mechanism; DEL-02-04 owns doors. | EST_DEL-02-07_2026-02-18_1600
DEL-02-07::L-0207-040 | DEL-02-07 | PKG-002 | L-0207-040 | 26-EMRG-GEN | PKG-002 | DEL-02-07 | Generator installation labour (electrician + millwright + crane operator for equipment setting) | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | Construction_Labour_Rates.csv / T-07 ($80/hr) + T-13 ($80/hr) + T-14 ($86/hr); Assumptions_Log.md / ASM-007 | LOW | Estimated: Electrician 60 hrs ($4800) + Millwright 40 hrs ($3200) + Crane 2 days ($3440) + misc ($560). Actual labour included partially in EQ-04 system price; this line captures incremental site-specific installation scope. | EST_DEL-02-07_2026-02-18_1600
DEL-02-07::L-0207-050 | DEL-02-07 | PKG-002 | L-0207-050 | 26-EMRG-DES | PKG-002 | DEL-02-07 | Electrical engineering design fees — generator sizing + specification + essential loads analysis | 1 | LS | 5000 | 5000 | CAD | ALLOWANCE | Professional_Design_Fees.csv / DF-05 (2.5% of electrical construction); Assumptions_Log.md / ASM-008 | LOW | Generator-specific design portion only. DF-05 basis = 2.5% of DEL-02-07 construction cost (~$196k) = ~$4900 rounded to $5000. Full building electrical design is in DEL-02-06. | EST_DEL-02-07_2026-02-18_1600
DEL-03-01::L-001 | DEL-03-01 | PKG-003 | L-001 | 03-DESIGN | PKG-003 | DEL-03-01 | Civil engineering design fees — DEL-03-01 share (site plan / circulation / parking layout design) | 1 | LS | 13500 | 13500 | CAD | RATE_TABLE | Professional_Design_Fees.csv DF-02 + Assumed_Project_Parameters.csv PP-23; apportionment per ASM-001 | LOW | DF-02 rate: 2.5% of site/civil construction cost ($1,800,000 PP-23) = $45,000 total civil design fee. DEL-03-01 apportioned at 30% = $13,500. See ASM-001 for apportionment basis. PP-23 is LOW confidence. | EST_DEL-03-01_2026-02-18_1900
DEL-03-01::L-002 | DEL-03-01 | PKG-003 | L-002 | 03-SURVEY | PKG-003 | DEL-03-01 | Construction survey and staking — initial site layout (DEL-03-01 share) | 1 | LS | 5000 | 5000 | CAD | RATE_TABLE | Earthwork_Civil_Rates.csv EC-11; apportionment per ASM-002 | MED | EC-11 full site survey = $12,000 LS. DEL-03-01 share (initial layout/staking) apportioned at ~42% = $5,000. Remaining survey effort (progress + as-built) belongs to DEL-01-07 / other deliverables. See ASM-002. | EST_DEL-03-01_2026-02-18_1900
DEL-03-02::L-001 | DEL-03-02 | PKG-003 | L-001 | 03-02-CLR | PKG-003 | DEL-03-02 | Site clearing and grubbing — developed area (~4.5 acres per PP-10) | 4.5 | acre | 4200 | 18900 | CAD | RATE_TABLE | Earthwork_Civil_Rates.csv EC-01; Assumed_Project_Parameters.csv PP-10 | MED | Brush/tree removal and grubbing across developed footprint; moderate vegetation assumed per EC-01 notes | EST_DEL-03-02_2026-02-18_1130
DEL-03-02::L-002 | DEL-03-02 | PKG-003 | L-002 | 03-02-CLR | PKG-003 | DEL-03-02 | Topsoil stripping and stockpiling — developed area (18211 m2 x 0.072 m avg depth = 1311 m3) | 1311 | m3 | 10 | 13110 | CAD | RATE_TABLE | Earthwork_Civil_Rates.csv EC-02; Datasheet.md topsoil avg 72 mm; PP-10 4.5 ac = 18211 m2 | MED | 72 mm avg topsoil per Geotech Report 4.1.3; stockpiled on-site for reuse per EC-02 | EST_DEL-03-02_2026-02-18_1130
DEL-03-02::L-003 | DEL-03-02 | PKG-003 | L-003 | 03-02-EW | PKG-003 | DEL-03-02 | Common excavation (cut to subgrade) — assumed 3000 m3 net cut | 3000 | m3 | 15 | 45000 | CAD | RATE_TABLE | Earthwork_Civil_Rates.csv EC-03; ASM-001 | LOW | Cut quantity TBD per Datasheet item B-001; 3000 m3 is assumption based on generally flat site with minor grade adjustments; see ASM-001 | EST_DEL-03-02_2026-02-18_1130
DEL-03-02::L-004 | DEL-03-02 | PKG-003 | L-004 | 03-02-EW | PKG-003 | DEL-03-02 | Engineered fill (imported granular; placed and compacted) — assumed 2000 m3 net import | 2000 | m3 | 30 | 60000 | CAD | RATE_TABLE | Earthwork_Civil_Rates.csv EC-04; ASM-002 | LOW | Fill quantity TBD per Datasheet item B-001; 2000 m3 assumes partial import for building pads and grade correction; see ASM-002 | EST_DEL-03-02_2026-02-18_1130
DEL-03-02::L-005 | DEL-03-02 | PKG-003 | L-005 | 03-02-EW | PKG-003 | DEL-03-02 | Building pad preparation — main PSB (18000 sf = 1672 m2; 300-450 mm granular base) | 1672 | m2 | 22 | 36784 | CAD | RATE_TABLE | Earthwork_Civil_Rates.csv EC-05; PP-05 18000 sf | MED | Main building footprint 18000 sf per PP-05; granular base compacted and proof-rolled per Geotech Report 5.1.1 | EST_DEL-03-02_2026-02-18_1130
DEL-03-02::L-006 | DEL-03-02 | PKG-003 | L-006 | 03-02-EW | PKG-003 | DEL-03-02 | Building pad preparation — cold storage (6000 sf = 557 m2; 300-450 mm granular base) | 557 | m2 | 22 | 12254 | CAD | RATE_TABLE | Earthwork_Civil_Rates.csv EC-05; PP-07 6000 sf | MED | Cold storage footprint 6000 sf (60x100) per PP-07/DEC-001; foundation type TBD by DB but pad prep is DEL-03-02 scope per brief | EST_DEL-03-02_2026-02-18_1130
DEL-03-02::L-007 | DEL-03-02 | PKG-003 | L-007 | 03-02-EW | PKG-003 | DEL-03-02 | Subgrade compaction (in-situ soils) — building pad areas + access routes (est. 4000 m3) | 4000 | m3 | 6 | 24000 | CAD | RATE_TABLE | Earthwork_Civil_Rates.csv EC-06; ASM-003 | MED | Proof-rolling and nuclear density testing across building pads and primary access routes; see ASM-003 | EST_DEL-03-02_2026-02-18_1130
DEL-03-02::L-008 | DEL-03-02 | PKG-003 | L-008 | 03-02-ESC | PKG-003 | DEL-03-02 | Erosion and sediment control — construction phase (lump sum) | 1 | LS | 22000 | 22000 | CAD | RATE_TABLE | Earthwork_Civil_Rates.csv EC-07 | MED | Silt fence; sediment trap; inlet protection; maintenance; per Alberta ESC guidelines | EST_DEL-03-02_2026-02-18_1130
DEL-03-02::L-009 | DEL-03-02 | PKG-003 | L-009 | 03-02-DRN | PKG-003 | DEL-03-02 | Surface drainage swales — estimated 400 lm across site | 400 | lm | 55 | 22000 | CAD | RATE_TABLE | Earthwork_Civil_Rates.csv EC-08; ASM-004 | LOW | Graded swale with rip-rap at outlets; no storm sewer; overland drainage per OSR 11.2; length is assumption; see ASM-004 | EST_DEL-03-02_2026-02-18_1130
DEL-03-02::L-010 | DEL-03-02 | PKG-003 | L-010 | 03-02-DRN | PKG-003 | DEL-03-02 | Stormwater retention pond — earthwork excavation (est. 2500 m3) | 2500 | m3 | 15 | 37500 | CAD | RATE_TABLE | Earthwork_Civil_Rates.csv EC-03 (excavation rate applied to pond); ASM-005 | LOW | Pond shown on TPN46 Sheets C2-C4; volume is assumption — sizing criteria TBD per REQ-3212/item F-001; see ASM-005 | EST_DEL-03-02_2026-02-18_1130
DEL-03-02::L-011 | DEL-03-02 | PKG-003 | L-011 | 03-02-DRN | PKG-003 | DEL-03-02 | Stormwater retention pond — outlet control and protection (lump sum) | 1 | LS | 15000 | 15000 | CAD | RATE_TABLE | ASM-006; Earthwork_Civil_Rates.csv EC-08 extrapolated | LOW | Outlet structure + rip-rap energy dissipation; no explicit rate in sources; priced via extrapolation from EC-08 drainage rates; see ASM-006 | EST_DEL-03-02_2026-02-18_1130
DEL-03-02::L-012 | DEL-03-02 | PKG-003 | L-012 | 03-02-FIN | PKG-003 | DEL-03-02 | Topsoil replacement and seeding (final grading) — disturbed areas (est. 10000 m2) | 10000 | m2 | 11 | 110000 | CAD | RATE_TABLE | Earthwork_Civil_Rates.csv EC-09; ASM-008 | MED | 150 mm topsoil + hydroseed on disturbed unpaved areas; area is net of building footprints and paved areas; see ASM-008 | EST_DEL-03-02_2026-02-18_1130
DEL-03-02::L-013 | DEL-03-02 | PKG-003 | L-013 | 03-02-SRV | PKG-003 | DEL-03-02 | Construction survey and staking (full site development) | 1 | LS | 12000 | 12000 | CAD | RATE_TABLE | Earthwork_Civil_Rates.csv EC-11 | MED | Initial layout; progress surveys; as-built; for earthworks and grading scope | EST_DEL-03-02_2026-02-18_1130
DEL-03-02::L-014 | DEL-03-02 | PKG-003 | L-014 | 03-02-GEO | PKG-003 | DEL-03-02 | Geotechnical services — compaction testing and subgrade certification | 1 | LS | 32000 | 32000 | CAD | RATE_TABLE | Earthwork_Civil_Rates.csv EC-10; REQ-3214 | MED | Geotech oversight during earthworks; compaction testing per REQ-3207 (1 test/lift/500 m2); subgrade certification per REQ-3214; EC-10 rate used as proxy | EST_DEL-03-02_2026-02-18_1130
DEL-03-02::L-015 | DEL-03-02 | PKG-003 | L-015 | 03-02-DSN | PKG-003 | DEL-03-02 | Civil engineering design fees — earthworks and drainage scope (2.5% of construction subtotal) | 1 | LS | 11514 | 11514 | CAD | RATE_TABLE | Professional_Design_Fees.csv DF-02 (2.5% recommended); ASM-009 | MED | Fee base = sum of L-001 through L-014 ($460548); 2.5% = $11514; see ASM-009 | EST_DEL-03-02_2026-02-18_1130
DEL-03-03::L-001 | DEL-03-03 | PKG-003 | L-001 | 03.03.ASP-HD | PKG-003 | DEL-03-03 | Heavy duty asphalt — fire apparatus routing (Zone A); 150mm HMA on 300mm granular; includes geogrid and geofabric | 2000 | m2 | 92 | 184000 | CAD | RATE_TABLE | Paving_Surfacing_Rates.csv PS-01; Qty per Assumed_Project_Parameters.csv PP-10 (0.5 ac fire routes) + ASM-003 | MED | Rate includes base prep per PS-01 notes. Area assumes ~0.5 ac per PP-10 converted to m2 and rounded. | EST_DEL-03-03_2026-02-18_1200
DEL-03-03::L-002 | DEL-03-03 | PKG-003 | L-002 | 03.03.ASP-LD | PKG-003 | DEL-03-03 | Light duty asphalt — parking near main structure (Zone B); 75mm HMA on 200mm granular; includes geofabric | 3200 | m2 | 60 | 192000 | CAD | RATE_TABLE | Paving_Surfacing_Rates.csv PS-02; Qty per Assumed_Project_Parameters.csv PP-10 (0.8 ac parking) + PP-19 (40 stalls) + ASM-004 | MED | Rate includes base prep per PS-02 notes. Area from PP-10 ~0.8 ac = ~3237 m2 rounded to 3200. | EST_DEL-03-03_2026-02-18_1200
DEL-03-03::L-003 | DEL-03-03 | PKG-003 | L-003 | 03.03.AGG | PKG-003 | DEL-03-03 | Aggregate surfacing — heavy equipment yard areas (Zone C); 150mm crushed gravel compacted per layer | 6000 | m2 | 30 | 180000 | CAD | RATE_TABLE | Paving_Surfacing_Rates.csv PS-03; Qty per Assumed_Project_Parameters.csv PP-10 (1.5 ac yard/storage) + ASM-005 | MED | PS-03 rate covers 150mm. Spec REQ-03-03-05 anticipates 300mm minimum. See L-004 for second lift. | EST_DEL-03-03_2026-02-18_1200
DEL-03-03::L-004 | DEL-03-03 | PKG-003 | L-004 | 03.03.AGG | PKG-003 | DEL-03-03 | Aggregate surfacing — second 150mm lift for 300mm total depth (Zone C) | 6000 | m2 | 30 | 180000 | CAD | RATE_TABLE | Paving_Surfacing_Rates.csv PS-03; ASM-006 (300mm minimum per Spec REQ-03-03-05 assumption) | MED | Second lift to achieve 300mm minimum anticipated by Specification. Rate same as PS-03. | EST_DEL-03-03_2026-02-18_1200
DEL-03-03::L-005 | DEL-03-03 | PKG-003 | L-005 | 03.03.CONC | PKG-003 | DEL-03-03 | Concrete aprons — main building overhead doors (8 doors); 200mm reinforced; sulphate-resistant mix | 312 | m2 | 132 | 41184 | CAD | RATE_TABLE | Paving_Surfacing_Rates.csv PS-04; Qty per PP-13 (8 doors) x 4.88m wide x 8m deep + ASM-007 | MED | 8 doors x 4.88m x 8.0m = 312 m2. Apron depth (8m) is assumed per ASM-007. Dimensions TBD pending PKG-002 architectural. | EST_DEL-03-03_2026-02-18_1200
DEL-03-03::L-006 | DEL-03-03 | PKG-003 | L-006 | 03.03.CONC | PKG-003 | DEL-03-03 | Concrete aprons — cold storage overhead doors (2 doors); 200mm reinforced; sulphate-resistant mix | 78 | m2 | 132 | 10296 | CAD | RATE_TABLE | Paving_Surfacing_Rates.csv PS-04; Qty per PP-14 (2 doors) x 4.88m wide x 8m deep + ASM-008 | MED | 2 doors x 4.88m x 8.0m = 78 m2. Dimensions TBD pending PKG-004 architectural. | EST_DEL-03-03_2026-02-18_1200
DEL-03-03::L-007 | DEL-03-03 | PKG-003 | L-007 | 03.03.CONC | PKG-003 | DEL-03-03 | Concrete curb and gutter — barrier type; parking area perimeter | 250 | lm | 82 | 20500 | CAD | RATE_TABLE | Paving_Surfacing_Rates.csv PS-05; Qty per ASM-009 | MED | Estimated perimeter of parking area. Actual length depends on DEL-03-01 site plan. | EST_DEL-03-03_2026-02-18_1200
DEL-03-03::L-008 | DEL-03-03 | PKG-003 | L-008 | 03.03.CONC | PKG-003 | DEL-03-03 | Concrete sidewalk — accessible routes from parking to main entrance; 100mm broom finish | 150 | m2 | 75 | 11250 | CAD | RATE_TABLE | Paving_Surfacing_Rates.csv PS-06; Qty per ASM-010 | MED | Accessible route from parking to main building entrance. Length/width TBD from site plan. | EST_DEL-03-03_2026-02-18_1200
DEL-03-03::L-009 | DEL-03-03 | PKG-003 | L-009 | 03.03.MARK | PKG-003 | DEL-03-03 | Parking lot line painting — stall lines and fire lane markings | 450 | lm | 4 | 1800 | CAD | RATE_TABLE | Paving_Surfacing_Rates.csv PS-07; Qty per ASM-011 | MED | 40 stalls x ~5.5m line + ~200m fire lane markings. Rounded to 450 lm. | EST_DEL-03-03_2026-02-18_1200
DEL-03-03::L-010 | DEL-03-03 | PKG-003 | L-010 | 03.03.MARK | PKG-003 | DEL-03-03 | Accessible parking signage and markings | 3 | each | 450 | 1350 | CAD | RATE_TABLE | Paving_Surfacing_Rates.csv PS-08; Qty per ASM-012 | MED | 3 accessible stalls assumed per Alberta Building Code for 40-stall lot. | EST_DEL-03-03_2026-02-18_1200
DEL-03-03::L-011 | DEL-03-03 | PKG-003 | L-011 | 03.03.SITE | PKG-003 | DEL-03-03 | Steel bollards — concrete-filled; painted; at overhead doors and building corners | 12 | each | 1000 | 12000 | CAD | RATE_TABLE | Paving_Surfacing_Rates.csv PS-09; Qty per ASM-013 | MED | Standard practice at overhead doors/corners/fuel areas. Count TBD from site plan. | EST_DEL-03-03_2026-02-18_1200
DEL-03-03::L-012 | DEL-03-03 | PKG-003 | L-012 | 03.03.ASP-HD | PKG-003 | DEL-03-03 | Geosynthetics allowance — biaxial geogrid for heavy duty asphalt (Zone A); supplemental to PS-01 rate | 2000 | m2 | 8 | 16000 | CAD | RATE_TABLE | ASM-014; rate based on typical geogrid supply+install $6-$10/m2 | MED | PS-01 notes say 'includes base prep' but geogrid may not be fully included. Conservative allowance. See ASM-014. | EST_DEL-03-03_2026-02-18_1200
DEL-03-03::L-013 | DEL-03-03 | PKG-003 | L-013 | 03.03.ASP-LD | PKG-003 | DEL-03-03 | Geosynthetics allowance — woven geofabric for light duty asphalt (Zone B); supplemental to PS-02 rate | 3200 | m2 | 5 | 16000 | CAD | RATE_TABLE | ASM-015; rate based on typical geofabric supply+install $3-$6/m2 | MED | PS-02 notes say 'includes base prep' but geofabric may not be fully included. Conservative allowance. See ASM-015. | EST_DEL-03-03_2026-02-18_1200
DEL-03-03::L-014 | DEL-03-03 | PKG-003 | L-014 | 03.03.AGG | PKG-003 | DEL-03-03 | Geosynthetics allowance — woven geofabric for aggregate yard (Zone C); separation layer at subgrade | 6000 | m2 | 5 | 30000 | CAD | RATE_TABLE | ASM-016; rate based on typical geofabric supply+install $3-$6/m2 | MED | Geofabric separation layer between subgrade and aggregate. Not included in PS-03 rate. See ASM-016. | EST_DEL-03-03_2026-02-18_1200
DEL-03-04::L-0304-01 | DEL-03-04 | PKG-003 | L-0304-01 | 31.40 | PKG-003 | DEL-03-04 | Water main 150mm PVC - municipal stub to Main PSB (120 m) | 120 | lm | 200 | 24000 | CAD | RATE_TABLE | Underground_Utility_Rates.csv UU-01; ASM-001 | MED | All-inclusive rate: trench/bed/pipe/backfill/compact; 1.5-2.0m depth; Alberta freeze depth | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-02 | DEL-03-04 | PKG-003 | L-0304-02 | 31.40 | PKG-003 | DEL-03-04 | Water main 150mm PVC - branch to Cold Storage Building (40 m) | 40 | lm | 200 | 8000 | CAD | RATE_TABLE | Underground_Utility_Rates.csv UU-01; ASM-002; ASM-004 | LOW | Cold Storage water service requirement TBD per Datasheet; assumed required | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-03 | DEL-03-04 | PKG-003 | L-0304-03 | 31.40 | PKG-003 | DEL-03-04 | Water service connection to Main PSB (50mm copper/PE) | 1 | each | 4500 | 4500 | CAD | RATE_TABLE | Underground_Utility_Rates.csv UU-02 | MED | From main to 1.5m outside building; includes curb stop | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-04 | DEL-03-04 | PKG-003 | L-0304-04 | 31.40 | PKG-003 | DEL-03-04 | Water service connection to Cold Storage Building (50mm copper/PE) | 1 | each | 4500 | 4500 | CAD | RATE_TABLE | Underground_Utility_Rates.csv UU-02; ASM-004 | LOW | Cold Storage water service requirement TBD; assumed required | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-05 | DEL-03-04 | PKG-003 | L-0304-05 | 31.41 | PKG-003 | DEL-03-04 | Sanitary sewer 200mm PVC gravity - municipal stub to Main PSB (120 m) | 120 | lm | 225 | 27000 | CAD | RATE_TABLE | Underground_Utility_Rates.csv UU-03; ASM-001 | MED | Includes bedding/backfill; manholes pro-rated at 1 per 90m | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-06 | DEL-03-04 | PKG-003 | L-0304-06 | 31.41 | PKG-003 | DEL-03-04 | Sanitary service connection to Main PSB | 1 | each | 4000 | 4000 | CAD | RATE_TABLE | Underground_Utility_Rates.csv UU-04 | MED | From main/manhole to 1.5m outside building; includes cleanout | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-07 | DEL-03-04 | PKG-003 | L-0304-07 | 31.42 | PKG-003 | DEL-03-04 | Natural gas service 50mm PE - to Main PSB (120 m) | 120 | lm | 140 | 16800 | CAD | RATE_TABLE | Underground_Utility_Rates.csv UU-06; ASM-001; ASM-007 | MED | ATCO Gas typically installs to meter; estimate for on-site distribution; Cold Storage unheated - no gas | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-08 | DEL-03-04 | PKG-003 | L-0304-08 | 31.43 | PKG-003 | DEL-03-04 | Power duct bank 2-way concrete-encased - to Main PSB (120 m) | 120 | lm | 240 | 28800 | CAD | RATE_TABLE | Underground_Utility_Rates.csv UU-07; ASM-001 | MED | From padmount transformer to building | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-09 | DEL-03-04 | PKG-003 | L-0304-09 | 31.43 | PKG-003 | DEL-03-04 | Power duct bank 2-way concrete-encased - branch to Cold Storage (40 m) | 40 | lm | 240 | 9600 | CAD | RATE_TABLE | Underground_Utility_Rates.csv UU-07; ASM-002 | MED | Electrical service confirmed required for Cold Storage per Datasheet | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-10 | DEL-03-04 | PKG-003 | L-0304-10 | 31.44 | PKG-003 | DEL-03-04 | Telecom conduit 100mm PVC direct-buried - to Main PSB (120 m) | 120 | lm | 100 | 12000 | CAD | RATE_TABLE | Underground_Utility_Rates.csv UU-08; ASM-001; ASM-006 | MED | Cold Storage telecom not required (ASM-006) | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-11 | DEL-03-04 | PKG-003 | L-0304-11 | 31.45 | PKG-003 | DEL-03-04 | Common trench shared utilities 2.0m deep (100 m) | 100 | lm | 100 | 10000 | CAD | RATE_TABLE | Underground_Utility_Rates.csv UU-09; ASM-003 | MED | Where water/sewer/gas share alignment; per lm of trench | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-12 | DEL-03-04 | PKG-003 | L-0304-12 | 31.49 | PKG-003 | DEL-03-04 | Municipal utility tie-in allowance - all utilities (DEC-004) | 1 | LS | 35000 | 35000 | CAD | ALLOWANCE | Underground_Utility_Rates.csv UU-12; DEC-004 | LOW | PENDING OWNER CONFIRMATION; combined water+sewer+gas+power+telecom tie-in execution at municipal stubs | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-13 | DEL-03-04 | PKG-003 | L-0304-13 | 31.50 | PKG-003 | DEL-03-04 | Water utility connection fee | 1 | LS | 10000 | 10000 | CAD | ALLOWANCE | Fees_Permits_Insurance.csv FP-11 | LOW | Town of Penhold fee schedule TBD; recommended value used | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-14 | DEL-03-04 | PKG-003 | L-0304-14 | 31.50 | PKG-003 | DEL-03-04 | Sewer utility connection fee | 1 | LS | 10000 | 10000 | CAD | ALLOWANCE | Fees_Permits_Insurance.csv FP-12 | LOW | Town of Penhold fee schedule TBD; recommended value used | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-15 | DEL-03-04 | PKG-003 | L-0304-15 | 31.50 | PKG-003 | DEL-03-04 | Power service connection fee | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | Fees_Permits_Insurance.csv FP-13 | LOW | ATCO Electric or FortisAlberta; depends on service size | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-16 | DEL-03-04 | PKG-003 | L-0304-16 | 31.50 | PKG-003 | DEL-03-04 | Gas service connection fee | 1 | LS | 5000 | 5000 | CAD | ALLOWANCE | Fees_Permits_Insurance.csv FP-14 | LOW | ATCO Gas; depends on service size and distance | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-17 | DEL-03-04 | PKG-003 | L-0304-17 | 31.50 | PKG-003 | DEL-03-04 | Telecom service connection fee | 1 | LS | 2000 | 2000 | CAD | ALLOWANCE | Fees_Permits_Insurance.csv FP-15 | LOW | Telus or local provider | EST_DEL-03-04_2026-02-18_2100
DEL-03-04::L-0304-18 | DEL-03-04 | PKG-003 | L-0304-18 | 31.00 | PKG-003 | DEL-03-04 | Civil engineering design fees - utility routing (2.5% of distribution construction cost) | 1 | LS | 3730 | 3730 | CAD | RATE_TABLE | Professional_Design_Fees.csv DF-02; fee base = $149200 distribution subtotal | MED | 2.5% recommended rate on distribution line items L-0304-01 through L-0304-11 | EST_DEL-03-04_2026-02-18_2100
DEL-03-05::L-01 | DEL-03-05 | PKG-003 | L-01 | PROF_SERVICES | PKG-003 | DEL-03-05 | Environmental consultant fees -- flood hazard assessment + wetland assessment update + AEPA interface + regulatory coordination | 1 | LS | 22000 | 22000 | CAD | RATE_TABLE | Fees_Permits_Insurance.csv FP-17 (RecommendedRate=$22000; range $15000-$30000) | MED | Professional assessment; regulatory coordination; AEPA interface. Per FP-17 and DF-07. | EST_DEL-03-05_2026-02-18_2000
DEL-03-05::L-02 | DEL-03-05 | PKG-003 | L-02 | REGULATORY_FEES | PKG-003 | DEL-03-05 | AEPA Water Act application fee -- regulatory application for construction near waterway/wetland | 1 | LS | 5000 | 5000 | CAD | ALLOWANCE | Fees_Permits_Insurance.csv FP-16 (RecommendedRate=$5000; range $3000-$8000) | LOW | If required for construction near waterway/wetland. AEPA approval PENDING (DEP-3505-E06). Priced as ALLOWANCE per FALLBACK_POLICY because fee schedule uncertain. | EST_DEL-03-05_2026-02-18_2000
DEL-03-05::L-03 | DEL-03-05 | PKG-003 | L-03 | REGULATORY_FEES | PKG-003 | DEL-03-05 | ABWRET-A wetland replacement fee -- in-lieu fee payable to Government of Alberta upon Water Act approval | 1 | LS | 10770 | 10770 | CAD | RATE_TABLE | Datasheet.md > Wetland/Waterbody Characteristics > ABWRET-A Wetland Replacement Fee ($10769.54 per Wetland Assessment Executive Summary Ghostpine Aug 2021) | HIGH | Exact fee calculated in Wetland Assessment: $10769.54. Rounded to $10770 per ROUNDING=DOLLAR. Not payable until Water Act approval issued. | EST_DEL-03-05_2026-02-18_2000
DEL-03-05::L-04 | DEL-03-05 | PKG-003 | L-04 | PROF_SERVICES | PKG-003 | DEL-03-05 | Erosion and sediment control plan preparation -- engineering design + monitoring plan per Alberta ESC guidelines | 1 | LS | 4500 | 4500 | CAD | RATE_TABLE | Fees_Permits_Insurance.csv FP-18 (RecommendedRate=$4500; range $3000-$6000) | MED | Engineering design + monitoring plan. Per Alberta ESC guidelines. | EST_DEL-03-05_2026-02-18_2000
DEL-03-05::L-05 | DEL-03-05 | PKG-003 | L-05 | REGULATORY_FEES | PKG-003 | DEL-03-05 | Development permit fee -- flood fringe approval component (Town of Penhold) | 1 | LS | 1200 | 1200 | CAD | ALLOWANCE | Fees_Permits_Insurance.csv FP-07 (RecommendedRate=$1200; range $500-$2000) | LOW | Application fee for development permit with flood fringe conditions. Penhold fee schedule TBD. Priced as ALLOWANCE per FALLBACK_POLICY. | EST_DEL-03-05_2026-02-18_2000
DEL-04-01::L-0401-01 | DEL-04-01 | PKG-004 | L-0401-01 | 04.01.SHELL | PKG-004 | DEL-04-01 | Pre-engineered metal building shell (60x100 ft clear-span; unheated) — includes framing; roof; wall cladding; gutters/downspouts; anchor bolts; erection. Does NOT include foundation; floor; doors; electrical; ventilation. | 1 | LS | 192000 | 192000 | CAD | PARAMETRIC | Parametric_Building_Rates.csv PB-01 RecommendedRate=$32/sf x 6000 sf (PP-07); DEC-001 confirms 60x100=6000 sf | MED | PB-01 shell-only parametric rate ($28-35/sf range; $32 recommended). Cost ownership: shell only per brief. Qty=1 LS per parametric convention. | EST_DEL-04-01_2026-02-18_1200
DEL-04-01::L-0401-02 | DEL-04-01 | PKG-004 | L-0401-02 | 04.01.DESIGN | PKG-004 | DEL-04-01 | Design and engineering services — cold storage building design basis and configuration (architectural/structural design for shell) | 1 | LS | 10000 | 10000 | CAD | ALLOWANCE | Assumptions_Log.md ASM-003; no explicit design fee source in PRICE_SOURCES | LOW | Allowance for DB design/engineering effort attributable to cold storage shell configuration. FALLBACK_POLICY=ALLOW_ALLOWANCE. Estimated as ~5% of shell construction cost. Qty=1 LS per allowance convention. | EST_DEL-04-01_2026-02-18_1200
DEL-04-02::L-0402-01 | DEL-04-02 | PKG-004 | L-0402-01 | 08-Doors | PKG-004 | DEL-04-02 | Overhead door 16x16 ft motorized insulated standard grade with windows (cold storage) | 2 | each | 13500 | 27000 | CAD | RATE_TABLE | Equipment_Pricing.csv row EQ-02 (RecommendedPrice=$13500; Qty_Assumed=2) | MED | EQ-02 explicitly for cold storage; standard grade per SOW-0302 | EST_DEL-04-02_2026-02-18_1100
DEL-04-02::L-0402-02 | DEL-04-02 | PKG-004 | L-0402-02 | 08-Doors | PKG-004 | DEL-04-02 | Person door - hollow metal door and frame single commercial | 2 | each | 1800 | 3600 | CAD | RATE_TABLE | Building_Envelope_Rates.csv row BE-11 (RecommendedRate=$1800) | MED | Standard commercial hollow metal per REQ-4202-06; code-compliant egress size | EST_DEL-04-02_2026-02-18_1100
DEL-04-02::L-0402-03 | DEL-04-02 | PKG-004 | L-0402-03 | 08-Doors | PKG-004 | DEL-04-02 | Door hardware set - commercial per opening (person doors) | 2 | each | 600 | 1200 | CAD | RATE_TABLE | Building_Envelope_Rates.csv row BE-13 (RecommendedRate=$600) | MED | Lever handle + closer + hinges + weatherstrip + keyed deadbolt per REQ-4202-07 | EST_DEL-04-02_2026-02-18_1100
DEL-04-02::L-0402-04 | DEL-04-02 | PKG-004 | L-0402-04 | 08-Doors | PKG-004 | DEL-04-02 | Door hardware set - overhead door hardware allowance (weatherstrip + guides + misc) | 2 | each | 600 | 1200 | CAD | RATE_TABLE | Building_Envelope_Rates.csv row BE-13 (RecommendedRate=$600); Assumptions_Log.md ASM-03 | MED | Overhead door hardware beyond what is included in EQ-02 unit price; assumed equivalent to one commercial hardware set per opening for guides + seals + misc | EST_DEL-04-02_2026-02-18_1100
DEL-04-02::L-0402-05 | DEL-04-02 | PKG-004 | L-0402-05 | 03-Concrete | PKG-004 | DEL-04-02 | Concrete apron at overhead door (200mm reinforced heavy-duty slab-on-grade) | 2 | each | 5400 | 10800 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv row SC-04 (RecommendedRate=$108/m2); Assumptions_Log.md ASM-04 | MED | 2 aprons at 50 m2 each (approx 7.5m wide x 6.7m deep per ASM-04); $108/m2 x 50 m2 = $5400 each | EST_DEL-04-02_2026-02-18_1100
DEL-04-02::L-0402-06 | DEL-04-02 | PKG-004 | L-0402-06 | 07-Thermal | PKG-004 | DEL-04-02 | Perimeter sealant and weatherstripping at overhead door openings | 2 | each | 512 | 1024 | CAD | RATE_TABLE | Building_Envelope_Rates.csv row BE-14 (RecommendedRate=$16/lm); Assumptions_Log.md ASM-05 | MED | Perimeter = 2*(4.88m+4.88m) = 19.5m per opening; 19.5 lm x $16/lm = $312 sealant + $200 weatherstrip allowance per ASM-06 = $512 each | EST_DEL-04-02_2026-02-18_1100
DEL-04-02::L-0402-07 | DEL-04-02 | PKG-004 | L-0402-07 | 07-Thermal | PKG-004 | DEL-04-02 | Perimeter sealant and weatherstripping at person door openings | 2 | each | 131 | 262 | CAD | RATE_TABLE | Building_Envelope_Rates.csv row BE-14 (RecommendedRate=$16/lm); Assumptions_Log.md ASM-05 | MED | Perimeter = 2*(0.81m+2.03m) = 5.7m per opening; 5.7 lm x $16/lm = $91 sealant + $40 weatherstrip allowance per ASM-06 = $131 each | EST_DEL-04-02_2026-02-18_1100
DEL-04-02::L-0402-08 | DEL-04-02 | PKG-004 | L-0402-08 | 08-Doors | PKG-004 | DEL-04-02 | Installation labour - overhead doors (carpenter) | 32 | hr | 72 | 2304 | CAD | RATE_TABLE | Construction_Labour_Rates.csv row T-02 (FullyBurdenedRate=$72/hr); Assumptions_Log.md ASM-07 | MED | 16 hrs per door x 2 doors = 32 hrs; includes unloading + assembly + hanging + opener installation + adjustment | EST_DEL-04-02_2026-02-18_1100
DEL-04-02::L-0402-09 | DEL-04-02 | PKG-004 | L-0402-09 | 08-Doors | PKG-004 | DEL-04-02 | Installation labour - person doors (carpenter) | 8 | hr | 72 | 576 | CAD | RATE_TABLE | Construction_Labour_Rates.csv row T-02 (FullyBurdenedRate=$72/hr); Assumptions_Log.md ASM-08 | MED | 4 hrs per door x 2 doors = 8 hrs; includes frame set + door hang + hardware install | EST_DEL-04-02_2026-02-18_1100
DEL-04-02::L-0402-10 | DEL-04-02 | PKG-004 | L-0402-10 | 03-Concrete | PKG-004 | DEL-04-02 | Installation labour - concrete aprons (concrete finisher + labourer) | 48 | hr | 62 | 2976 | CAD | RATE_TABLE | Construction_Labour_Rates.csv rows T-04 ($68/hr) and T-01 ($55/hr) blended; Assumptions_Log.md ASM-09 | MED | 24 hrs per apron x 2 aprons = 48 hrs; blended rate ($68+$55)/2=$62; includes forming + placement + finishing + curing | EST_DEL-04-02_2026-02-18_1100
DEL-04-02::L-0402-11 | DEL-04-02 | PKG-004 | L-0402-11 | 08-Doors | PKG-004 | DEL-04-02 | Emergency exit lights above person doors (battery backup) | 2 | each | 350 | 700 | CAD | RATE_TABLE | Assumptions_Log.md ASM-10; location TBD | LOW | Per REQ-4202-11; unit rate based on typical commercial LED exit light with battery; no direct rate table entry -- see QA warning | EST_DEL-04-02_2026-02-18_1100
DEL-04-02::L-0402-12 | DEL-04-02 | PKG-004 | L-0402-12 | 08-Doors | PKG-004 | DEL-04-02 | Weatherproof light switches at person doors | 2 | each | 85 | 170 | CAD | RATE_TABLE | Assumptions_Log.md ASM-11; location TBD | LOW | Per REQ-4202-12; unit rate based on typical weatherproof switch assembly; no direct rate table entry -- see QA warning | EST_DEL-04-02_2026-02-18_1100
DEL-04-03::L-001 | DEL-04-03 | PKG-004 | L-001 | 05-Metals | PKG-004 | DEL-04-03 | Screw piles - galvanized helical piles installed (2.75-3.5 in shaft; helix below 2.0 m frost depth; 6-8 m typical) | 20 | each | 3000 | 60000 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv SC-14 (RecommendedRate=$3000/each) | MED | Pile count assumes 60x100 ft PEMB perimeter columns at ~10-12 ft spacing; see ASM-001 and ASM-002 | EST_DEL-04-03_2026-02-18_1400
DEL-04-03::L-002 | DEL-04-03 | PKG-004 | L-002 | 03-Concrete | PKG-004 | DEL-04-03 | Concrete grade beams connecting pile caps (strip footing rate as proxy for formed concrete beams) | 80 | lm | 220 | 17600 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv SC-13 (RecommendedRate=$220/lm) | MED | Perimeter grade beam ~320 lf (97.5 m) = 2x100ft + 2x60ft; assumed ~80 lm net for pile-to-pile beams; see ASM-006 | EST_DEL-04-03_2026-02-18_1400
DEL-04-03::L-003 | DEL-04-03 | PKG-004 | L-003 | 03-Concrete | PKG-004 | DEL-04-03 | Concrete slab-on-grade 150mm with W/W mesh - cold storage floor (60x100 ft = 557.4 m2) | 557 | m2 | 85 | 47345 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv SC-03 (RecommendedRate=$85/m2) | MED | Full concrete floor per DEC-002; includes sub-base prep; sulphate-resistant mix per REQ-07 (Type HS cement 32 MPa) | EST_DEL-04-03_2026-02-18_1400
DEL-04-03::L-004 | DEL-04-03 | PKG-004 | L-004 | 03-Concrete | PKG-004 | DEL-04-03 | Concrete aprons at overhead doors (2 doors x 16x16 ft = 2 x 23.8 m2 = 47.6 m2; 200mm reinforced for vehicle loads) | 48 | m2 | 108 | 5184 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv SC-04 (RecommendedRate=$108/m2) | MED | Heavy-duty 200mm slab for service vehicle loads per REQ-06 (OSR 10.3.10); 2 OH doors at 16x16 ft each | EST_DEL-04-03_2026-02-18_1400
DEL-04-03::L-005 | DEL-04-03 | PKG-004 | L-005 | 03-Concrete | PKG-004 | DEL-04-03 | Concrete aprons at person doors (2 doors x approx 1.5m x 2.0m = 6.0 m2; 150mm with mesh) | 6 | m2 | 85 | 510 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv SC-03 (RecommendedRate=$85/m2) | MED | Smaller aprons at 2 person doors per REQ-06; standard 150mm slab adequate for pedestrian traffic | EST_DEL-04-03_2026-02-18_1400
DEL-04-03::L-006 | DEL-04-03 | PKG-004 | L-006 | 31-Earthwork | PKG-004 | DEL-04-03 | Subgrade preparation - strip topsoil and compact per Geotech Report section 7.1 (557.4 m2 building footprint) | 557 | m2 | 12 | 6684 | CAD | RATE_TABLE | Assumed_Project_Parameters.csv PP-07 (6000 sf footprint) + Parametric_Building_Rates.csv PB-06 ($16/sf site dev rate prorated) | MED | Includes stripping topsoil; scarifying; compacting to 98% SPDD; proof rolling; rate derived as fraction of PB-06 site rate; see ASM-007 | EST_DEL-04-03_2026-02-18_1400
DEL-04-03::L-007 | DEL-04-03 | PKG-004 | L-007 | 02-Sitework | PKG-004 | DEL-04-03 | Granular base - 150mm radon rock below slab (557.4 m2 x 150mm depth) | 557 | m2 | 15 | 8355 | CAD | RATE_TABLE | Decision_Log.md DEC-EST-007 (derived from subgrade prep component of SC-03 rate) | MED | 20 mm screened/washed rock per Geotech section 7.1 item 6; rate estimated from granular material supply + placement; see ASM-008 | EST_DEL-04-03_2026-02-18_1400
DEL-04-03::L-008 | DEL-04-03 | PKG-004 | L-008 | 02-Sitework | PKG-004 | DEL-04-03 | Vapour barrier - polyethylene sheeting per CAN/CGSB-51.34-M below slab (557.4 m2) | 557 | m2 | 5 | 2785 | CAD | RATE_TABLE | Decision_Log.md DEC-EST-008 (derived rate for poly sheeting supply + install) | MED | 6 mil minimum thickness assumed per REQ-08 [E-002]; includes laps and sealing | EST_DEL-04-03_2026-02-18_1400
DEL-04-03::L-009 | DEL-04-03 | PKG-004 | L-009 | 03-Concrete | PKG-004 | DEL-04-03 | Reinforcing steel for grade beams and slab edges (estimated 1500 kg for perimeter + slab mesh supplement) | 1500 | kg | 3.25 | 4875 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv SC-07 (RecommendedRate=$3.25/kg) | MED | Includes rebar for grade beams and supplemental reinforcing at slab edges/joints; W/W mesh included in SC-03 rate | EST_DEL-04-03_2026-02-18_1400
DEL-04-03::L-010 | DEL-04-03 | PKG-004 | L-010 | 05-Metals | PKG-004 | DEL-04-03 | Anchor bolts - screw pile to grade beam connections (20 piles x 4 bolts = 80 bolts) | 80 | each | 45 | 3600 | CAD | RATE_TABLE | Structural_Concrete_Rates.csv SC-15 (RecommendedRate=$45/each) | MED | Standard anchor bolts set in concrete grade beams at pile cap locations; 4 per pile assumed | EST_DEL-04-03_2026-02-18_1400
DEL-04-04::L-0404-01 | DEL-04-04 | PKG-004 | L-0404-01 | 26-ELEC | PKG-004 | DEL-04-04 | Cold storage basic electrical -- panel; receptacles; lighting; door opener feeds (ES-12 rate applied to 6000 sf) | 6000 | sf | 6 | 36000 | CAD | RATE_TABLE | Electrical_System_Rates.csv / ES-12; Assumed_Project_Parameters.csv / PP-07 | MED | ES-12 recommended rate $6/sf; area PP-07 = 6000 sf confirmed. Includes service entry at building wall to panel and in-building distribution. ES-05 lighting-only rate NOT layered to avoid double-count. | EST_DEL-04-04_2026-02-18_1500
DEL-04-04::L-0404-02 | DEL-04-04 | PKG-004 | L-0404-02 | 23-VENT | PKG-004 | DEL-04-04 | Cold storage ventilation -- condensation/icing prevention; ridge vents or gable fans; minimal mechanical (MS-13 rate applied to 6000 sf) | 6000 | sf | 3 | 18000 | CAD | RATE_TABLE | Mechanical_System_Rates.csv / MS-13; Assumed_Project_Parameters.csv / PP-07 | MED | MS-13 recommended rate $3/sf; area PP-07 = 6000 sf confirmed. Passive/low-energy systems for condensation prevention in unheated PEMB. | EST_DEL-04-04_2026-02-18_1500
DEL-05-01::L-05-01-001 | DEL-05-01 | PKG-005 | L-05-01-001 | CBS-0500-EQUIP | PKG-005 | DEL-05-01 | Built-in wash bay complete system (equipment + containment + drainage + water treatment/recycling + HVAC modification for heated wash area; installed in PW bay area) | 1 | LS | 95000 | 95000 | CAD | ALLOWANCE | Optional_Items_Pricing.csv row OPT-01 (RecommendedPrice); FALLBACK per DEC-EST-001 | LOW | REQUIRES VENDOR QUOTE REPLACEMENT. Range: $75000-$120000. Includes equipment + containment + drainage + water treatment/recycling + HVAC modification. Excludes base bay sump (DEL-02-05) and base mechanical rough-in (DEL-02-05). Excludes structural modifications (DEL-02-04). | EST_DEL-05-01_2026-02-18_1500
DEL-05-01::L-05-01-002 | DEL-05-01 | PKG-005 | L-05-01-002 | CBS-0500-PLMB | PKG-005 | DEL-05-01 | Wash bay plumbing/drainage modifications (hot/cold water supply; floor drain; containment curb; connection to separator) | 1 | LS | 16000 | 16000 | CAD | ALLOWANCE | Optional_Items_Pricing.csv row OPT-02 (RecommendedPrice); FALLBACK per DEC-EST-001 | LOW | REQUIRES VENDOR QUOTE REPLACEMENT. Range: $12000-$20000. Dedicated wash bay plumbing beyond base building rough-in. Excludes base building bay sumps (DEL-02-05). Excludes base building mechanical rough-in to wash bay location (DEL-02-05). | EST_DEL-05-01_2026-02-18_1500
DEL-05-01::L-05-01-003 | DEL-05-01 | PKG-005 | L-05-01-003 | CBS-0500-ENVR | PKG-005 | DEL-05-01 | Wash bay environmental compliance -- effluent treatment (oil/water separator; possible connection to municipal sewer; AEPA requirements TBD) | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | Optional_Items_Pricing.csv row OPT-03 (RecommendedPrice); FALLBACK per DEC-EST-001 | LOW | REQUIRES VENDOR QUOTE REPLACEMENT. Range: $8000-$18000. AEP/Town regulatory requirements unresolved (DEP-05-01-E04). Cost highly sensitive to regulatory outcome. Excludes base building bay sumps (DEL-02-05). | EST_DEL-05-01_2026-02-18_1500
DEL-05-02::L-0502-01 | DEL-05-02 | PKG-005 | L-0502-01 | 26-ELEC | PKG-005 | DEL-05-02 | Yard light - pole + LED fixture + concrete base + wiring (per unit installed); 25-30 ft pole; IES dark-sky compliant LED | 12 | each | 7500 | 90000 | CAD | RATE_TABLE | Optional_Items_Pricing.csv row OPT-04 | MED | UNIT RATE ITEM: $7500/light is the per-unit rate. Qty 12 is ASSUMED per PP-20 (LOW confidence); actual quantity elected by Owner. Total scales linearly with quantity. | EST_DEL-05-02_2026-02-18_1600
DEL-05-02::L-0502-02 | DEL-05-02 | PKG-005 | L-0502-02 | 26-COND | PKG-005 | DEL-05-02 | Yard lighting conduit run - underground conduit + wiring from building electrical room to first pole (one-time fixed cost; does not scale per light) | 100 | lm | 80 | 8000 | CAD | RATE_TABLE | Optional_Items_Pricing.csv row OPT-05 | MED | FIXED COST per installation (not per light). Length 100 lm is ASSUMED based on brief (fence line ~100 m from nearest structure). Actual length TBD pending site plan from DEL-03-01. | EST_DEL-05-02_2026-02-18_1600
DEL-05-03::L-05-03-001 | DEL-05-03 | PKG-005 | L-05-03-001 | 26 05 00 | PKG-005 | DEL-05-03 | Access control system - 10-zone base (readers; controllers; head-end software; door contacts; REX; wiring; programming; commissioning) | 1 | LS | 45000 | 45000 | CAD | PARAMETRIC | Optional_Items_Pricing.csv > OPT-06 | LOW | Parametric pricing for 10-zone system installed. No vendor quote exists -- REQUIRES VENDOR QUOTE REPLACEMENT. Zone count assumed per PP-28. Excludes IT network infrastructure (DEL-02-06) and door hardware (DEL-02-01) and electrical power circuits (DEL-02-06). | EST_DEL-05-03_2026-02-18_1700
DEL-05-04::L-0504-01 | DEL-05-04 | PKG-005 | L-0504-01 | 26-SECURITY | PKG-005 | DEL-05-04 | Security camera system - 16 IP cameras (interior + exterior) with NVR + storage + network switches + cabling + mounting + programming + commissioning | 1 | LS | 50000 | 50000 | CAD | PARAMETRIC | Optional_Items_Pricing.csv > OPT-08 (RecommendedPrice=$50000; range $40000-$60000) | LOW | No vendor quote; parametric placeholder from OPT-08. Includes all equipment + wiring + installation per cost ownership rules. Camera count (16) is assumed per PP-29. REQUIRES VENDOR QUOTE REPLACEMENT. | EST_DEL-05-04_2026-02-18_1800
DEL-05-04::L-0504-02 | DEL-05-04 | PKG-005 | L-0504-02 | 26-SECURITY-MONITORING | PKG-005 | DEL-05-04 | Security monitoring service - annual remote monitoring + alarm response coordination | 1 | LS | 5400 | 5400 | CAD | PARAMETRIC | Optional_Items_Pricing.csv > OPT-09 (RecommendedPrice=$5400; range $3600-$7200) | LOW | No vendor quote; parametric placeholder from OPT-09. Annual subscription cost; separated from installation cost per RFP OSR 12.4. REQUIRES VENDOR QUOTE REPLACEMENT. | EST_DEL-05-04_2026-02-18_1800
DEL-05-05::L-05-05-01 | DEL-05-05 | PKG-005 | L-05-05-01 | 09-SIGNAGE-FAB | PKG-005 | DEL-05-05 | Town branding signage -- fabricated non-illuminated (primary scenario; per sign) | 1 | LS | 12000 | 12000 | CAD | ALLOWANCE | Optional_Items_Pricing.csv > OPT-10 (RecommendedPrice) | LOW | Allowance fallback from QUOTE basis; branding guidelines PENDING; assumes 1 sign unit; aluminum + vinyl or dimensional letters; structural mount included in unit rate; quantity TBD pending branding guidelines | EST_DEL-05-05_2026-02-18_1800
DEL-05-05::L-05-05-02 | DEL-05-05 | PKG-005 | L-05-05-02 | 09-SIGNAGE-FAB | PKG-005 | DEL-05-05 | Town branding signage -- fabricated illuminated (alternate scenario; per sign) | 1 | LS | 22000 | 22000 | CAD | ALLOWANCE | Optional_Items_Pricing.csv > OPT-11 (RecommendedPrice) | LOW | Alternate scenario if illuminated signage is selected; LED backlighting or halo illumination; illumination decision TBD; electrical connection cost included in unit rate; incremental electrical circuit cost excluded (owned by DEL-02-06) | EST_DEL-05-05_2026-02-18_1800
DEL-05-06::L-0506-01 | DEL-05-06 | PKG-005 | L-0506-01 | CBS-EQP | PKG-005 | DEL-05-06 | Refrigerator with freezer (commercial residential; per unit) | 2 | each | 1500 | 3000 | CAD | QUOTE | Optional_Items_Pricing.csv OPT-12 (RecommendedPrice) | MEDIUM | 2 units required per OSR S12.6; retail pricing treated as quote-equivalent per DEC-EST-001 | EST_DEL-05-06_2026-02-18_1900
DEL-05-06::L-0506-02 | DEL-05-06 | PKG-005 | L-0506-02 | CBS-EQP | PKG-005 | DEL-05-06 | Microwave (commercial; per unit) | 2 | each | 450 | 900 | CAD | QUOTE | Optional_Items_Pricing.csv OPT-13 (RecommendedPrice) | MEDIUM | 2 units required per OSR S12.6; retail pricing treated as quote-equivalent per DEC-EST-001 | EST_DEL-05-06_2026-02-18_1900
DEL-05-06::L-0506-03 | DEL-05-06 | PKG-005 | L-0506-03 | CBS-EQP | PKG-005 | DEL-05-06 | Stove/oven with range hood (residential) | 1 | each | 3500 | 3500 | CAD | QUOTE | Optional_Items_Pricing.csv OPT-14 (RecommendedPrice) | MEDIUM | 1 unit; electric or gas range with range hood and exhaust | EST_DEL-05-06_2026-02-18_1900
DEL-05-06::L-0506-04 | DEL-05-06 | PKG-005 | L-0506-04 | CBS-EQP | PKG-005 | DEL-05-06 | Dishwasher (commercial residential) | 1 | each | 1100 | 1100 | CAD | QUOTE | Optional_Items_Pricing.csv OPT-15 (RecommendedPrice) | MEDIUM | 1 unit; standard built-in | EST_DEL-05-06_2026-02-18_1900
DEL-05-06::L-0506-05 | DEL-05-06 | PKG-005 | L-0506-05 | CBS-EQP | PKG-005 | DEL-05-06 | Residential laundry set (washer + dryer; per set) | 2 | set | 2800 | 5600 | CAD | QUOTE | Optional_Items_Pricing.csv OPT-16 (RecommendedPrice) | MEDIUM | 2 sets required per OSR S12.6; front-load washer + dryer | EST_DEL-05-06_2026-02-18_1900
DEL-05-06::L-0506-06 | DEL-05-06 | PKG-005 | L-0506-06 | CBS-INST | PKG-005 | DEL-05-06 | Appliance installation and connection (all units) | 1 | LS | 4500 | 4500 | CAD | QUOTE | Optional_Items_Pricing.csv OPT-17 (RecommendedPrice) | MEDIUM | Plumbing connections; electrical connections; venting; testing for all appliances | EST_DEL-05-06_2026-02-18_1900
DEL-05-07::L-0507-001 | DEL-05-07 | PKG-005 | L-0507-001 | FF&E | PKG-005 | DEL-05-07_Optional-FFandE-Allowance | FF&E cash allowance (furniture fixtures and equipment) - fixed per DEC-005 | 1 | LS | 20000 | 20000 | CAD | ALLOWANCE | _PriceSources/Optional_Items_Pricing.csv row OPT-18; DEC-005 | HIGH | Fixed $20k cash allowance. DB allocates: Meeting/Training $8k; Lunchroom $6k; Reception $3k; Misc $3k. Excludes connected appliances (DEL-05-06 scope). | EST_DEL-05-07_2026-02-18_2200

## Summary_WBS
WBS_PackageID | WBS_DeliverableID | Amount_Total_CAD | LineCount | TBD_Count | Notes
PKG-001 | DEL-01-01 | 44800 | 4 | 0
PKG-001 | DEL-01-02 | 17400 | 3 | 0
PKG-001 | DEL-01-03 | 15240 | 4 | 0
PKG-001 | DEL-01-04 | 79910 | 7 | 0
PKG-001 | DEL-01-05 | 19750 | 2 | 0
PKG-001 | DEL-01-06 | 263700 | 4 | 0
PKG-001 | DEL-01-07 | 23650 | 3 | 0
PKG-002 | DEL-02-01 | 168329 | 10 | 0
PKG-002 | DEL-02-02 | 279279 | 38 | 0
PKG-002 | DEL-02-03 | 212396 | 32 | 0
PKG-002 | DEL-02-04 | 1721269 | 28 | 0
PKG-002 | DEL-02-05 | 1014095 | 16 | 0
PKG-002 | DEL-02-06 | 642936 | 13 | 0
PKG-002 | DEL-02-07 | 201000 | 5 | 0
PKG-003 | DEL-03-01 | 18500 | 2 | 0
PKG-003 | DEL-03-02 | 472062 | 15 | 0
PKG-003 | DEL-03-03 | 896380 | 14 | 0
PKG-003 | DEL-03-04 | 226930 | 18 | 0
PKG-003 | DEL-03-05 | 43470 | 5 | 0
PKG-004 | DEL-04-01 | 202000 | 2 | 0
PKG-004 | DEL-04-02 | 51812 | 12 | 0
PKG-004 | DEL-04-03 | 156938 | 10 | 0
PKG-004 | DEL-04-04 | 54000 | 2 | 0
PKG-005 | DEL-05-01 | 123000 | 3 | 0
PKG-005 | DEL-05-02 | 98000 | 2 | 0
PKG-005 | DEL-05-03 | 45000 | 1 | 0
PKG-005 | DEL-05-04 | 55400 | 2 | 0
PKG-005 | DEL-05-05 | 34000 | 2 | 0
PKG-005 | DEL-05-06 | 18600 | 6 | 0
PKG-005 | DEL-05-07 | 20000 | 1 | 0
--- Package Subtotals ---
PKG-001 | SUBTOTAL | 464450 | 27 | 0
PKG-002 | SUBTOTAL | 4239304 | 142 | 0
PKG-003 | SUBTOTAL | 1657342 | 54 | 0
PKG-004 | SUBTOTAL | 464750 | 26 | 0
PKG-005 | SUBTOTAL | 394000 | 17 | 0

## Summary_CBS
CBS | Amount_Total_CAD | LineCount | TBD_Count | Notes
01-CMGT | 203700 | 2 | 0
01-FEES | 71950 | 5 | 0
01-MGMT | 7960 | 2 | 0
01-SITE | 60000 | 2 | 0
02-Sitework | 11140 | 2 | 0
03-02-CLR | 32010 | 2 | 0
03-02-DRN | 74500 | 3 | 0
03-02-DSN | 11514 | 1 | 0
03-02-ESC | 22000 | 1 | 0
03-02-EW | 178038 | 5 | 0
03-02-FIN | 110000 | 1 | 0
03-02-GEO | 32000 | 1 | 0
03-02-SRV | 12000 | 1 | 0
03-CONCRETE | 401219 | 14 | 0
03-Concrete | 89290 | 7 | 0
03-DESIGN | 13500 | 1 | 0
03-SURVEY | 5000 | 1 | 0
03.03.AGG | 390000 | 3 | 0
03.03.ASP-HD | 200000 | 2 | 0
03.03.ASP-LD | 208000 | 2 | 0
03.03.CONC | 83230 | 4 | 0
03.03.MARK | 3150 | 2 | 0
03.03.SITE | 12000 | 1 | 0
04.01.DESIGN | 10000 | 1 | 0
04.01.SHELL | 192000 | 1 | 0
05-Metals | 63600 | 2 | 0
05-STEEL | 461668 | 4 | 0
07-ENVELOPE | 554790 | 6 | 0
07-Thermal | 1286 | 2 | 0
08-Doors | 36750 | 8 | 0
08-OPENINGS | 249100 | 6 | 0
09-FINISHES | 62850 | 26 | 0
09-FLOORING | 58520 | 2 | 0
09-SIGNAGE-FAB | 34000 | 2 | 0
10-SPECIALTIES | 92600 | 3 | 0
11-EQUIPMENT | 55000 | 1 | 0
21.03.01 | 31850 | 3 | 0
21.03.02 | 40188 | 4 | 0
21.03.03 | 34000 | 2 | 0
21.03.04 | 95060 | 12 | 0
21.03.05 | 11298 | 11 | 0
22-PLUMBING | 18000 | 1 | 0
23-COMM | 18000 | 1 | 0
23-CTRL | 72000 | 1 | 0
23-EQUP | 49000 | 3 | 0
23-EXHS | 144000 | 2 | 0
23-FPRT | 108000 | 1 | 0
23-HVAC | 435200 | 3 | 0
23-MECH | 20000 | 1 | 0
23-MECH-DESIGN | 24295 | 1 | 0
23-PLMB | 163600 | 4 | 0
23-VENT | 18000 | 1 | 0
26 05 00 | 45000 | 1 | 0
26-00 | 333400 | 3 | 0
26-10 | 12000 | 1 | 0
26-50 | 173800 | 3 | 0
26-80 | 8000 | 1 | 0
26-90 | 15486 | 1 | 0
26-COND | 8000 | 1 | 0
26-ELEC | 126000 | 2 | 0
26-EMRG-DES | 5000 | 1 | 0
26-EMRG-DIST | 18000 | 1 | 0
26-EMRG-DOOR | 16000 | 1 | 0
26-EMRG-GEN | 162000 | 2 | 0
26-SECURITY | 50000 | 1 | 0
26-SECURITY-MONITORING | 5400 | 1 | 0
27-00 | 80250 | 3 | 0
27-50 | 20000 | 1 | 0
31-EARTHWORK | 6000 | 1 | 0
31-Earthwork | 6684 | 1 | 0
31.00 | 3730 | 1 | 0
31.40 | 41000 | 4 | 0
31.41 | 31000 | 2 | 0
31.42 | 16800 | 1 | 0
31.43 | 38400 | 2 | 0
31.44 | 12000 | 1 | 0
31.45 | 10000 | 1 | 0
31.49 | 35000 | 1 | 0
31.50 | 39000 | 5 | 0
3100 | 11012 | 1 | 0
3200 | 30225 | 1 | 0
3300 | 47200 | 3 | 0
3400 | 58882 | 3 | 0
3500 | 9490 | 1 | 0
3600 | 11520 | 1 | 0
50-DESIGN | 20801 | 1 | 0
ADMIN | 8800 | 2 | 0
CBS-0107-ADM | 1600 | 1 | 0
CBS-0107-CX | 16800 | 1 | 0
CBS-0107-MGT | 5250 | 1 | 0
CBS-0500-ENVR | 12000 | 1 | 0
CBS-0500-EQUIP | 95000 | 1 | 0
CBS-0500-PLMB | 16000 | 1 | 0
CBS-EQP | 14100 | 5 | 0
CBS-INST | 4500 | 1 | 0
CBS-LABOUR-ADMIN | 640 | 1 | 0
CBS-LABOUR-SAFETY | 6600 | 1 | 0
CBS-SUPPLIES | 3500 | 1 | 0
CBS-TRAINING | 4500 | 1 | 0
DESIGN | 5800 | 1 | 0
FF&E | 20000 | 1 | 0
MGMT | 34200 | 2 | 0
MGMT.PROJ_CONTROLS | 17400 | 3 | 0
PM | 15750 | 1 | 0
PROF_SERVICES | 26500 | 2 | 0
REGULATORY_FEES | 16970 | 3 | 0

## WBSxCBS_Matrix
WBS_PackageID | WBS_DeliverableID | CBS | Currency | Amount_Total | LineCount | ProvenanceCompletenessPct | Notes
PKG-001 | DEL-01-01 | ADMIN | CAD | 4800 | 1 | 100%
PKG-001 | DEL-01-01 | DESIGN | CAD | 5800 | 1 | 100%
PKG-001 | DEL-01-01 | MGMT | CAD | 34200 | 2 | 100%
PKG-001 | DEL-01-02 | MGMT.PROJ_CONTROLS | CAD | 17400 | 3 | 100%
PKG-001 | DEL-01-03 | CBS-LABOUR-ADMIN | CAD | 640 | 1 | 100%
PKG-001 | DEL-01-03 | CBS-LABOUR-SAFETY | CAD | 6600 | 1 | 100%
PKG-001 | DEL-01-03 | CBS-SUPPLIES | CAD | 3500 | 1 | 100%
PKG-001 | DEL-01-03 | CBS-TRAINING | CAD | 4500 | 1 | 100%
PKG-001 | DEL-01-04 | 01-FEES | CAD | 71950 | 5 | 100%
PKG-001 | DEL-01-04 | 01-MGMT | CAD | 7960 | 2 | 100%
PKG-001 | DEL-01-05 | ADMIN | CAD | 4000 | 1 | 100%
PKG-001 | DEL-01-05 | PM | CAD | 15750 | 1 | 100%
PKG-001 | DEL-01-06 | 01-CMGT | CAD | 203700 | 2 | 100%
PKG-001 | DEL-01-06 | 01-SITE | CAD | 60000 | 2 | 100%
PKG-001 | DEL-01-07 | CBS-0107-ADM | CAD | 1600 | 1 | 100%
PKG-001 | DEL-01-07 | CBS-0107-CX | CAD | 16800 | 1 | 100%
PKG-001 | DEL-01-07 | CBS-0107-MGT | CAD | 5250 | 1 | 100%
PKG-002 | DEL-02-01 | 3100 | CAD | 11012 | 1 | 100%
PKG-002 | DEL-02-01 | 3200 | CAD | 30225 | 1 | 100%
PKG-002 | DEL-02-01 | 3300 | CAD | 47200 | 3 | 100%
PKG-002 | DEL-02-01 | 3400 | CAD | 58882 | 3 | 100%
PKG-002 | DEL-02-01 | 3500 | CAD | 9490 | 1 | 100%
PKG-002 | DEL-02-01 | 3600 | CAD | 11520 | 1 | 100%
PKG-002 | DEL-02-02 | 03-CONCRETE | CAD | 30829 | 6 | 100%
PKG-002 | DEL-02-02 | 09-FINISHES | CAD | 62850 | 26 | 100%
PKG-002 | DEL-02-02 | 10-SPECIALTIES | CAD | 92600 | 3 | 100%
PKG-002 | DEL-02-02 | 11-EQUIPMENT | CAD | 55000 | 1 | 100%
PKG-002 | DEL-02-02 | 22-PLUMBING | CAD | 18000 | 1 | 100%
PKG-002 | DEL-02-02 | 23-MECH | CAD | 20000 | 1 | 100%
PKG-002 | DEL-02-03 | 21.03.01 | CAD | 31850 | 3 | 100%
PKG-002 | DEL-02-03 | 21.03.02 | CAD | 40188 | 4 | 100%
PKG-002 | DEL-02-03 | 21.03.03 | CAD | 34000 | 2 | 100%
PKG-002 | DEL-02-03 | 21.03.04 | CAD | 95060 | 12 | 100%
PKG-002 | DEL-02-03 | 21.03.05 | CAD | 11298 | 11 | 100%
PKG-002 | DEL-02-04 | 03-CONCRETE | CAD | 370390 | 8 | 100%
PKG-002 | DEL-02-04 | 05-STEEL | CAD | 461668 | 4 | 100%
PKG-002 | DEL-02-04 | 07-ENVELOPE | CAD | 554790 | 6 | 100%
PKG-002 | DEL-02-04 | 08-OPENINGS | CAD | 249100 | 6 | 100%
PKG-002 | DEL-02-04 | 09-FLOORING | CAD | 58520 | 2 | 100%
PKG-002 | DEL-02-04 | 31-EARTHWORK | CAD | 6000 | 1 | 100%
PKG-002 | DEL-02-04 | 50-DESIGN | CAD | 20801 | 1 | 100%
PKG-002 | DEL-02-05 | 23-COMM | CAD | 18000 | 1 | 100%
PKG-002 | DEL-02-05 | 23-CTRL | CAD | 72000 | 1 | 100%
PKG-002 | DEL-02-05 | 23-EQUP | CAD | 49000 | 3 | 100%
PKG-002 | DEL-02-05 | 23-EXHS | CAD | 144000 | 2 | 100%
PKG-002 | DEL-02-05 | 23-FPRT | CAD | 108000 | 1 | 100%
PKG-002 | DEL-02-05 | 23-HVAC | CAD | 435200 | 3 | 100%
PKG-002 | DEL-02-05 | 23-MECH-DESIGN | CAD | 24295 | 1 | 100%
PKG-002 | DEL-02-05 | 23-PLMB | CAD | 163600 | 4 | 100%
PKG-002 | DEL-02-06 | 26-00 | CAD | 333400 | 3 | 100%
PKG-002 | DEL-02-06 | 26-10 | CAD | 12000 | 1 | 100%
PKG-002 | DEL-02-06 | 26-50 | CAD | 173800 | 3 | 100%
PKG-002 | DEL-02-06 | 26-80 | CAD | 8000 | 1 | 100%
PKG-002 | DEL-02-06 | 26-90 | CAD | 15486 | 1 | 100%
PKG-002 | DEL-02-06 | 27-00 | CAD | 80250 | 3 | 100%
PKG-002 | DEL-02-06 | 27-50 | CAD | 20000 | 1 | 100%
PKG-002 | DEL-02-07 | 26-EMRG-DES | CAD | 5000 | 1 | 100%
PKG-002 | DEL-02-07 | 26-EMRG-DIST | CAD | 18000 | 1 | 100%
PKG-002 | DEL-02-07 | 26-EMRG-DOOR | CAD | 16000 | 1 | 100%
PKG-002 | DEL-02-07 | 26-EMRG-GEN | CAD | 162000 | 2 | 100%
PKG-003 | DEL-03-01 | 03-DESIGN | CAD | 13500 | 1 | 100%
PKG-003 | DEL-03-01 | 03-SURVEY | CAD | 5000 | 1 | 100%
PKG-003 | DEL-03-02 | 03-02-CLR | CAD | 32010 | 2 | 100%
PKG-003 | DEL-03-02 | 03-02-DRN | CAD | 74500 | 3 | 100%
PKG-003 | DEL-03-02 | 03-02-DSN | CAD | 11514 | 1 | 100%
PKG-003 | DEL-03-02 | 03-02-ESC | CAD | 22000 | 1 | 100%
PKG-003 | DEL-03-02 | 03-02-EW | CAD | 178038 | 5 | 100%
PKG-003 | DEL-03-02 | 03-02-FIN | CAD | 110000 | 1 | 100%
PKG-003 | DEL-03-02 | 03-02-GEO | CAD | 32000 | 1 | 100%
PKG-003 | DEL-03-02 | 03-02-SRV | CAD | 12000 | 1 | 100%
PKG-003 | DEL-03-03 | 03.03.AGG | CAD | 390000 | 3 | 100%
PKG-003 | DEL-03-03 | 03.03.ASP-HD | CAD | 200000 | 2 | 100%
PKG-003 | DEL-03-03 | 03.03.ASP-LD | CAD | 208000 | 2 | 100%
PKG-003 | DEL-03-03 | 03.03.CONC | CAD | 83230 | 4 | 100%
PKG-003 | DEL-03-03 | 03.03.MARK | CAD | 3150 | 2 | 100%
PKG-003 | DEL-03-03 | 03.03.SITE | CAD | 12000 | 1 | 100%
PKG-003 | DEL-03-04 | 31.00 | CAD | 3730 | 1 | 100%
PKG-003 | DEL-03-04 | 31.40 | CAD | 41000 | 4 | 100%
PKG-003 | DEL-03-04 | 31.41 | CAD | 31000 | 2 | 100%
PKG-003 | DEL-03-04 | 31.42 | CAD | 16800 | 1 | 100%
PKG-003 | DEL-03-04 | 31.43 | CAD | 38400 | 2 | 100%
PKG-003 | DEL-03-04 | 31.44 | CAD | 12000 | 1 | 100%
PKG-003 | DEL-03-04 | 31.45 | CAD | 10000 | 1 | 100%
PKG-003 | DEL-03-04 | 31.49 | CAD | 35000 | 1 | 100%
PKG-003 | DEL-03-04 | 31.50 | CAD | 39000 | 5 | 100%
PKG-003 | DEL-03-05 | PROF_SERVICES | CAD | 26500 | 2 | 100%
PKG-003 | DEL-03-05 | REGULATORY_FEES | CAD | 16970 | 3 | 100%
PKG-004 | DEL-04-01 | 04.01.DESIGN | CAD | 10000 | 1 | 100%
PKG-004 | DEL-04-01 | 04.01.SHELL | CAD | 192000 | 1 | 100%
PKG-004 | DEL-04-02 | 03-Concrete | CAD | 13776 | 2 | 100%
PKG-004 | DEL-04-02 | 07-Thermal | CAD | 1286 | 2 | 100%
PKG-004 | DEL-04-02 | 08-Doors | CAD | 36750 | 8 | 100%
PKG-004 | DEL-04-03 | 02-Sitework | CAD | 11140 | 2 | 100%
PKG-004 | DEL-04-03 | 03-Concrete | CAD | 75514 | 5 | 100%
PKG-004 | DEL-04-03 | 05-Metals | CAD | 63600 | 2 | 100%
PKG-004 | DEL-04-03 | 31-Earthwork | CAD | 6684 | 1 | 100%
PKG-004 | DEL-04-04 | 23-VENT | CAD | 18000 | 1 | 100%
PKG-004 | DEL-04-04 | 26-ELEC | CAD | 36000 | 1 | 100%
PKG-005 | DEL-05-01 | CBS-0500-ENVR | CAD | 12000 | 1 | 100%
PKG-005 | DEL-05-01 | CBS-0500-EQUIP | CAD | 95000 | 1 | 100%
PKG-005 | DEL-05-01 | CBS-0500-PLMB | CAD | 16000 | 1 | 100%
PKG-005 | DEL-05-02 | 26-COND | CAD | 8000 | 1 | 100%
PKG-005 | DEL-05-02 | 26-ELEC | CAD | 90000 | 1 | 100%
PKG-005 | DEL-05-03 | 26 05 00 | CAD | 45000 | 1 | 100%
PKG-005 | DEL-05-04 | 26-SECURITY | CAD | 50000 | 1 | 100%
PKG-005 | DEL-05-04 | 26-SECURITY-MONITORING | CAD | 5400 | 1 | 100%
PKG-005 | DEL-05-05 | 09-SIGNAGE-FAB | CAD | 34000 | 2 | 100%
PKG-005 | DEL-05-06 | CBS-EQP | CAD | 14100 | 5 | 100%
PKG-005 | DEL-05-06 | CBS-INST | CAD | 4500 | 1 | 100%
PKG-005 | DEL-05-07_Optional-FFandE-Allowance | FF&E | CAD | 20000 | 1 | 100%

## BOE_Index
FromDeliverableID | FromPackageID | DeclaredBasis | FallbackPolicy | AllowMixed | ActualMethodsUsed | RunStatus | RunContextPath
DEL-01-01 | PKG-001 | RATE_TABLE | STRICT | FALSE | RATE_TABLE | OK | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-01_2026-02-18_1200/Run_Context.md
DEL-01-02 | PKG-001 | RATE_TABLE | ALLOW_ALLOWANCE | TRUE | ALLOWANCE, RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-02_2026-02-18_2100/Run_Context.md
DEL-01-03 | PKG-001 | RATE_TABLE | ALLOW_ALLOWANCE | TRUE | ALLOWANCE, RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-03_2026-02-18_2100/Run_Context.md
DEL-01-04 | PKG-001 | RATE_TABLE | ALLOW_ALLOWANCE | TRUE | ALLOWANCE, RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-04_2026-02-18_1400/Run_Context.md
DEL-01-05 | PKG-001 | RATE_TABLE | STRICT | FALSE | RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-05_2026-02-18_0000/Run_Context.md
DEL-01-06 | PKG-001 | RATE_TABLE | ALLOW_ALLOWANCE | TRUE | ALLOWANCE, RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-06_2026-02-18_2100/Run_Context.md
DEL-01-07 | PKG-001 | RATE_TABLE | STRICT | FALSE | RATE_TABLE | OK | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-07_2026-02-18_1830/Run_Context.md
DEL-02-01 | PKG-002 | RATE_TABLE | STRICT | FALSE | RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-01_2026-02-18_2100/Run_Context.md
DEL-02-02 | PKG-002 | RATE_TABLE | ALLOW_ALLOWANCE | TRUE | ALLOWANCE, RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-02_2026-02-18_1036/Run_Context.md
DEL-02-03 | PKG-002 | RATE_TABLE | ALLOW_ALLOWANCE | TRUE | ALLOWANCE, RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-03_2026-02-18_1100/Run_Context.md
DEL-02-04 | PKG-002 | RATE_TABLE | STRICT | FALSE | RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Run_Context.md
DEL-02-05 | PKG-002 | RATE_TABLE | STRICT | FALSE | RATE_TABLE | OK | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-05_2026-02-18_1400/Run_Context.md
DEL-02-06 | PKG-002 | RATE_TABLE | STRICT | FALSE | RATE_TABLE | OK | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-06_2026-02-18_1500/Run_Context.md
DEL-02-07 | PKG-002 | QUOTE | ALLOW_ALLOWANCE | TRUE | ALLOWANCE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Run_Context.md
DEL-03-01 | PKG-003 | RATE_TABLE | STRICT | FALSE | RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-01_2026-02-18_1900/Run_Context.md
DEL-03-02 | PKG-003 | RATE_TABLE | STRICT | FALSE | RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-02_2026-02-18_1130/Run_Context.md
DEL-03-03 | PKG-003 | RATE_TABLE | STRICT | FALSE | RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-03_2026-02-18_1200/Run_Context.md
DEL-03-04 | PKG-003 | RATE_TABLE | ALLOW_ALLOWANCE | TRUE | ALLOWANCE, RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-04_2026-02-18_2100/Run_Context.md
DEL-03-05 | PKG-003 | RATE_TABLE | ALLOW_ALLOWANCE | TRUE | ALLOWANCE, RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-05_2026-02-18_2000/Run_Context.md
DEL-04-01 | PKG-004 | PARAMETRIC | ALLOW_ALLOWANCE | TRUE | ALLOWANCE, PARAMETRIC | OK | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-01_2026-02-18_1200/Run_Context.md
DEL-04-02 | PKG-004 | RATE_TABLE | STRICT | FALSE | RATE_TABLE | OK | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Run_Context.md
DEL-04-03 | PKG-004 | RATE_TABLE | STRICT | FALSE | RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-03_2026-02-18_1400/Run_Context.md
DEL-04-04 | PKG-004 | RATE_TABLE | STRICT | FALSE | RATE_TABLE | OK | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-04_2026-02-18_1500/Run_Context.md
DEL-05-01 | PKG-005 | QUOTE | ALLOW_ALLOWANCE | TRUE | ALLOWANCE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-01_2026-02-18_1500/Run_Context.md
DEL-05-02 | PKG-005 | RATE_TABLE | STRICT | FALSE | RATE_TABLE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-02_2026-02-18_1600/Run_Context.md
DEL-05-03 | PKG-005 | QUOTE | ALLOW_ALLOWANCE | TRUE | PARAMETRIC | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-03_2026-02-18_1700/Run_Context.md
DEL-05-04 | PKG-005 | QUOTE | ALLOW_ALLOWANCE | TRUE | PARAMETRIC | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-04_2026-02-18_1800/Run_Context.md
DEL-05-05 | PKG-005 | QUOTE | ALLOW_ALLOWANCE | TRUE | ALLOWANCE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-05_2026-02-18_1800/Run_Context.md
DEL-05-06 | PKG-005 | QUOTE | STRICT | FALSE | QUOTE | WARNINGS | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-06_2026-02-18_1900/Run_Context.md
DEL-05-07 | PKG-005 | ALLOWANCE | STRICT | FALSE | ALLOWANCE | OK | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-07_2026-02-18_2200/Run_Context.md

## Coverage
FromPackageID | FromDeliverableID | FromDeliverableName | DetailPath | RunContextPath | AssumptionsPath | RisksPath | SchemaStatus | Notes
PKG-001 | DEL-01-01 | Integrated Design Management & Submission Packages | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-01_2026-02-18_1200/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-01_2026-02-18_1200/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-01_2026-02-18_1200/Assumptions_Log.md | NOT_PRESENT | OK
PKG-001 | DEL-01-02 | Baseline Schedule, Updates & Reporting | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-02_2026-02-18_2100/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-02_2026-02-18_2100/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-02_2026-02-18_2100/Assumptions_Log.md | NOT_PRESENT | OK
PKG-001 | DEL-01-03 | Health & Safety Plan | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-03_2026-02-18_2100/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-03_2026-02-18_2100/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-03_2026-02-18_2100/Assumptions_Log.md | NOT_PRESENT | OK
PKG-001 | DEL-01-04 | Permitting, Inspections & AHJ Coordination | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-04_2026-02-18_1400/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-04_2026-02-18_1400/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-04_2026-02-18_1400/Assumptions_Log.md | NOT_PRESENT | OK
PKG-001 | DEL-01-05 | Meetings, Documentation & Change Control | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-05_2026-02-18_0000/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-05_2026-02-18_0000/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-05_2026-02-18_0000/Assumptions_Log.md | NOT_PRESENT | OK
PKG-001 | DEL-01-06 | Site Supervision, Logistics & Housekeeping | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-06_2026-02-18_2100/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-06_2026-02-18_2100/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-06_2026-02-18_2100/Assumptions_Log.md | NOT_PRESENT | OK
PKG-001 | DEL-01-07 | Commissioning, Closeout & Warranty | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-07_2026-02-18_1830/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-07_2026-02-18_1830/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-07_2026-02-18_1830/Assumptions_Log.md | NOT_PRESENT | OK
PKG-002 | DEL-02-01 | Architectural Program, Layout & Code Planning | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-01_2026-02-18_2100/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-01_2026-02-18_2100/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-01_2026-02-18_2100/Assumptions_Log.md | NOT_PRESENT | OK
PKG-002 | DEL-02-02 | Firehall Apparatus Bays & Support Spaces | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-02_2026-02-18_1036/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-02_2026-02-18_1036/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-02_2026-02-18_1036/Assumptions_Log.md | NOT_PRESENT | OK
PKG-002 | DEL-02-03 | Public Works Shop Bays & Support Spaces | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-03_2026-02-18_1100/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-03_2026-02-18_1100/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-03_2026-02-18_1100/Assumptions_Log.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-03_2026-02-18_1100/Risk_Register.md | OK
PKG-002 | DEL-02-04 | Structure, Envelope, Roof & Overhead Doors | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md | NOT_PRESENT | OK
PKG-002 | DEL-02-05 | Mechanical, Plumbing, Ventilation & Exhaust | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-05_2026-02-18_1400/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-05_2026-02-18_1400/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-05_2026-02-18_1400/Assumptions_Log.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-05_2026-02-18_1400/Risk_Register.md | OK
PKG-002 | DEL-02-06 | Electrical Power, Lighting, IT/Telecom & PA | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-06_2026-02-18_1500/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-06_2026-02-18_1500/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-06_2026-02-18_1500/Assumptions_Log.md | NOT_PRESENT | OK
PKG-002 | DEL-02-07 | Emergency Power & Backup Generator | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Assumptions_Log.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Risk_Register.md | OK
PKG-003 | DEL-03-01 | Site Plan, Circulation & Parking Design | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-01_2026-02-18_1900/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-01_2026-02-18_1900/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-01_2026-02-18_1900/Assumptions_Log.md | NOT_PRESENT | OK
PKG-003 | DEL-03-02 | Earthworks, Grading & Drainage | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-02_2026-02-18_1130/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-02_2026-02-18_1130/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-02_2026-02-18_1130/Assumptions_Log.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-02_2026-02-18_1130/Risk_Register.md | OK
PKG-003 | DEL-03-03 | Paving, Surfacing & Site Improvements | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-03_2026-02-18_1200/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-03_2026-02-18_1200/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-03_2026-02-18_1200/Assumptions_Log.md | NOT_PRESENT | OK
PKG-003 | DEL-03-04 | Underground Utilities & Service Connections | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-04_2026-02-18_2100/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-04_2026-02-18_2100/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-04_2026-02-18_2100/Assumptions_Log.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-04_2026-02-18_2100/Risk_Register.md | OK
PKG-003 | DEL-03-05 | Environmental, Regulatory & Permitting | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-05_2026-02-18_2000/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-05_2026-02-18_2000/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-05_2026-02-18_2000/Assumptions_Log.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-05_2026-02-18_2000/Risk_Register.md | OK
PKG-004 | DEL-04-01 | Cold Storage Building Shell (60x100 ft PEMB) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-01_2026-02-18_1200/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-01_2026-02-18_1200/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-01_2026-02-18_1200/Assumptions_Log.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-01_2026-02-18_1200/Risk_Register.md | OK
PKG-004 | DEL-04-02 | Cold Storage Doors, Openings & Hardware | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Assumptions_Log.md | NOT_PRESENT | OK
PKG-004 | DEL-04-03 | Cold Storage Foundation & Floor Slab | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-03_2026-02-18_1400/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-03_2026-02-18_1400/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-03_2026-02-18_1400/Assumptions_Log.md | NOT_PRESENT | OK
PKG-004 | DEL-04-04 | Cold Storage Electrical & Ventilation | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-04_2026-02-18_1500/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-04_2026-02-18_1500/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-04_2026-02-18_1500/Assumptions_Log.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-04_2026-02-18_1500/Risk_Register.md | OK
PKG-005 | DEL-05-01 | Option: Built-In Vehicle Wash Bay | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-01_2026-02-18_1500/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-01_2026-02-18_1500/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-01_2026-02-18_1500/Assumptions_Log.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-01_2026-02-18_1500/Risk_Register.md | OK
PKG-005 | DEL-05-02 | Option: Yard Lighting | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-02_2026-02-18_1600/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-02_2026-02-18_1600/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-02_2026-02-18_1600/Assumptions_Log.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-02_2026-02-18_1600/Risk_Register.md | OK
PKG-005 | DEL-05-03 | Option: Access Control System | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-03_2026-02-18_1700/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-03_2026-02-18_1700/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-03_2026-02-18_1700/Assumptions_Log.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-03_2026-02-18_1700/Risk_Register.md | OK
PKG-005 | DEL-05-04 | Option: Security Camera System | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-04_2026-02-18_1800/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-04_2026-02-18_1800/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-04_2026-02-18_1800/Assumptions_Log.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-04_2026-02-18_1800/Risk_Register.md | OK
PKG-005 | DEL-05-05 | Option: Town Branding Signage | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-05_2026-02-18_1800/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-05_2026-02-18_1800/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-05_2026-02-18_1800/Assumptions_Log.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-05_2026-02-18_1800/Risk_Register.md | OK | 2 mutually exclusive scenarios (primary=$12k non-illuminated; alternate=$22k illuminated)
PKG-005 | DEL-05-06 | Option: Kitchen & Laundry Appliances | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-06_2026-02-18_1900/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-06_2026-02-18_1900/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-06_2026-02-18_1900/Assumptions_Log.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-06_2026-02-18_1900/Risk_Register.md | OK
PKG-005 | DEL-05-07 | Option: FF&E Cash Allowance | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-07_2026-02-18_2200/Detail.csv | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-07_2026-02-18_2200/Run_Context.md | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-07_2026-02-18_2200/Assumptions_Log.md | NOT_PRESENT | OK

## Assumptions
AssumptionUID | FromDeliverableID | AssumptionID | Title | Assumption | Source | SourcePath
DEL-01-01::ASM-001 | DEL-01-01 | ASM-001 | Project Duration | Construction duration is 18 months (NTP to Substantial Performance). | Assumed_Project_Parameters.csv, PP-01 (Source=ASSUMPTION, Confidence=MEDIUM). | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-01_2026-02-18_1200/Assumptions_Log.md
DEL-01-01::ASM-002 | DEL-01-01 | ASM-002 | Design Phase Duration | Design phase duration is 4 months. | Assumed_Project_Parameters.csv, PP-02 (Source=ASSUMPTION, Confidence=MEDIUM). | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-01_2026-02-18_1200/Assumptions_Log.md
DEL-01-01::ASM-003 | DEL-01-01 | ASM-003 | Staff Rates Are Market-Basis Estimates | Hourly rates in Professional_Staff_Rates.csv are representative market rates for Alberta, not negotiated/contracted rates. | Professional_Staff_Rates.csv, Basis=MARKET for all roles, Confidence=MEDIUM. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-01_2026-02-18_1200/Assumptions_Log.md
DEL-01-01::ASM-004 | DEL-01-01 | ASM-004 | Level of Effort Is Parametric | Hour estimates in Level_of_Effort.csv are parametric (based on typical project effort distribution), not based on detailed task-level work breakdown. | Level_of_Effort.csv, Basis=PARAMETRIC for all rows. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-01_2026-02-18_1200/Assumptions_Log.md
DEL-01-01::ASM-005 | DEL-01-01 | ASM-005 | No Escalation or Inflation Factor | Rates are current (no escalation applied for future periods). | Professional_Staff_Rates.csv contains no escalation column or date-based adjustment. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-01_2026-02-18_1200/Assumptions_Log.md
DEL-01-02::ASM-001 | DEL-01-02 | ASM-001 | Scheduler Hours Based on 18-Month Duration | Scheduler Hours Based on 18-Month Duration |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-02_2026-02-18_2100/Assumptions_Log.md
DEL-01-02::ASM-002 | DEL-01-02 | ASM-002 | PM Hours for Schedule Oversight Are Incremental | PM Hours for Schedule Oversight Are Incremental |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-02_2026-02-18_2100/Assumptions_Log.md
DEL-01-02::ASM-003 | DEL-01-02 | ASM-003 | Staff Rates Are Blended/Market Rates | Staff Rates Are Blended/Market Rates |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-02_2026-02-18_2100/Assumptions_Log.md
DEL-01-02::ASM-004 | DEL-01-02 | ASM-004 | Software/Tools Cost (UPDATED) | Scheduling software/tools cost estimated at $3,500 CAD as a parametric allowance for an 18-month project. Based on typical P6 Cloud or MS Project Online licensing. | Parametric estimate; no vendor quote or rate table | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-02_2026-02-18_2100/Assumptions_Log.md
DEL-01-07::ASM-0107 | DEL-01-07 | ASM-0107 | -001 Construction duration of 18 months | -001 Construction duration of 18 months | Assumed_Project_Parameters.csv, row PP-01. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-07_2026-02-18_1830/Assumptions_Log.md
DEL-01-07::ASM-0107 | DEL-01-07 | ASM-0107 | -002 Commissioning Lead hours breakdown | -002 Commissioning Lead hours breakdown | Level_of_Effort.csv, row DEL-01-07/R-21, Notes column. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-07_2026-02-18_1830/Assumptions_Log.md
DEL-01-07::ASM-0107 | DEL-01-07 | ASM-0107 | -003 Warranty period of 12 months | -003 Warranty period of 12 months | Datasheet.md > Deficiency Process Attributes; RFP section 7.6. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-07_2026-02-18_1830/Assumptions_Log.md
DEL-01-07::ASM-0107 | DEL-01-07 | ASM-0107 | -004 Document deliverables quantity | -004 Document deliverables quantity | Datasheet.md > Delivery Format Requirements; RFP section 7.5. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-07_2026-02-18_1830/Assumptions_Log.md
DEL-01-07::ASM-0107 | DEL-01-07 | ASM-0107 | -005 Rates are current and un-escalated | -005 Rates are current and un-escalated | Professional_Staff_Rates.csv, Basis=MARKET. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-07_2026-02-18_1830/Assumptions_Log.md
DEL-01-07::ASM-0107 | DEL-01-07 | ASM-0107 | -006 No disbursements or third-party costs included | -006 No disbursements or third-party costs included | PRICE_SOURCES contain only labor rates and hours; no disbursement schedule provided. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-01-07_2026-02-18_1830/Assumptions_Log.md
DEL-02-04::ASM-01 | DEL-02-04 | ASM-01 | Building Footprint Area | Main PSB ground floor area is 18,000 sf (1,672 m2), based on functional program layout with 4 fire bays + 4 PW bays + office/admin + support spaces, with approximate dimensions ~160 ft x 110 ft. | PP-05 (Assumed_Project_Parameters.csv) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-02 | DEL-02-04 | ASM-02 | Building Perimeter | Building perimeter is approximately 540 lf (165 lm), based on ~160 ft x 110 ft rectangular footprint. | Derived from PP-05 dimensional notes | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-03 | DEL-02-04 | ASM-03 | Bay Area | Total bay area (fire apparatus + PW shop) is approximately 12,000 sf (1,115 m2), based on 8 bays at approximately 1,500 sf each. | Derived from PP-11 (4 fire bays) + PP-12 (4 PW bays); bay size estimated from 16x16 ft doors + circulation/work space | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-04 | DEL-02-04 | ASM-04 | Office/Shared Area | Office and shared space area is approximately 6,000 sf (557 m2), calculated as 18,000 sf total minus 12,000 sf bay area. | Derived from PP-05 minus ASM-03 | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-05 | DEL-02-04 | ASM-05 | Average Wall Height | Average exterior wall height is 6.5 m (21.3 ft), accommodating 16 ft minimum clear door height plus structural depth and parapet. | Derived from SOW-0215 (16 ft min clear height) plus assumed structural depth and parapet | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-06 | DEL-02-04 | ASM-06 | Gross Wall Area | Gross exterior wall area is approximately 1,073 m2 (perimeter 165 lm x average height 6.5 m). | Derived from ASM-02 x ASM-05 | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-07 | DEL-02-04 | ASM-07 | Screw Pile Count | 48 screw piles at approximately 3.5 m spacing around perimeter and at interior column lines. | Typical spacing for steel-framed institutional building on screw pile foundations; consistent with SC-14 description for Penhold soils | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-08 | DEL-02-04 | ASM-08 | Pile Cap / Grade Beam Concrete Volume | Total concrete volume for pile caps and grade beams is 38 m3 (48 caps x ~0.4 m3 average + ~19 m3 grade beams). | Typical pile cap dimensions for screw pile foundations; grade beam between perimeter piles | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-09 | DEL-02-04 | ASM-09 | Foundation Formwork (Pile Caps + Grade Beams) | 180 m2 of formwork for pile caps and grade beams combined. | Estimated from 48 caps x ~2 m2/cap + grade beam faces | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-10 | DEL-02-04 | ASM-10 | Foundation Wall Formwork | Perimeter frost wall/stem wall formwork is 165 m2 (165 lm x ~1.0 m height average, both sides). | Typical frost wall depth for Penhold, AB climate | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-11 | DEL-02-04 | ASM-11 | Reinforcing Steel Quantity (Foundations) | 4,800 kg of reinforcing steel for foundation system (~100 kg per pile cap average including grade beam rebar). | Typical reinforcing ratios for pile caps and grade beams | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-12 | DEL-02-04 | ASM-12 | Anchor Bolt Count | 96 anchor bolts (2 per pile cap x 48 piles). | Minimum 2 anchor bolts per column base plate; conservative (some may require 4) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-13 | DEL-02-04 | ASM-13 | Primary Steel Tonnage | Primary structural steel (W-shapes and HSS) is approximately 42,000 kg (~25 kg/m2 of building footprint x 1,672 m2). | Typical steel intensity for single-storey steel-framed institutional/municipal buildings with clear-span bays. Range is typically 20-30 kg/m2; 25 kg/m2 used as mid-range. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-14 | DEL-02-04 | ASM-14 | Miscellaneous Steel | 3,500 kg of miscellaneous steel (stairs, handrails, platforms, embed plates, lintels). | Typical for building of this size; ~2 kg/m2 of footprint | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-15 | DEL-02-04 | ASM-15 | Net Wall Panel Area (Insulated Metal Panels) | 730 m2 of insulated metal wall panels. Calculated as: gross wall area (1,073 m2) minus masonry base (200 m2) minus glazing/window openings (54 m2) minus overhead door openings (8 doors x ~23.5 m2/door = ~188 m2). Net = 1,073 - 200 - 54 - 188 = ~631 m2. Adjusted upward to 730 m2 to account for panel waste, returns at openings, and soffit areas. | Derived from ASM-06 minus deductions; waste/returns factor applied | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-16 | DEL-02-04 | ASM-16 | Masonry Base Course Area | 200 m2 of 200mm CMU base course at approximately 1.2 m height around the full perimeter (165 lm x 1.2 m). | Typical for municipal/institutional metal buildings with impact-resistant masonry base | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-17 | DEL-02-04 | ASM-17 | Flashing and Trim Length | 380 lm of metal flashing and trim (corners, drip edges, window heads/sills, parapet cap, base flashing). Approximately 2.3x the building perimeter to account for multiple runs. | Typical for insulated metal panel buildings | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-18 | DEL-02-04 | ASM-18 | Sealant Length | 520 lm of perimeter sealant at all openings, joints, and panel transitions. Approximately 3.1x the building perimeter. | Typical for insulated metal panel buildings with multiple opening types | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-19 | DEL-02-04 | ASM-19 | Glazing Area | 54 m2 of commercial glazing, approximately 5% of gross wall area. | Typical for municipal operations facility; lower glazing ratio than office buildings due to bay/shop functions | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-20 | DEL-02-04 | ASM-20 | Storefront Entries | 2 storefront entries (main public entry + secondary entry). | Typical for combined fire hall / public works building with separate public-facing and operational entries | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-21 | DEL-02-04 | ASM-21 | Person Door Count (Single) | 12 single hollow metal person doors for bay access, service exits, and code-required egress. | Estimated based on 8 bays requiring egress doors + additional service/exterior doors per code requirements | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-22 | DEL-02-04 | ASM-22 | Person Door Count (Double) | 2 sets of double hollow metal doors at main corridor/bay transitions. | Typical for separation between office/admin and bay areas in firehall/PW buildings | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-04::ASM-23 | DEL-02-04 | ASM-23 | Sump Rough-In Rate | Sump rough-in (blockout in structural slab) is estimated at $750 per location. This covers formwork, blockout framing, and PVC sleeve cast into the 200mm slab. The sump assembly, oil/water separator, and plumbing connection costs are excluded (DEL-02-05 scope per cost ownership rules). | Not directly from rate tables. Informed by MS-10 (bay sump assembly at $4,500 complete) with rough-in estimated as approximately 15-20% of complete assembly cost. This is a LOW confidence assumption. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-04_2026-02-18_1130/Assumptions_Log.md
DEL-02-07::ASM-001 | DEL-02-07 | ASM-001 | Generator Runtime = 72 Hours | Generator Runtime = 72 Hours |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Assumptions_Log.md
DEL-02-07::ASM-002 | DEL-02-07 | ASM-002 | Generator Size = 100-150 kW | Generator Size = 100-150 kW |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Assumptions_Log.md
DEL-02-07::ASM-003 | DEL-02-07 | ASM-003 | Diesel Fuel Type | Diesel Fuel Type |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Assumptions_Log.md
DEL-02-07::ASM-004 | DEL-02-07 | ASM-004 | Single Generator (Not Redundant) | Single Generator (Not Redundant) |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Assumptions_Log.md
DEL-02-07::ASM-005 | DEL-02-07 | ASM-005 | Emergency Distribution Scope | Emergency Distribution Scope |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Assumptions_Log.md
DEL-02-07::ASM-006 | DEL-02-07 | ASM-006 | Door Backup Mechanism — 8 Doors at $2,000 Each | Door Backup Mechanism — 8 Doors at $2,000 Each |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Assumptions_Log.md
DEL-02-07::ASM-007 | DEL-02-07 | ASM-007 | Installation Labour Hours | Installation Labour Hours |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Assumptions_Log.md
DEL-02-07::ASM-008 | DEL-02-07 | ASM-008 | Design Fee Basis | Design Fee Basis |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Assumptions_Log.md
DEL-04-02::ASM-01 | DEL-04-02 | ASM-01 | Overhead Door Supply Price Includes Opener | Overhead Door Supply Price Includes Opener |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Assumptions_Log.md
DEL-04-02::ASM-02 | DEL-04-02 | ASM-02 | Person Doors are Standard Single-Leaf Commercial | Person Doors are Standard Single-Leaf Commercial |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Assumptions_Log.md
DEL-04-02::ASM-03 | DEL-04-02 | ASM-03 | Overhead Door Hardware Supplement | Overhead Door Hardware Supplement |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Assumptions_Log.md
DEL-04-02::ASM-04 | DEL-04-02 | ASM-04 | Concrete Apron Dimensions | Concrete Apron Dimensions |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Assumptions_Log.md
DEL-04-02::ASM-05 | DEL-04-02 | ASM-05 | Perimeter Sealant Lengths | Perimeter Sealant Lengths |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Assumptions_Log.md
DEL-04-02::ASM-06 | DEL-04-02 | ASM-06 | Weatherstrip Allowance Beyond Sealant | Weatherstrip Allowance Beyond Sealant |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Assumptions_Log.md
DEL-04-02::ASM-07 | DEL-04-02 | ASM-07 | Overhead Door Installation Labour | Overhead Door Installation Labour |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Assumptions_Log.md
DEL-04-02::ASM-08 | DEL-04-02 | ASM-08 | Person Door Installation Labour | Person Door Installation Labour |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Assumptions_Log.md
DEL-04-02::ASM-09 | DEL-04-02 | ASM-09 | Concrete Apron Installation Labour and Blended Rate | Concrete Apron Installation Labour and Blended Rate |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Assumptions_Log.md
DEL-04-02::ASM-10 | DEL-04-02 | ASM-10 | Emergency Exit Light Unit Rate | Emergency Exit Light Unit Rate |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Assumptions_Log.md
DEL-04-02::ASM-11 | DEL-04-02 | ASM-11 | Weatherproof Light Switch Unit Rate | Weatherproof Light Switch Unit Rate |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-02_2026-02-18_1100/Assumptions_Log.md

## Risks
RiskUID | FromDeliverableID | RiskID | Title | Description | Likelihood | Impact | SourcePath | Likelihood_Level | Impact_Level
DEL-02-03::RSK-001 | DEL-02-03 | RSK-001 | Scope Boundary | Locker room and support space fit-up may be claimed by DEL-02-01 (general interior) during aggregation, resulting in double-counting or gaps at the project level. | MEDIUM | HIGH ($95,060 at risk -- 44.8% of estimate) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-03_2026-02-18_1100/Risk_Register.md | MEDIUM | HIGH
DEL-02-03::RSK-002 | DEL-02-03 | RSK-002 | Area Uncertainty | Support space areas are assumed, not confirmed. Actual floor plan may differ significantly, especially for locker room (1,200 sf assumed) which drives the largest CBS category. | HIGH | MEDIUM ($15,000 +/- range on locker room lines) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-03_2026-02-18_1100/Risk_Register.md | HIGH | MEDIUM
DEL-02-03::RSK-003 | DEL-02-03 | RSK-003 | Allowance Accuracy | 5 ALLOWANCE items ($60,500 total) are based on professional judgment, not competitive pricing. Actual costs could vary +/- 40%. | MEDIUM | MEDIUM ($24,000 +/- range) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-03_2026-02-18_1100/Risk_Register.md | MEDIUM | MEDIUM
DEL-02-03::RSK-004 | DEL-02-03 | RSK-004 | Wash Bay Option | If Owner selects optional wash bay (SOW-0500), one PW bay is replaced, reducing bay count from 4 to 3. This reduces bay-area-driven costs by ~25% but adds wash bay conversion costs (separate DEL-05-01 estimate). | LOW | LOW ($13,000 reduction in DEL-02-03) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-03_2026-02-18_1100/Risk_Register.md | LOW | LOW
DEL-02-03::RSK-005 | DEL-02-03 | RSK-005 | Missing Scope | Items that could arguably belong to DEL-02-03 but were excluded per cost ownership rules: overhead doors ($80,000), HVAC/ventilation ($44,000+), electrical ($14/sf on 8,400 sf = ~$118,000), bay sumps ($18,000). Total excluded scope: ~$260,000. If cost ownership rules change, this estimate would increase significantly. | LOW | HIGH (potential 2x increase) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-03_2026-02-18_1100/Risk_Register.md | LOW | HIGH
DEL-02-05::RSK-01 | DEL-02-05 | RSK-01 | Fire protection may not be required by AHJ, leading to over-estimation of $108,000 | MEDIUM | HIGH ($108k / 10.7% of total) | AHJ confirmation during design phase; estimate clearly flags this as conditional with LOW confidence | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-05_2026-02-18_1400/Risk_Register.md | HIGH | HIGH
DEL-02-05::RSK-02 | DEL-02-05 | RSK-02 | Actual building zone areas differ from assumed 6,400/6,400/5,200 split | MEDIUM | MEDIUM (~$15-20k per 10% area shift) | Validate against architectural layout from DEL-02-01 when available; rerun estimate | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-05_2026-02-18_1400/Risk_Register.md | MEDIUM | MEDIUM
DEL-02-05::RSK-03 | DEL-02-05 | RSK-03 | Compressed air scope boundary (CON-M-01) resolution could add scope to DEL-02-05 | LOW | MEDIUM ($55,000 if breathing air system added per MS-08) | Brief excludes compressed air from DEL-02-05; if boundary ruling changes, add MS-08 pricing | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-05_2026-02-18_1400/Risk_Register.md | MEDIUM | MEDIUM
DEL-02-05::RSK-04 | DEL-02-05 | RSK-04 | BAS/controls scope may be broader or narrower than full-building application | LOW | MEDIUM ($20k-$72k range depending on coverage) | Confirm BAS scope during design; adjust L-11 area as needed | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-05_2026-02-18_1400/Risk_Register.md | MEDIUM | MEDIUM
DEL-02-07::RISK-001 | DEL-02-07 | RISK-001 | Generator System Cost Exceeds Allowance | Generator System Cost Exceeds Allowance |  |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Risk_Register.md
DEL-02-07::RISK-002 | DEL-02-07 | RISK-002 | Scope Creep on Essential Loads List | Scope Creep on Essential Loads List |  |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Risk_Register.md
DEL-02-07::RISK-003 | DEL-02-07 | RISK-003 | Double-Counting with Adjacent Deliverables | Double-Counting with Adjacent Deliverables |  |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Risk_Register.md
DEL-02-07::RISK-004 | DEL-02-07 | RISK-004 | Seismic Anchorage Requirement | Seismic Anchorage Requirement |  |  | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-02-07_2026-02-18_1600/Risk_Register.md
DEL-03-04::RSK-001 | DEL-03-04 | RSK-001 | Actual utility run lengths significantly differ from assumed 120 m / 40 m due to actual stub locations and building siting | MEDIUM | HIGH | +/-$30,000 to $40,000 | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-04_2026-02-18_2100/Risk_Register.md | HIGH | HIGH
DEL-03-04::RSK-002 | DEL-03-04 | RSK-002 | DEC-004 tie-in allowance ($35,000) is insufficient to cover actual tie-in execution costs | MEDIUM | MEDIUM | +$15,000 (if actual = $50,000 high end of UU-12 range) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-04_2026-02-18_2100/Risk_Register.md | MEDIUM | MEDIUM
DEL-03-04::RSK-003 | DEL-03-04 | RSK-003 | Utility connection fees exceed recommended parametric values | MEDIUM | LOW | +$10,000 to $20,000 | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-04_2026-02-18_2100/Risk_Register.md | LOW | LOW
DEL-03-04::RSK-004 | DEL-03-04 | RSK-004 | Cold Storage Building requires additional utility services (sanitary, telecom) not currently included | LOW | LOW | +$17,000 (sanitary $13K + telecom $4K) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-04_2026-02-18_2100/Risk_Register.md | LOW | LOW
DEL-03-04::RSK-005 | DEL-03-04 | RSK-005 | Common trench double-counting (UU-09 cost additive to individual utility rates which include trench) | LOW | LOW | -$10,000 (overstatement) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-04_2026-02-18_2100/Risk_Register.md | LOW | LOW
DEL-03-04::RSK-006 | DEL-03-04 | RSK-006 | Unknown underground conditions (rock, contamination, high water table) increase trenching costs | LOW | HIGH | +$20,000 to $50,000 | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-04_2026-02-18_2100/Risk_Register.md | HIGH | HIGH
DEL-03-05::RSK-01 | DEL-03-05 | RSK-01 | AEPA conditions of Water Act approval impose additional mitigation requirements (e.g., construction-phase environmental monitoring, post-construction monitoring, additional setback buffers) that require consultant services beyond FP-17 scope. | MEDIUM | MEDIUM ($10,000-$30,000 additional) | Confirm AEPA application status early in design phase; request pre-consultation with AEPA to scope conditions. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-05_2026-02-18_2000/Risk_Register.md | MEDIUM | MEDIUM
DEL-03-05::RSK-02 | DEL-03-05 | RSK-02 | 2021 Wetland Assessment and Environmental Assessment have lapsed or are deemed insufficient by AEPA, requiring new assessments. | LOW-MEDIUM | HIGH ($15,000-$30,000+ for new assessments + new ABWRET-A calculation) | Confirm with AEPA whether 2021 reports remain accepted as basis for Water Act application. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-05_2026-02-18_2000/Risk_Register.md | HIGH | HIGH
DEL-03-05::RSK-03 | DEL-03-05 | RSK-03 | ABWRET-A wetland replacement fee has been recalculated by AEPA at a different amount than the 2021 figure of $10,769.54. | LOW | LOW-MEDIUM (delta could be +/- $2,000-$5,000) | Confirm current ABWRET-A fee with AEPA or through updated assessment. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-05_2026-02-18_2000/Risk_Register.md | LOW-MEDIUM | LOW-MEDIUM
DEL-03-05::RSK-04 | DEL-03-05 | RSK-04 | Town of Penhold imposes additional flood fringe development conditions requiring additional environmental consultant effort or additional regulatory applications. | LOW-MEDIUM | MEDIUM ($5,000-$15,000) | Engage Town planning department early to confirm flood fringe development requirements. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-05_2026-02-18_2000/Risk_Register.md | MEDIUM | MEDIUM
DEL-03-05::RSK-05 | DEL-03-05 | RSK-05 | Upstream DEL-03-02 outputs reveal that stormwater discharge points or earthwork volumes near the flood fringe require additional environmental assessment or regulatory coordination. | MEDIUM | MEDIUM ($5,000-$15,000) | Coordinate DEL-03-02 and DEL-03-05 concurrently; flag any flood fringe earthwork volumes for environmental review. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-03-05_2026-02-18_2000/Risk_Register.md | MEDIUM | MEDIUM
DEL-04-01::RISK-001 | DEL-04-01 | RISK-001 | Market | PEMB manufacturer pricing may differ from parametric rate ($32/sf) due to steel market volatility, lead times, or regional supply constraints. | MEDIUM | MEDIUM ($24,000 variance at range endpoints: $168K to $210K) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-01_2026-02-18_1200/Risk_Register.md | MEDIUM | MEDIUM
DEL-04-01::RISK-002 | DEL-04-01 | RISK-002 | Scope | PB-01 parametric rate may exclude minor shell components (e.g., specialized flashing, snow guards, fall protection anchors) that could be required for code compliance. | LOW | LOW (estimated $2,000-$8,000 for add-on items) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-01_2026-02-18_1200/Risk_Register.md | LOW | LOW
DEL-04-01::RISK-003 | DEL-04-01 | RISK-003 | Design | Design engineering allowance ($10,000) may be insufficient if cold storage configuration requires more coordination effort than typical (e.g., complex aesthetic integration, specialized structural analysis). | LOW | LOW ($5,000-$10,000 additional) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-04-01_2026-02-18_1200/Risk_Register.md | LOW | LOW
DEL-05-02::RSK-001 | DEL-05-02 | RSK-001 | Actual pole quantity significantly differs from assumed 12 (could be 6-20 depending on site layout and spacing requirements) | MEDIUM | HIGH (total cost scales linearly at $7,500/pole) | Provide scaling formula to Owner; present as unit rate so total adjusts transparently | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-02_2026-02-18_1600/Risk_Register.md | HIGH | HIGH
DEL-05-02::RSK-002 | DEL-05-02 | RSK-002 | Conduit run distance materially longer or shorter than 100 lm assumed | MEDIUM | MEDIUM (fixed cost changes at $80/lm; +/- $2,000-$4,000 likely range) | Update when site plan from DEL-03-01 is available | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-02_2026-02-18_1600/Risk_Register.md | MEDIUM | MEDIUM
DEL-05-02::RSK-003 | DEL-05-02 | RSK-003 | Parametric-origin rates ($7,500/pole; $80/lm) may not reflect actual supplier pricing at time of procurement | LOW-MEDIUM | MEDIUM (source range: $6,500-$9,000/pole; $65-$95/lm) | Obtain supplier quotes before final submission; consider using PriceMax for conservative estimate | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-02_2026-02-18_1600/Risk_Register.md | MEDIUM | MEDIUM
DEL-05-02::RSK-004 | DEL-05-02 | RSK-004 | Soil conditions or underground obstructions increase conduit installation cost | LOW | LOW-MEDIUM | Geotech investigation and utility locate as part of site development (DEL-03-02) would inform | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-02_2026-02-18_1600/Risk_Register.md | LOW-MEDIUM | LOW-MEDIUM
DEL-05-03::RSK-001 | DEL-05-03 | RSK-001 | Actual zone count exceeds 10 once DEL-02-01 floor plan is finalized | MEDIUM | Each additional zone adds ~$3,200 (range $2,500-$4,000 per OPT-07). 5 extra zones = ~$16,000 increase. | Re-run estimate with confirmed zone count once DEL-02-01 is available. Carry OPT-07 per-zone rate for sensitivity analysis. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-03_2026-02-18_1700/Risk_Register.md | MEDIUM
DEL-05-03::RSK-002 | DEL-05-03 | RSK-002 | Parametric pricing significantly understates or overstates actual vendor quote | MEDIUM | OPT-06 range is $35,000-$55,000 (57% spread). Vendor quote could fall outside this range. | Replace with vendor quote as soon as available. Flag to Owner that this is a placeholder estimate. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-03_2026-02-18_1700/Risk_Register.md | MEDIUM
DEL-05-03::RSK-003 | DEL-05-03 | RSK-003 | Scope boundary disputes at interface with DEL-02-06 (electrical/IT) | LOW | Conduit, low-voltage power, or network costs may be double-counted or missed between deliverables if interface is not clearly coordinated. | Enforce cost ownership rules from brief. Coordinate with DEL-02-06 estimate during aggregation. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-03_2026-02-18_1700/Risk_Register.md | LOW
DEL-05-03::RSK-004 | DEL-05-03 | RSK-004 | Owner elects both access control (DEL-05-03) and security cameras (DEL-05-04), requiring integration | LOW | Integration costs (shared head-end, software, wiring synergies) are not priced. Could be a cost savings or additional cost depending on system selection. | If both options are elected, re-scope for integration opportunities per Guidance.md. | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-03_2026-02-18_1700/Risk_Register.md | LOW
DEL-05-04::RSK-01 | DEL-05-04 | RSK-01 | Camera count changes significantly once floor plan is finalized (DEL-02-01) | MEDIUM | MEDIUM -- price range for OPT-08 is $40k-$60k; more cameras could exceed range | Re-estimate after DEL-02-01 layout is available; obtain vendor quote with actual camera schedule | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-04_2026-02-18_1800/Risk_Register.md | MEDIUM | MEDIUM
DEL-05-04::RSK-02 | DEL-05-04 | RSK-02 | Scope boundary between camera system (DEL-05-04) and IT infrastructure (DEL-02-06) is unclear for network equipment | MEDIUM | MEDIUM -- potential for double-count or cost gap in network switches/PoE | Coordinate DEL-05-04 and DEL-02-06 estimates; define explicit scope split for network equipment before final pricing | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-04_2026-02-18_1800/Risk_Register.md | MEDIUM | MEDIUM
DEL-05-04::RSK-03 | DEL-05-04 | RSK-03 | Parametric pricing significantly under- or over-estimates actual vendor quote | HIGH | HIGH -- all lines are LOW confidence; OPT-08 range spans $20k ($40k-$60k) | Replace parametric pricing with competitive vendor quotes as soon as possible | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-04_2026-02-18_1800/Risk_Register.md | HIGH | HIGH
DEL-05-04::RSK-04 | DEL-05-04 | RSK-04 | Monitoring service pricing does not reflect actual contract terms (multi-year, escalation, service levels) | MEDIUM | LOW -- annual cost is $5,400; variance within $3,600-$7,200 range | Obtain monitoring service proposals; confirm contract structure (annual vs multi-year) | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-04_2026-02-18_1800/Risk_Register.md | LOW | LOW
DEL-05-04::RSK-05 | DEL-05-04 | RSK-05 | Integration with access control (DEL-05-03) adds unpriced cost if both options are elected | LOW | LOW -- integration cost likely modest relative to system total | If both options are elected, add integration line item in a future estimate revision | /Users/ryan/ai-env/projects/chirality-app-test/test/execution-6a/_Estimates/EST_DEL-05-04_2026-02-18_1800/Risk_Register.md | LOW | LOW

## BOE_Collection
Basis of Estimate Collection (Project Level)
# Basis of Estimate Collection -- Project Level ## Overview This document collects the basis-of-estimate evidence from all 30 deliverable-level estimate snapshots. The authoritative per-deliverable source is each snapshot's `Run_Context.md`. This collection is a convenience index for project-level review. **Project:** Town of Penhold -- Public Services Building (PSB) **Currency:** CAD **Base Year:** 2024 **BOE Strategy Document:** `_Estimates/BASIS_OF_ESTIMATE.md` --- ## Basis Summary by Package ### PKG-001 -- General Requirements & Delivery Controls All 7 deliverables use `BASIS_OF_ESTIMATE = RATE_TABLE` with rates from `Professional_Staff_Rates.csv` and hours from `Level_of_Effort.csv`. Permit fees in DEL-01-04 use ALLOWANCE method (authorized by `FALLBACK_POLICY=ALLOW_ALLOWANCE`). **Update (2130 snapshot):** DEL-01-02, DEL-01-03, and DEL-01-06 were re-estimated with `FALLBACK_POLICY=ALLOW_ALLOWANCE` to resolve previously-TBD line items. DEL-01-02 added 1 ALLOWANCE line (scheduling software $3,500). DEL-01-03 added 2 ALLOWANCE lines (training $4,500 + PPE/signage $3,500). DEL-01-06 added 2 ALLOWANCE lines (temporary facilities $35,000 + site cleaning $25,000). All 5 ALLOWANCE lines are LOW confidence parametric allowances authorized by DEC-EST-005 in the source snapshots. ¦ DEL ¦ Declared Basis ¦ Actual Methods ¦ Fallback Policy ¦ Run Status ¦ ¦---¦---¦---¦---¦---¦ ¦ DEL-01-01 ¦ RATE_TABLE ¦ RATE_TABLE ¦ STRICT ¦ OK ¦ ¦ DEL-01-02 ¦ RATE_TABLE ¦ ALLOWANCE, RATE_TABLE ¦ ALLOW_ALLOWANCE ¦ WARNINGS ¦ ¦ DEL-01-03 ¦ RATE_TABLE ¦ ALLOWANCE, RATE_TABLE ¦ ALLOW_ALLOWANCE ¦ WARNINGS ¦ ¦ DEL-01-04 ¦ RATE_TABLE ¦ ALLOWANCE, RATE_TABLE ¦ ALLOW_ALLOWANCE ¦ WARNINGS ¦ ¦ DEL-01-05 ¦ RATE_TABLE ¦ RATE_TABLE ¦ STRICT ¦ WARNINGS ¦ ¦ DEL-01-06 ¦ RATE_TABLE ¦ ALLOWANCE, RATE_TABLE ¦ ALLOW_ALLOWANCE ¦ WARNINGS ¦ ¦ DEL-01-07 ¦ RATE_TABLE ¦ RATE_TABLE ¦ STRICT ¦ OK ¦ **Key price sources:** Professional_Staff_Rates.csv, Level_of_Effort.csv, Assumed_Project_Parameters.csv, Fees_Permits_Insurance.csv --- ### PKG-002 -- Main Public Services Building 6 of 7 deliverables use `BASIS_OF_ESTIMATE = RATE_TABLE`. DEL-02-07 declares `QUOTE` but falls back to `ALLOWANCE` (no vendor quote available). **Update (2130 snapshot):** DEL-02-01 was re-estimated with the new `Interior_Architectural_Rates.csv` price source (PS-27). All 7 previously-TBD lines (partitions, floor finishes, ceiling, accessibility, wayfinding signage, paint, and interior design fees) are now priced using RATE_TABLE method. DEL-02-01 total increased from $47,200 to $168,329 (+$121,129 / +256%). Fallback policy remains STRICT as all lines use RATE_TABLE. ¦ DEL ¦ Declared Basis ¦ Actual Methods ¦ Fallback Policy ¦ Run Status ¦ ¦---¦---¦---¦---¦---¦ ¦ DEL-02-01 ¦ RATE_TABLE ¦ RATE_TABLE ¦ STRICT ¦ WARNINGS ¦ ¦ DEL-02-02 ¦ RATE_TABLE ¦ ALLOWANCE, RATE_TABLE ¦ ALLOW_ALLOWANCE ¦ WARNINGS ¦ ¦ DEL-02-03 ¦ RATE_TABLE ¦ ALLOWANCE, RATE_TABLE ¦ ALLOW_ALLOWANCE ¦ WARNINGS ¦ ¦ DEL-02-04 ¦ RATE_TABLE ¦ RATE_TABLE ¦ STRICT ¦ WARNINGS ¦ ¦ DEL-02-05 ¦ RATE_TABLE ¦ RATE_TABLE ¦ STRICT ¦ OK ¦ ¦ DEL-02-06 ¦ RATE_TABLE ¦ RATE_TABLE ¦ STRICT ¦ OK ¦ ¦ DEL-02-07 ¦ QUOTE ¦ ALLOWANCE ¦ ALLOW_ALLOWANCE ¦ WARNINGS ¦ **Key price sources:** Structural_Concrete_Rates.csv, Building_Envelope_Rates.csv, Interior_Architectural_Rates.csv, Equipment_Pricing.csv, Mechanical_System_Rates.csv, Electrical_System_Rates.csv, Construction_Labour_Rates.csv, Professional_Design_Fees.csv --- ### PKG-003 -- Site & Civil Works All 5 deliverables use `BASIS_OF_ESTIMATE = RATE_TABLE`. Several include ALLOWANCE fallback lines for fees and tie-in costs. ¦ DEL ¦ Declared Basis ¦ Actual Methods ¦ Fallback Policy ¦ Run Status ¦ ¦---¦---¦---¦---¦---¦ ¦ DEL-03-01 ¦ RATE_TABLE ¦ RATE_TABLE ¦ STRICT ¦ WARNINGS ¦ ¦ DEL-03-02 ¦ RATE_TABLE ¦ RATE_TABLE ¦ STRICT ¦ WARNINGS ¦ ¦ DEL-03-03 ¦ RATE_TABLE ¦ RATE_TABLE ¦ STRICT ¦ WARNINGS ¦ ¦ DEL-03-04 ¦ RATE_TABLE ¦ ALLOWANCE, RATE_TABLE ¦ ALLOW_ALLOWANCE ¦ WARNINGS ¦ ¦ DEL-03-05 ¦ RATE_TABLE ¦ ALLOWANCE, RATE_TABLE ¦ ALLOW_ALLOWANCE ¦ WARNINGS ¦ **Key price sources:** Earthwork_Civil_Rates.csv, Paving_Surfacing_Rates.csv, Underground_Utility_Rates.csv, Fees_Permits_Insurance.csv, Professional_Design_Fees.csv --- ### PKG-004 -- Cold Storage Building 4 deliverables. DEL-04-01 uses PARAMETRIC basis (shell rate x area). Others use RATE_TABLE. ¦ DEL ¦ Declared Basis ¦ Actual Methods ¦ Fallback Policy ¦ Run Status ¦ ¦---¦---¦---¦---¦---¦ ¦ DEL-04-01 ¦ PARAMETRIC ¦ ALLOWANCE, PARAMETRIC ¦ ALLOW_ALLOWANCE ¦ OK ¦ ¦ DEL-04-02 ¦ RATE_TABLE ¦ RATE_TABLE ¦ STRICT ¦ OK ¦ ¦ DEL-04-03 ¦ RATE_TABLE ¦ RATE_TABLE ¦ STRICT ¦ WARNINGS ¦ ¦ DEL-04-04 ¦ RATE_TABLE ¦ RATE_TABLE ¦ STRICT ¦ OK ¦ **Key price sources:** Parametric_Building_Rates.csv, Structural_Concrete_Rates.csv, Building_Envelope_Rates.csv, Equipment_Pricing.csv, Construction_Labour_Rates.csv, Electrical_System_Rates.csv, Mechanical_System_Rates.csv --- ### PKG-005 -- Optional Priced Items Mixed basis across deliverables. Several use QUOTE with ALLOWANCE fallback. DEL-05-03 and DEL-05-04 use PARAMETRIC. ¦ DEL ¦ Declared Basis ¦ Actual Methods ¦ Fallback Policy ¦ Run Status ¦ ¦---¦---¦---¦---¦---¦ ¦ DEL-05-01 ¦ QUOTE ¦ ALLOWANCE ¦ ALLOW_ALLOWANCE ¦ WARNINGS ¦ ¦ DEL-05-02 ¦ RATE_TABLE ¦ RATE_TABLE ¦ STRICT ¦ WARNINGS ¦ ¦ DEL-05-03 ¦ QUOTE ¦ PARAMETRIC ¦ ALLOW_ALLOWANCE ¦ WARNINGS ¦ ¦ DEL-05-04 ¦ QUOTE ¦ PARAMETRIC ¦ ALLOW_ALLOWANCE ¦ WARNINGS ¦ ¦ DEL-05-05 ¦ QUOTE ¦ ALLOWANCE ¦ ALLOW_ALLOWANCE ¦ WARNINGS ¦ ¦ DEL-05-06 ¦ QUOTE ¦ QUOTE ¦ STRICT ¦ WARNINGS ¦ ¦ DEL-05-07 ¦ ALLOWANCE ¦ ALLOWANCE ¦ STRICT ¦ OK ¦ **Key price sources:** Optional_Items_Pricing.csv --- ## Method Mix Summary (All 266 Priced Lines) ¦ Method ¦ Lines ¦ Amount (CAD) ¦ % of Amount ¦ ¦---¦---¦---¦---¦ ¦ RATE_TABLE ¦ 220 ¦ $6,216,696 ¦ 86.1% ¦ ¦ ALLOWANCE ¦ 36 ¦ $692,150 ¦ 9.6% ¦ ¦ PARAMETRIC ¦ 4 ¦ $292,400 ¦ 4.1% ¦ ¦ QUOTE ¦ 6 ¦ $18,600 ¦ 0.3% ¦ ¦ TBD (unpriced) ¦ 0 ¦ -- ¦ -- ¦ --- ## Confidence Summary (266 Priced Lines) ¦ Confidence ¦ Lines ¦ Amount (CAD) ¦ ¦---¦---¦---¦ ¦ HIGH ¦ 2 ¦ $30,770 ¦ ¦ MED / MEDIUM ¦ 216 ¦ $6,118,156 ¦ ¦ LOW ¦ 48 ¦ $1,070,920 ¦ The LOW-confidence lines are concentrated in: - PKG-005 optional items (ALLOWANCE/PARAMETRIC; no vendor quotes) - DEL-02-07 emergency generator (ALLOWANCE; no vendor quote) - DEL-03-02 earthwork quantities (assumed cut/fill volumes) - DEL-03-04 utility connection fees and tie-in allowances - DEL-01-02 scheduling software allowance ($3,500) - DEL-01-03 training and PPE allowances ($8,000) - DEL-01-06 temporary facilities and site cleaning allowances ($60,000)

## Lists
Packages | Deliverables | Methods | Confidence
All | All | All | All
PKG-001 | DEL-01-01 | ALLOWANCE | HIGH
PKG-002 | DEL-01-02 | PARAMETRIC | LOW
PKG-003 | DEL-01-03 | QUOTE | MED
PKG-004 | DEL-01-04 | RATE_TABLE | MEDIUM
PKG-005 | DEL-01-05
DEL-01-06
DEL-01-07
DEL-02-01
DEL-02-02
DEL-02-03
DEL-02-04
DEL-02-05
DEL-02-06
DEL-02-07
DEL-03-01
DEL-03-02
DEL-03-03
DEL-03-04
DEL-03-05
DEL-04-01
DEL-04-02
DEL-04-03
DEL-04-04
DEL-05-01
DEL-05-02
DEL-05-03
DEL-05-04
DEL-05-05
DEL-05-06
DEL-05-07